## Sam Lee
PRS Residencies - sesssion schedule
SAM LEE
[5 empty] | Jack D | Sam Pirt | Richard O'Neil | Belinda & Heidi
Sam Lee visits | dates |  | no days
| 14 & 15 Nov 2016 | Initial visit, Traveller sites, planning meeting | 2
| Thurs 2 & Fri 3 Feb | Visit Trinity House, Visit R Smith, Meet Sam Pirt | 2 | [7 empty] | 108.34
| Tues 14 Feb | Jack Durtnall to meet schools |  |  | 1
| Fri 24 Feb | Jack Durtnall to attend CPD with James Redwood |  |  | 1
| Tues 7 Mar | Workshops start with Jack D Trinity Academy |  |  | 1
| Wed 8 Mar | am Trinity Academy, pm Buckingham Primary with Jack D |  |  | 1
| Tues 14 Mar | Trinity Academy, Sam Lee with Jack D and Richard O'Neil | 1 |  | 1 |  | 1
| Wed 15 Mar | am Trinity Academy, pm Buckingham Primary Sam Lee with Jack D and Richard O'Neil | 1 |  | 1 |  | 1
| Tues 4 Apr | Trinity Academy with Jack D, Sam Pirt |  |  | 1 | 1
| Wed 5 Apr | am Trinity Academy, pm Buckingham Primary with Jack D, Sam Pirt |  |  | 1 | 1
| Tues 25 April | Trinity Academy with Jack D, Sam Pirt |  |  | 1 | 1
| Wed 26 Apr | am Trinity Academy, pm Buckingham Primary with Jack D, Sam Pirt |  |  | 1 | 1
| Tues 9 May | Trinity Academy with Sam Lee, Jack D, Belinda & Heidi | 1 |  | 1 |  |  | 2
| Wed 10 May | am Trinity Academy, pm Buckingham Primary with Sam Lee, Jack D, Belinda & Heidi | 1 |  | 1 |  |  | 2
| Tues 23 May | Trinity Academy with Sam Lee, Jack D and Sam Pirt | 1 |  | 1 | 1
| Wed 24 May | am Trinity Academy, pm Buckingham Primary with Sam Lee, Jack D & Sam Pirt | 1 |  | 1 | 1
| Tues 13 Jun | Trinity Academy with Jack D |  |  | 1
| Wed 14 June | am Trinity Academy, pm Buckingham Primary with Jack D |  |  | 1
| Fri 23 Jun | Rehearsals - venue to be confirmed - with Sam Lee, Jack D & Sam Pirt | 1 |  | 1 | 1
| Sat 24 June | Showcase performance at Hull City Hall, with Sam Lee, Jack D & Sam Pirt | 1 |  | 1 | 1
| Sun 2 July | Festival performance, Princes Quay, with Sam Lee, Jack D, Richard, Belinda and Heidi | 1 |  | 1 | 1 | 1 | 1
|  | TOTAL | 13 |  | 19 | 9 | 3 | 5 |  | 0
| 2017-02-02 | W/C 6 FEB | 2017-02-14 | HALF TERM | 28 FEB & 1 MAR | W/C 6 MAR | 14 & 15 MAR | 21 & 22 MAR | W/C 27 MAR | 4 & 5 APR | EASTER | 25 & 26 APR | W/C 1 MAY | 9 & 10 MAY | W/C 15 MAY | 22 & 23 MAY | HALF TERM | W/C 5 JUN | 13 & 14 JUN | W/C 19 JUN | 23 & 24 June | 27 & 28 JUNE | 2017-07-02
JACK DURTNALL | [15 empty] | FINISH & SUBMIT FINAL PIECE
SAM LEE
GUEST |  |  |  |  | SAM PIRT |  |  |  |  | SAM PIRT |  | SAM PIRT | [8 empty] | SAM PIRT - Sat |  | SAM PIRT
Topic | [6 empty] | GUEST ARTIST - RICHARD O'NEIL | [6 empty] | GUEST ARTIST - BELINDA & HEIDI |  |  |  |  | rehearsal |  | Rehearsal Fri / Perf to other comm groups Sat |  | Performance
Jack total | 1 |  | 1 |  | 2 |  | 2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 1 |  | 2 |  | 1 | 18
Sam lee Total | 1 | [5 empty] | 2 | [6 empty] | 2 |  | 2 |  |  |  |  | 2 |  | 1 | 10
Sam Pirt |  |  |  |  | 2 |  |  |  |  | 2 |  | 2 |  |  |  | 2 |  |  |  |  | 1 |  | 1 | 10
Richard | [6 empty] | 2 | [15 empty] | 1 | 3
Heidi & Belinda | [13 empty] | 4 | [8 empty] | 1 | 5
Note on B31: SL up early 2nd, leave night of 3rd -Polly Eldridge

## Jason Singh
PRS Residencies - sesssion schedule
JASON SINGH
|  |  | Jason | Jez Riley French
Jason Singh visits | dates |  | no days
| 2016-11-09 |  | 1
| 2016-12-15 | Masterclass | 1
| 2017-02-27 | query availability | 1
| 2017-02-28 | Warren meeting | 1
| 2017-03-13 |  | 1
| 2017-03-14 | Warren MC/RAP session with Paul Clark tbc | 1
|  | Jez with a naval ship - sound recording - tbc |  | 1
| 2017-03-27 | Meet Seniors | 1
| 2017-03-28 |  | 1
| 2017-04-10 | Easter Holidays | 1
| 2017-04-11 | Sound recording session with Jez and The Warren | 1 | 1
| 2017-04-24 |  | 1
| 2017-04-25 | Warren | 1
| 2017-05-08 |  | 1
| 2017-05-09 | Warren | 1
| 2017-05-22 |  | 1
| 2017-05-23 | All audio to be ready for programming by Kinicho | 1
| 2017-06-05 | Rehearsal with all artists for composed piece | 1
| 2017-06-06 | Warren/ Rehearsal with all artists for composed piece | 1
2017-06-24
|  | TOTAL | 18

## Eliza Carthy
PRS Residencies - sesssion schedule
ELIZA CARTHY
ELIZA CARTHY | dates |  | no days
| 2016-09-14 |  | 1 | Visit - planning and introductions
Wed | 2017-02-08 |  | 1 | Walton St Market am walkabout, Indoor Market,
Mon | 2017-02-13 | 9-11am | 1 | Wyke College, music and creative writing students together in one session – contact Ben Newton and Jamie Farrow (one of them will be waiting in reception at Wyke College for you just before 9am)
|  | 1:00-3:15pm |  | Spring Cottage Primary School (45 mins with Yr1 class followed by 45 mins with Yr5)
1.05-2.05 then 2.15-3.15
Spring Cottage Primary School, 13 Dressay Grove, Hull HU8 9JH
Contact: The Head, Andy Rhodes
|  | 5:30-6:30pm |  | Kingston Boxing club - informal chat with members of the club (They are uncomfortable about a workshop)
Hessle High Road, HU4 6 Hull (on north side of road before junction with Pickering Rd).
Contact Sean Smith who organises the club – he’s a great guy to talk to himself (ex fish filliter, his dad was a trawlerman, and he used to be a Union Activist) (tel 07504040058)
Thur | 2017-02-16 | 10:30am-12 noon | 1 | Boulevard Village Hall (community coffee morning group am)
Boulevard, Hull, HU3 2UE it’s next to the church (and there is a small car park beside the hall)
Your host is Eddy Bewsher (07748573124) another character
|  | 1:30pm |  | Visit Day Centre - Fernleigh Day Centre for the Elderly – waiting final confirmation this is OK
Contact Barbara Wright, Day Care Manager, Hull City Council
Fernleigh Day Centre, Waterloo Street, Hull, HU2 9LG
|  | 3:30pm |  | Workshop with volunteers and workers, Giroscope Housing Co-op
Giroscope Limited, 69 Coltman Street, Hull, HU3 2SJ
Liaison in advance is Sally, she’s not there on the day, but will brief volunteers to expect you, Eddy Bewsher will probably be there in this afternoon session as well. They have a room that fits 15 people, so it will be a cozy group.
Tel 01482 576374
Fri | 2017-02-17 | up until 2:15 | 1 | Morning at Trinity Market
|  | 3-4:30pm |  | ABP dock workers - at ABP Port House, Northern Gateway, Hull – HU9 5PQ (HU9 5NS for sat nav). Contact Louise Thackwray (Tel: 01472 246228¦ Mob: 07725 639462)
Fri | 2017-03-03 | 1-2:30pm and 3-4:30pm | 1 | Two afternoon workshops with Hull 2017 volunteers (30 in each session) – at the following times 1pm until 2:30pm and 3pm until 4:30pm (venue tbc)
|  | 6-7pm |  | Hindu Cultural Association - dancers (mixed ages),
Contact Uma Rajesh tel 07900 408655
Hindu Cultural Association, 7 Park St., Hull
| 2017-03-13 |  | 1 | working with Gary and Sam on music creation | at Eliza's Studio, Robin Hood's Bay
| 2017-03-14 |  | 1 | working with Gary and Sam on music creation, joined by Sarah Dew (PhD composition student) | at Eliza's Studio, Robin Hood's Bay
| 2017-03-15 |  | 1 | working with Gary and Sam on music creation | at Eliza's Studio, Robin Hood's Bay

## Errollyn Wallen
PRS Residencies - session schedule and planning
ERROLLYN WALLEN
Errollyn Wallen | dates | Detail | no days | EWB | Sarah | Michael Harper | Mambo? | Gary H | Nola marshall | Orch X | Students
Thurs | 2017-01-26 | Visit Open Doors, meet key contacts working in the community, event showcasing musical achievements of local groups working with Open Doors, meet staff of Pearson and Thoresby Primary Schools at Thoresby Primary school, possibly meet local supporting artists - tbc | 1 | x6 hrs meeting & planning |  |  | 3 hrs meeting
Fri | 2017-01-27 | planning and meet supporting artists/ student morning | 1
Thurs | 2017-03-09 | Thoresby am , Open Doors visit, Errollyn, Em, Pete and Frankie | 1 | 1 |  |  | 1
Fri | 2017-03-10 | Pearson Primary am tbc Errollyn and Em, planning with artists pm; Errollyn will perform at WOW Festival launch in the evening | 1 | 1
Sat | 2017-03-11 | Masterclass at Albemarle, Errollyn with Sarah Suckling part of WOW Festival | 1 |  | 1
Sun | 2017-03-12 | Errollyn to contribute to panel discussion as part of WOW
Thurs | 2017-03-23 | Thoresby Primary am Errollyn with Em and Gary, with Open Doors pm Errollyn with Gary | 1 | 0.5 |  |  |  | 1
Fri | 2017-03-24 | Pearson Primary am tbc - Gary alone | [5 empty] | 0.5
Thurs | 2017-04-06 | Pearson Primary am Open Doors pm Errollyn with Pete and Frankie | 1 |  |  |  | 1
| 2017-04-20 | Open Doors 10am-3pm - Gary Hammond alone | [5 empty] | 0.5
Tues | 2017-04-25 | Pearson at Thoresby am all day - Em and Mambo Jambo - twilight with parents |  | 1 |  |  | 1
Tues | 2017-05-02 | Thoresby at Pearson tbc all day - Mambo Jambo - twilight with parents |  |  |  |  | 1
thurs | 2017-05-11 | workshops Errollyn and Mambo Jambo | 1 | CANCEL??? |  |  | 1
Thurs | 2017-05-25 | Open Doors, plus in school workshop - Kaleidoscope week 2 at Thoresby with Errollyn, Em, Sarah, Mambo Jambo,and Gary | 1 | 1 | 1 |  | 1 | 1
Fri | 2017-05-26 | workshops in schools - finale of Kaleidoscope week at Thoresby with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 1 | 1 |  | 1 | 1
Thurs | 2017-06-15 | workshops open doors schools together 9-5 with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 1 | 1 |  | 1 | 1 |  | x
Thurs | 2017-06-22 | workshop coming together rehearsal 9-5, supporting musicians without Errollyn |  | 1 | 1 |  | 1 | 1 |  | x
| 2017-06-24 | Residency showcase day at Hull City Hall with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 1 | 1 |  | 1 | 1 |  | x
| 2017-06-29 | Rehearsal for supergroup moment 3.30 onwards with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 0.5 | 0.5 |  | 0.5 | 0.5 |  | x
| 2017-07-01 | Mighty River performance - 2pm
| 2017-07-02 | Performance at Festival weekend - residencies, with Errollyn, Em, Sarah, Mambo Jambo and Gary | 1 | 0.5 | 0.5 |  | 0.5 | 0.5 |  | x
|  | TOTAL of days | 14 | 9.5 | 7 | 0 | 11 | 8 |  | 5

## Brian Irvine
PRS Residencies - sesssion schedule
BRIAN IRVINE
BRIAN IRVINE | dates |  | no days
| 2016-11-30 |  | 1
Thurs | 2017-03-02 |  | 1
|  | Buckingham Day Centre pm from 12 noon ish |  | tbc
3:30/4pm 6pm Crossings at Emmaus
Fri | 2017-03-03 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS 1.05-2.05 then 2.15-3.15 pm
Thurs | 2017-04-06 |  | 1
|  | Buckingham Day Centre pm from 12 noon ish |  | tbc
|  | 3:30/4pm 6pm Crossings possibly at Emmaus |  | tbc
Fri | 2017-04-07 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS 1.05-2.05 then 2.15-3.15 pm
Thurs | 2017-05-04 |  | 1
|  | Buckingham Day Centre pm |  | tbc
3:30/4pm 6pm Crossings possibly at Emmaus
Fri | 2017-05-05 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS 1.05-2.05 then 2.15-3.15 pm
Thurs | 2017-05-25 |  | 1
|  | Buckingham Day Centre pm |  | tbc
3:30/4pm 6pm Crossings possibly at Emmaus
Fri | 2017-05-26 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Mersey PS 1.05-2.05 then 2.15-3.15 pm
Sats | 2017-05-27 | Albemarle Saturday masterclass | 1
Thurs | 2017-06-01 |  | 1
|  | Buckingham Day Centre pm |  | tbc
3:30/4pm 6pm Crossings possibly at Emmaus
Fri | 2017-06-02 | 10:30-12noon - Big Elastic Band - P&F Homes | 1
Thurs | 2017-06-22 | Groups coming together | 1
|  | Buckingham Day Centre pm |  | tbc
3:30/4pm 6pm Crossings possibly at Emmaus
Fri | 2017-06-23 | Groups coming together | 1
Sat | 2017-06-24 | Sharing event all day at Hull City Hall | 1
Thurs | 2017-06-28 | rehearsal | 1
Fri | 2017-06-29 | rehearsal | 1
Sun | 2017-07-02 | performance at NMB Festival | 1
|  | TOTAL | 18

## James Redwood CPD
James Redwood CPD sessions
CPD sessions for students and local musicians
Date | Venue | Details
Friday 4 November | University of Hull | am local leaders, pm joined by students
Friday 24th Feb | Albemarle Musci Centre | all day from 10am
Friday 21st April | Albemarle Musci Centre | all day from 10am

## Other relevant dates
Albemarle Saturdays
2016-03-11 | Errollyn Wallen
2016-04-08
2017-05-27 | Brian Irvine
2016-06-17
2016-07-08
2016-08-05
2016-09-09
2016-10-07
2016-11-04