Project Management Meeting 18.07.17

Attending: Katy, Sara, Lily

| To Do | Lead | Notes |
| --- | --- | --- |
| FAQs to Chris Marr | Lily | x |
| Peace Library – shipping costs and drawing costs for translated text | Sara |  |
| Install schedule and go back to Steve with further questions about breakdowns | Sara | x |
| Ferens closure press release – OK to go after amends and Tate have seen | Sara | x |
| Check with Partnerships if Friends of Ferens need to come to the TP opening | Lily |  |
| Resolve A Day in the Life charge question with Heritage Learning | Sara |  |
| Research Audio Guide equipment options for Access | Lily | x |
| Confirm whether we want to use the foyer outside Live Arts Space | Curators/Sara to confirm with Ferens |  |
| Cash flow for budget | Sara | x |

Build

Andrea Buettner

Still a couple of issues to be resolved for Andrea’s install;

- Tables – Will seems to think the copyright won’t be a problem, but we are waiting on images of the underside of the tables from Kordansky before we can get a definitive answer. If the copyright is not an issue, then we compare whether we should ship or make an exhibition copy of the tables.

- Fabric Wall – Andrea to be put in touch with David Kohn and not the actual fabricator. Daniel Slater from Tate agrees this is best.

- Peace Library – Andrea needs to provide sizes for shipping so we can get costs and we need to pay someone to re-draw the translated text. Sara to lead.

Hurvin Anderson

- Confirmed that we are not shipping any paintings that we do not intend to hang. Final shortlist coming from Hurvin in the next day or so.

Install Schedule

- Sara working on new install schedule

- Further questions to Steve – ask him to break down the costs and schedule further, why do they need two teams and what are they each working on and when

- Push Anna on press release and show to Tate once she has accepted our amends. Ben for final sign off in Katy’s absence.

Catalogue

Katy feedback received and passed back to Curators for redrafting. Main points are;

- Language clarity and comprehension – feels like curators talking to curators as it stands. Do we want to make it more accessible?

- The purpose of the introduction wasn’t clear

- Important to have an overview of all the different introductions and how they complement each other – Alex to submit his intro to us by the end of this week

Events

- Katy to catch up with Martin on the phone about the awards options. Lily to rephrase feast document.

- Opening event 6-9pm, speeches at 7pm.

Opening/Invite List

- Who from Ferens/HCAL needs to come? Are they part of the 300 number?

- Do Friends of Ferens need to come or can we have a separate event for them? Check in with Partnerships.

Learning programme

- A Day in the Life - Need to clarify how much Heritage Learning are charging and resolve this

- Need to clarify whether we are using the Live Art Space foyer. Curators need to confirm.

Access

- Have Ferens got their own audio guide equipment? LM to lead.

- Large print to go in to marketing costs

Budget

- Sara to work on cash flow this week and Lily to add breakdown of spends to budget once the re-journaling has gone through