## Org Chart
Roles and responsibilities & Work Stream _ Draft one: Discussion Doc.
Work Streams: lead and Sign off contact for stream. |  | Hull 2017 | Jason Bruges studios | Outside
Legal, contracting, partnerships.
Legal documentation: between all parties |  | Will Hutchinson/ Niccy Hallifax
Outside Planning Licensing |  | Chris Clay (L)
Event licensing |  | Chris clay (L)
Show Timing |  | Niccy Hallifax (L)
Legal (Venue) |  | Will Hutchinson (L)
Legal (Music : PRS & PPL) |  | Will Hutchinson/ Sam Hunt
Sound Interpritation |  | Sam Hunt
Liability & ownership (Post event) |  | NiccyHallifax / Sam Hunt
Artist engagement |  | Niccy Hallifax (L)
Crediting on Shows |  | Niccy Hallifax / Sam Hunt
Contracting of suppliers |  | Chris Clay / Niccy Hallifax
Contracting of talent |  | Niccy Hallifax / Sam Hunt
Venue Negotiation |  | Chris Clay/Niccy Hallifax
Insurance - Community outside event |  | TBD
Insurance (artists and staff) |  | TBD
Insurance (Production) |  | Chris Clay
Public liability |  | Chris Clay (L)
Partnerships | - | Liz Draper (L) |  |  | +
Creative, Production
Illustrations for the lifetime of the project. |  | Niccy Hallifax
Content development (wayfinding scenic) | - | Niccy Hallifax / Sam Hunt |  |  | +
Content -Education |  | Sam Hunt (L) / Ian Read
Creative, Art installation Production
Wayfinding and Design Look and feel |  | Niccy Hallifax
Logistics & operations | - | Chris Clay |  |  | +
Concept for marketing & PR assets |  | Sarah Moore / Ben McKnight
Floor Plan design and implementation | - | Niccy Hallifax (L)/ Chris Clay |  |  | +
Stakeholder Engagement | - | Niccy Hallifax |  |  | +
Social Media | - | Bethany Watson |  |  | +
Event Management |  | Haitham R / Laura B
Transport logistics | - | Chris Clay |  |  | +
Technical fit up | - | Chris Clay |  |  | +
Crowd management |  | Chris clay/NH/SH
Post Production | - | Niccy hallifax/Sam Hunt |  |  | +
Marketing & PR
Website: Joint across platforms | - | Bethany Watson |  |  | +
Print Management - outside of Show assets. | - | Sarah Moore / Niccy hallifax |  |  | +
Creation of assets |  | Sarah Moore
Marketing | - | Sarah Moore/ Phil Batty |  |  | +
PR | - | Ben McKnight/Clair |  |  | +
Filming for Legacy |  | Bethany Watson
Project management
Project Administration | - | Haitham R / Laura B |  |  | +
Venue management | - | Haitham R / Laura B |  |  | +
Open book accounting |  | Niccy hallifax / Glenn
Budget management | - | Niccy Hallifax |  |  | +
Post Evaluation |  | Eleainor Churchill
Approvers
Legal |  | Will Hutchinson
Budget |  | Niccy Hallifax/ Sam Hunt
Creative and Production |  | Niccy Hallifax/ Sam Hunt
Technical |  | Chris Clay
Digital |  | Niccy Hallifax/ Sam Hunt
Marketing and Community |  | Niccy Hallifax/ Sam Hunt