Slung Low: Producing Meeting: 21.03.2017

Present: Alan Lane (AL), Gareth Hughes (GH), Joanna Resnick (JR), Martin Green (MG), Martin Atkinson (MA), Lindsey Alvis (LA)

Artistic update

- Part Two will be 90 mins maximum but ideally 75 mins. Chorus are really important.

- Draft for part 3 arrived last week. AL to circulate.

- Read through of Part 3 this week. JR to invite Hull team.

- Lost TV Director. Noreen Kershaw is being talked to. AL thinks Noreen will say yes.

- Filming in June.

GH update about site management:

- Audience encouraged to use sustainable forms of transport to site.

- Parking at Deep if they need to drive.

- Walk route from the carpark will be along estuary. 15 – 20 minutes.

- Arrival 45 mins if driving. 30 mins if on Public Transport. MA to check geographic data of audience.

- Toilet use pre & post show being negotiated with The Deep. GH to pick this up.

- No toilets on site itself. Provision at community centre during show.

- £2000 for wayfinding and car park. Slung Low to confirm how much they have for site management. Hull2017 cover the rest. JR to confirm.

- Need to record non ticketed walk up each evening.

- Clearance to be taken from GH at car park followed by JR.

- Provisional request has been put in to volunteering. Meeting later today to discuss. Need to merge Hull & SL requests for this event. GH, MA & JR meeting today.

Site map

- GH to circulate.

Access

- Blue badge parking at the pub due to level access and disabled toilets. GH to pick this up.

- 5- 10 wheelchair spaces if possible. JR to confirm asap.

- Captioner & tech support confirmed for dress rehearsal. MA to confirm KCOM van with DW.

Residents dress rehearsal

- 400 residents attending.

- SL provided printed tickets which would be hard to duplicate.

- Potential to invite volunteers working on FOH & BO to watch the dress. JR to discuss with volunteering.

- BO to attend dress for info.

Invites/Press Night:

- Matt Burnham.

- Paul Hamlyn: Moira coming up.

- LA/MA to work out how many of 600 tickets can go back onsale & discuss with DW.

- LA/MA ask James Maguire/Ian Read re groups & education, incl Hull College Drama.

- SL to offer two tickets per community cast person. Capture email address & access requirements at time of booking so they can receive pre-show info. JR to manage this.

October Extension

- Options for extension discussed including running Part Two for a week and then two weeks of Parts Two & Four back to back.

- Discussion about ticket types, prices etc. LA to model options.

- Running the show back to back from 6:30pm-10:30pm.

- Site licence requires site to be cleared by 11pm.

- Make a decision on that last Friday of performance. Clear communication with designer & constructor on the extension with good notice, bringing forward their deadlines. JR to discuss with them in advance.

- Dates checked with KF & comparing to other Hull 2017 openings, w/c 18 is best. JR to check with full team and provisionally pencil with all.