| Assessment of: | No Boundaries & Middle Child Pub Quiz | Assessment carried out by: | Carys Tavener |
| --- | --- | --- | --- |
| Assessment number: | 001 | Position: | Junior Production Manager |
| Date: | 15/03/2017 | Review date: | 27.03.17 |

| No. | ACTIVITY & WHO IS AT RISK | HAZARDS PRESENT | EXISTING CONTROL MEASURES | No. at risk | Risk factors |  |  | FURTHER ACTION REQUIRED & BY WHOM | DATE OF ACTION |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Likelihood | Severity | Risk Level |  |  |
| 1. | Equipment Get-In/Out Crew, artists, volunteers and members of the public | Unloading a van from height Potential Outcomes: Falls leading to persons receiving physical injury from slight to moderate | Only suppliers who are experienced and competent are to unload from tail lift | 2 | 2 | 3 | LOW |  | 28.03.17 |
|  |  | Trip Hazards (cables etc.) Potential Outcomes: Persons receiving minor injuries: bruises, cuts, sprains | Ensure all items are tied and stored appropriately Ensure a clear path before moving equipment | 7 | 2 | 2 | LOW | CT to ensure cables are tied and stored before artists arrival | 28.03.17 |
| 2. | Manual Handling of heavy items Crew | Carrying and positioning equipment Potential Outcomes: Spinal and muscular injuries, as well as foot, and toe injuries if dropped | Only suppliers trained in manual handling to lift heavy items Where possible, supports during movement, such as flycases, are to be used | 2 | 2 | 3 | LOW |  | 28.03.17 |
| 3. | Installing temporary electrical items (PA systems, dimmers etc.) Crew, artists, members of the public, and volunteers | Faulty equipment or incorrect set-ups Potential Outcomes: Electric shocks and consequences of shocks e.g. falls from height | All equipment to be PAT tested Only suppliers who are competent and trained are to install devices | 7 | 1 | 4 | LOW |  | 28.03.17 |
|  |  | Cables across public spaces Potential Outcomes: Persons receiving minor injuries: bruises, cuts, sprains | Ensure all cables are taped down |  | 2 | 2 | LOW | CT to ensure cables are tied and stored before guests arrival | 28.03.17 |
| 4. | Raised temporary structure in reduced visibility Artists | Artists performing on raised surface Potential Outcome: Physical injury from trips and falls | No consumption of alcohol permitted by artists Artists will see dimensions and rehearse on the stage in performance state lighting prior to event White gaffer tape will be placed outlining the edges of the stage | 5 | 2 | 2 | LOW |  | 28.03.17 |
| 5. | Manual Build of Pub Flats Structure Crew and artists | Crew delivering, unloading, setting-up and securing, as well as working on, Pub Quiz Set Potential Outcome: Varying physical Injuries from minor to severe in cuts, entanglement, musculo-skeletal etc. | Risk Assessment has been completed by Production Manager responsible for build & checked by CT See Attached Appropriate PPE is to be worn at all times at work Only those experienced building the structure are to do so | 4 | 2 | 5 | MEDIUM | Production Manager responsible, AR, to inform CT of any changes to the Method Statement | 28.03.17 |
| 6. | Temporary Cabaret style seating arrangement with added furniture to current venue's provisions Crew, Staff, Artists, Members of the Public, Volunteers | Impractical and obstructive layout of furniture Potential Outcome: Possible restrictions in evacuation or nuisance and inconvenience for passage and movement | Venue staff have confirmed maximum capacity CT and venue staff to coordinate safe positions of furniture with regards to clear gangways, fire exits, and wheelchair movement |  | 2 | 5 | MEDIUM | CT to draw a plan of room as accurately as possible | 28.03.17 |
| 7. | Drunk and Disorderly Behavior Crew, volunteers, artists, members of the public | Anti-social behavior Potential Outcomes: Aggression and physical violence leading to slight, moderate or severe injury | Hull 2017 staff to inform venue staff of any unruly behavior to escort individuals out |  | 1 | 2 | LOW |  | 28.03.17 |

RISK MATRIX

| LIKELIHOOD SEVERITY | 1. Very unlikely (no known history) | 2. Unlikely (unlikely sequence of events) | 3. Possible (Foreseeable under unusual circumstances) | 4. Likely (Easily foresseable – some incidents may have occurred) | 5. Very likely (Common occurrence – aware of incidents) |
| --- | --- | --- | --- | --- | --- |
| 1. Negligible (no visible injury – no pain) | LOW | LOW | LOW | LOW | LOW |
| 2. Slight (minor cuts or bruises – no long term effects) | LOW | LOW | LOW | MEDIUM | MEDIUM |
| 3. Moderate (Heavy bruising, deep wounds, lost time) | LOW | LOW | MEDIUM | MEDIUM | HIGH |
| 4. Severe (Major injuries, lost time accidents, RIDDOR reportable) | LOW | MEDIUM | MEDIUM | HIGH | HIGH |
| 5. Very Severe (Long term disability or death) | LOW | MEDIUM | HIGH | HIGH | HIGH |

| NAME OF ASSESSOR: | Carys Tavener | DATE OF ASSESSMENT: | 15/03/2017 |
| --- | --- | --- | --- |
| SIGNATURE: |  |  |  |
| CONTACT DETAILS |  |  |  |
| EMAIL: | carys.tavener@hull2017.co.uk | PHONE: | 07851077582 |