## Detailed Critial Path
Event Name: Contains Strong Language
Client: Hull City of Culture
Event Date: 28th September - 1st October
Project Code:
Revision
KEY
Milestones |  |  |  | No. of Months | 4 |  |  |  |  | 3 |  |  |  | 2 |  |  |  |  | 1 |  |  |  | 0
Completed |  |  |  | Month | May |  |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September
Needs Immediate Action |  |  |  | Weeks before
|  |  |  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  |  |  | Dates | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25
Key Meetings | Start Date | End Date | Notes | Name / Responsibility
BBC, Hull 2017 and Humber Mouth Meetings |  |  | fortnightly??? | [8 empty] | 2017-06-21 | [12 empty] | 2007-09-15
Wider Partner Meetings | [12 empty] | 2017-06-27
Marketing and Communications
Deadline for Season 4 brochure copy | 2017-06-16 | [9 empty] | 2017-06-16
Proofing first draft of brochure w/c 19th June
Programme launch | 2017-07-17 | [14 empty] | 2017-07-17
Headline tickets on sale | 2017-07-17 | [14 empty] | 2017-07-17
Deadline for Festival Brochure
Festival Brochure Out | 2017-08-14 | [18 empty] | 2017-08-14
Free tickets online | 2017-08-14 | [18 empty] | 2017-08-14
Deadline for Z card copy
National Poetry Day Countdown starts | 2017-09-04 | 2017-09-28
Education Programme
Schools Programme finalised and sent out | [12 empty] | 2017-06-26
National Writing Day | 2017-06-21
GCSE Schools Poetry Readings | 2017-09-28 | [24 empty] | 2017-09-28
First Story | 2017-09-29 | [24 empty] | 2017-09-29
Key Events
National Writing Day | 2017-06-21
National Poetry Day | 2017-09-28 | [24 empty] | 2017-09-28
Fred Voss in Bread Factory | 2017-09-24
Kate Fox and Women of Words event | 2017-09-28 | [24 empty] | 2017-09-28
Bohdan Piasecki event | 2017-09-28 | [24 empty] | 2017-09-28
Gala Launch Reading | 2017-09-28 | [24 empty] | 2017-09-28
John Cooper Clarke | 2017-09-29 | [24 empty] | 2017-09-29
Kate Tempest | 2017-09-30 | [24 empty] | 2017-09-30
Larkin Reflections with Roger McGough and Brian Patten | 2017-10-01 | [24 empty] | 2017-10-01
Bohdan Piasecki Project
Confirm with British Council which poet and when | 2017-06-19
Start Marketing Project | 2017-06-28 | [11 empty] | 2017-06-28
Mobile Poetry Station July/August | 2017-07-06 | 2017-08-09 | [11 empty] | 06/07/17 - 09/07/17 |  |  | 22/07/17 - 23/07/17 |  | 05/08/17 - 08/08/17
Launch event | 2017-07-08 | [12 empty] | 2017-07-08
City Centre Space part 1 | 2017-09-02 | 2017-09-08 | [20 empty] | 02/09/17 - 08/09/17
City Centre Sapce part 2 | 2017-09-22 | 2017-09-28 | [23 empty] | 22/09/17 - 28/09/18
CSL event | 2017-09-28 | [24 empty] | 2017-09-28
End of Project Report | October
Kate Fox and Women of Words Project
Research and Writing | 2017-06-01
Kate Fox and Women of Words meeting | 2017-07-03 | [12 empty] | 2017-07-03
Rehersal period | 2017-09-20 | [23 empty] | 20/096/17
Kate Fox and Women of Words event | 2017-09-28 | [24 empty] | 2017-09-28
End of Project Report | October
Volunteers
Initial meeting with Harriet | 2017-06-21 | [10 empty] | 2017-06-21
Deadline for volunteer request form
Deadline for shifts going live
Training?
Joined Up Dance
Payment 1 | 2017-05-20 | [5 empty] | 2017-05-20
Progress Report | 2017-07-20 | [14 empty] | 2017-07-20
End of project report and final payment | 2017-10-20
Ticketing
Deadline for ticketing form
On sale date 1 | 2017-07-17
On sale date 2 | 2017-08-14
Finance Stages & Reconciliation
Contracts of artists and core team agreed & finalised
Budget approved
Payment schedule agreed
Artists Contract signed
T&Cs and payment schedules agreed with suppliers
Purchase orders sent to suppliers
Budget reconciled
General Project
Onsite
Sponsorship
Way finding
Staging & Props
Assets & Products
Technical Design - infustructure
Technical Production services. - Ground Control
Event Capture (Videographer & Photographer)
Ticketing/Accreditation (Special events)
Miscellaneous
Marketing, Digital and PR

## Operations Project Critical Pat
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
Current week commencing
KEY
Milestones |  | No. of Months | 5 |  |  |  |  | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
Completed |  | Month | August |  |  |  |  | September |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September
Needs Immediate Action |  | Weeks before Parade
|  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
|  | Dates | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
| Notes | Name / Responsibility
Key Meetings
Licensing, Approval & Permissions
Financials /Contracting - Client
Drawings/ Plans/ Designs
Traffic Management
Health & Safety
Crowd Management
Stewarding & Security
Media Management
Venue Management
Technical Production
Site Management
Signage Planning
Financials/Contracting - Suppliers
Hull City of culture and Ground Control Operations
Crew and project team logistics
Legal Requirements
Sustainability

## Stakeholder Meeting Dates
Event Name: Made in Hull
Client: Hull City of Culture |  |  |  |  | Current week commencing
Event Date: 1st January - 15th January |  |  |  |  | `
Project Code:
Revision |  | No. of Months | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  | Month | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September
Weeks before Happening
|  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
Key Dates & Trigger Points | Notes | Name / Responsibility
Core Group Milestones

## Community Engagement Plan
Event Name: Made in Hull
Client: Hull City of Culture
Event Date: 1st January - 15th January
Project Code:
Revision
|  | No. of Months | 4 |  |  |  | 3 |  |  |  |  | 2 |  |  |  | 1 |  |  |  | 0
|  | Month | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September
Weeks before Parade
|  | Days | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m | m
Dates
Key Dates & Trigger Points | Notes | Name / Responsibility
Bank Holidays
Other relevant dates
Community Engagement Comms Plan