25/10/2017

Learning & Participation Meeting

Kirsten Simister, George Vasey, James McGuire, Ian Read, Lily Mellor, Claire Drury, Rebecca Clark, Katie, David

- Heritage Learning – Schools

- 25/10/2017 - Curator Tour
30 x people, fully booked. LM anticipating two thirds drop off as the previous curator tours have proved, considering opening future tours up to more people.
LM / IR to inform Box Office

- 27/10/2017 – Print Workshop now free
Open it up to staff and HCAL staff as the school group has cancelled
15 x capacity – IR to circulate

- Turner Return

- Event Details
No longer using the side entrance to the gallery

Hack & Host Blue Box located outside – doing their own risk assessment

Gallery 11 will host music and bar 

Feesting in Gallery 2 provision has been reduced, CD has been talking to catering – KS confirmed main contact is Carol Copley and Vicki Knightwaller

Additional lighting in Gallery 3 and Gallery 5 to be added by Matt w/c 30/10/2017

KS suggested screening artist’s film in between in the activities in the studio

Locus Dance to do their own risk assessment

CD / RC / LM to visit gallery w/c 30/10/2017 and check lighting
CD to e-mail KS for Ferens shop contact details
CD to confirm capacity of Gallery 11 with KS / SC – 40 people approx
(Does furniture reduce capacity - poseur tables are needed)

CD to speak to KS about staffing, LM to request Matt Lund for tech support
KS to ask Matt about HD projector

LM to ask Shaun about trestles / CD to ask Vicki for white clothes

- Marketing
CD/LM would like to send event info out on HCAL channels. KS suggested speaking to Malcom Dunn.
400 attendees at the event is the aim
RC to incorporate managing audience on the night into the event plan
RC to a briefing note for next meeting 01/11/2017 - KS on annual leave next week. LM to invite Shaun in her place.

- Future Ferens
Heritage learning meeting with Future Ferens 26/10/2017
IR to meet with Anna Bean to create proposal and feedback to Future Ferens

- Broadsheet
George is working on second broadsheet - completed for Turner Return Event on 16/11/2017

- AOB
Turner Prize tote bags to be held back for the Friends of the Ferens preview (400 approximately)
LM to speak to Simon about the Tote Bags