## Sheet1
| December |  |  |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  |  | June |  |  |  | July
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5
Activity | December Week 2: Charity status; December Week 3: Headline Act; January Week 2: Appeal for community photos; January Week 3: Sponsorship details; January Week 4: Outline details of main event; January Week 5: Get involved PR; February Week 1: Announce second headliner; February Week 2: LGBT 50 project reminder; February Week 3: Film festival announcement; February Week 4: Duckie involvement; March Week 1: Hull Uni collaboration; March Week 2: Photography project closing date; March Week 3: Polari @ City of Culture; March Week 4: Feature on Lads and Lasses at Fruit; April Week 1: Feature on comedy night; April Week 2: Reminder of Pride day details; April Week 4: Sponsorship reminder
Key messages | December Week 2: Benefits to Pride attendees and the LGBT+ community.; December Week 3: Marc Almond; January Week 2: LGBT 50 project info; January Week 3: Benefits of sponsorship; January Week 4: Venue, new format, bigger and better!; January Week 5: Volunteering; February Week 4: UK Pride and community involvement; March Week 2: 2017-04-30
Notes | December Week 3: Can we utilise UK Pride network again for this announcement? Can we do an exclusive with HDM? If Marc Almond would do an interview with them, this would be a good way of securing.; January Week 2: What is the deadline for this? How do people submit entries? Need to target community groups with this, not just media.; January Week 3: How are we planning to reach the business community directly?; January Week 4: This could be a bigger announcement if we could add something else in. What else is there that is special or different about the format?; January Week 5: Would be good to get organisations that have volunteer banks to promote this for us too. E.g. CoC, Humberside Police, Humberside Fire, NHS orgs.; February Week 1: Depending on who this is, we could look at doing a tie in with local media. E.g. 90s act like All Saints or B*Witched would be good for Viking FM.; February Week 3: Need details; February Week 4: Need to make a huge deal of this, especially with gay press. Could we look at contacting GT or Attitude ahead of this announcement? Also a great one for the UK Pride network to support on social again.; March Week 1: Debate/talk, possible hosted by BBCs Ben Thompson; March Week 4: Potential link with Rikki Beadle Blair. When is the play? Can we invite theatre critic from HDM to come?; April Week 1: Details to be confirmed