PRSF NEW MUSIC BIENNIAL

HULL

29th JUNE to 2nd JULY 2017

ARTIST PACK

ARTIST: Mark Simpson

ARTIST CONTACT (Mobile number): TBC – PROMOTER TO CONFIRM

VENUE: Mortimer Suite (Sharp)

Address: Hull City Hall, Queen Victoria Square, Carr Lane, Hull, Hu1 3RQ

Phone: direct no??

LOADING IN FROM: Paragon Street (Pink Dot)

PARKING REQUIREMENT and LOCATION:

TBC – PROMOTER TO CONFIRM

PERSONNEL

STAGE MANAGER (Primary contact show weekend only): Danielle Harris - 07594 212377

PRODUCTION MANAGER: Gareth Hughes – 07733112272

PRODUCTION ASSISTANT: Joanna Morley – 07725 942808

VENUE CONTACT: Tony Evans (Technical)/Lorna (FOH)

DATE AND TIME OF PERFORMANCE:Sunday 2ndJuly 11:00 (45mins)

PRODUCTION SCHEDULE:

| FRIDAY 30 JUNE |  |  |
| --- | --- | --- |
| 06:00 - 00:00 (ACCESS) | 06:00 - 11:00 | Tech in - ALL |
|  | 09:00 | Piano delivery - Mortimer Suite - Sharpe |
|  |  | BOTH MORTIMERS AS DRESS ROOMS FOR BBC PHIL |
|  | 10:00 | Piano tuning - Mortimer |
| SATURDAY 1 JULY |  |  |
| 08:00 - 00:00 (ACCESS) | 09:00 | Piano tuning - Mortimer |
|  | 09:00 - 11:00 | Branding and dressing - Mortimer Suite (Sharp) |
|  | 11:00 - 14:00 | Emily Hall - Artists arrive and rehearsal - Mortimer Suite (sharp) |
|  | 15:00 | DOORS - Mortimer Suite (sharp) |
|  | 15:15 - 16:00 | Emily Hall - PERFORMANCE |
|  | 16:30 - 21:00 | Reset tech for Mortimer Suite (sharp) - Gould Piano Trio |
| SUNDAY 2 JULY |  |  |
| 08:00 - 20:00 (ACCESS) | 08:00 | Piano tuning - Mortimer Suite |
|  | 09:00 - 10:45 | Piano Trio rehearsal - Mortimer Suite (sharp) |
|  | 09:30 | Box office on site |
|  | 10:45 | DOORS - Mortimer Suite (sharp) - Mark Simpson |
|  | 11:00 - 11:45 | Mark Simpson PERFORMANCE |
|  | 14:00 - 20:00 | Derig and clear |
| MONDAY 3 JULY |  |  |
|  | AM | Materials back to storage |
|  | AM | Piano off site |

TECHNICAL

Speech System

Basic PA System

1 Combined System Rack 1

2 L Acoustic MTD108A

1 Camco Vortex 6

2 Powerdrive 44BE Speaker Stand

2 13A To 16A Adapter

8 XLR Splitter

Microphones

2 Pulse Headset Microphone - Beige

2 Sennheiser EW512 G3 - Belt Pack System - Range GB

Staff

1 Engineer - Systems

RIDER:

TBC

BACKLINE:

ACCREDITATION

David & Alice Porter (Directors)

Steve & Sam Shaw (Directors)

Peter & Lorraine Boardman (Directors)

Wes Zepherin (Director)

Kirsty & Gary Halliday (Marketing)

Ben Pugh (Production)