DRAFT SUBJECT TO CHANGE

HULL 2017 PROJECT SUMMARY – The Last Ballad of Lillian Bilocca

Crediting 
Hull UK City of Culture 2017 
The Last Ballad of Lillian Bilocca (TBC)  
by Maxine Peake

Music & Lyrics by Adrian McNally & The Unthanks

Associate Movement Director 	Jon Beney

Lighting Designer			Chris Davey

Director 				Sarah Frankcom

Choreographer / Co-director 	Imogen Knight

Sound Designer			Peter Malkin

Set & Costume Designer		Amanda Stoodley

Casting Director			Polly Jerrold

Summary

Inspired by the women who campaigned for better and safer working conditions on Britain’s trawler ships, the Ballad of Big Lil is a site specific project with a strong mix of music, movement and text. The production explores Hull’s heritage as a port city, and celebrates the hard and dangerous life of trawlerman ruled by a feudal system of ship owners in a voracious capitalist system. At the heart of the story is Lillian Bilocca, a women who dared to speak out and take action to improve conditions for men at sea. With a community chorus and live music, the evening will be a visceral, joyous evening of song, music & theatre.

The following details describe the production parameters which reflect the project budget

Venue		Guildhall, Hull TBC

A civic space with the faded grandeur of the past.

Music 	New musical works written by Adrian McNally and The Unthanks. To be performed live by The Unthanks. 
One song, the Ballad of Big Lil, to have lyrics by Maxine Peake, with original music by Adrian McNally and The Unthanks.

Cast & Band  	Cast of 8

Band of 6
	Max cast & band no more than 14

Digital 	Explore live broadcast & filming opportunities to extend reach for audiences.

Project Timeline

June 16 	Brief delivered to Hull 2017 by Maxine Peake

July 16 	Commission the script

Secure director

August 16 	Site scouting & site to be identified.

Sept/Oct 16	Recce visit for Guildhall – SF, AS, PR as well as MP if schedule allows

10 -14 Oct 	R&D in Manchester. 
To be arranged by Michelle Hickman from Manchester
Royal Exchange with actors from Streetcar. 
In attendance: 	Maxine Peake
			Sarah Frankcom
 			Adrian McNally (only avail 10 & 11 and tbc)
			Amanda Stoodley

Nov/Dec 16 	Secure designer, choreographer, sound & lighting designer production manager

First delivery of script due

Jan 17		Creative team site recce in Hull

Confirm details of RET involvement

Feb 17 	Script R&D week & draft due

Mar 17		Presentation to SLT at Guildhall 21.03.17

April 17	Artistic presentation to SLT at Hull 2017 followed by practical MarComms planning session at Hull 2017.

Final script delivered

Prelim designs & outline costings

Casting of professional company

May 17 	Budget revisions based

June 17	Image & copy generated

Confirm site – venue contracted

Confirm & contract rehearsal space, Hull

Stage management team confirmed

Sign off season brochure page

July 17		Recruitment & casting of Community Cast

Final designs & detailed costings

Sept 17 	Pre-Production – build & prep venue

Oct 17 		Rehearse

Install at venue

Nov 17 	Tech, open & perform

Nov 17 	Close

Production Team 
Production Manager
Company Stage Manager
DSM
ASM x 2
Sound Op 
LX Op
Dresser
Technician 
Production Sound

Production LX
Costume Supervisor – RET in kind support

(One role to take the lead on volunteer supervision)

FOH Manager
Box Office Manager & Assistant – To be provided by Hull 2017 core team TBC

Stewards 
Security
Access Performance Interpreter

Bar staff 				Licensee & Operator TBC

Production Schedule 
All dates to be discussed and confirmed with MP/SF and Unthanks
Rehearsals Week 1			w/c 2 Oct 2107		Reh in Manchester 
 				 			 		(Pro Cast)
 									Reh in Hull Comm Cast

Rehearsals Week 2 			w/c 9 Oct			Reh in Manchester

(Pro Cast)
 									Reh in Hull Comm Cast

Rehearsals Week 3			w/c 16 Oct 			Reh in Hull
Rehearsals Week 4			w/c 23 Oct			Reh in Hull
Start venue set up

Production / Tech Week		w/c 30 Oct				
First Preview				Fri 3 Nov
Second Preview			Sat 4 Nov 	
Performance Week 1			w/c 6 Nov

Press Night				Wed 8 or Thurs 9 Nov

Perf Week 2				w/c 13 Nov
Final Performances			Sat 18 Nov 2017

Proposal for possible Community Ensemble process:
Community Cast			To be 16 + years old 
 					Overall Group of 30 – for min 20 per perf
 					Rehearsals in Hull
					3 sessions a week, evenings & weekend
					6 sessions during Tech Week, daytime, evening & Sat
 					6 performances per week during run

Min 6 performances per week inc one matinee TBC.

05.06.17