Initial First draft for discussion.

Where Do We Go From Here? Schedule of Events

Production

Wednesday 15th Nov	- First robots arrive on site  / Production

Monday 20th Nov		- Programming start

Prelude

Wc. 20th 			- Robot Journey / Press Story

Thursday 23rd Nov		- Christmas Lights turn on / first signals from Beverley Gate / initial thought

Wednesday 29th Nov 	- Volunteers briefing tour /  this is for the volunteers who will be explaining the piece each night

potentially so they have spoken to the design and technical teams

Live / First draft: Normal running days : Wednesday to Sunday unless indicated on specail days.

Running times 17.00 to 21.00.

Thursday 30th Nov 		- Press Launch: individual interviews in the afternoon, run by Hull 2017 and then a walk around with

press to each location, under embargo potentially if completed prior to 6pm.

Friday 1st Dec 		- Opening / Partners tour and artist talk and tours culminating in a reception of some kind (To be

discussed and scoped as to what and where this is) (evening)

Saturday 2nd Dec 		- Youth workshop / C4DI robot programming and tour : learning programme, with the potential to

‘winners’ being able to interact with a robot programming in the final week. (afternoon)

Sunday 3rd Dec		- Access (20 people) Special tour. (evening)

Tuesday 5th Dec		- Turner Prize / coordinate with their lights potential special as per timings given

(note: Event in Minster closing 22.45) (open til late)

Saturday 16th Dec		- Nativity Play / potential special light to light the live nativity

Sunday 31st Dec 		- Normal day

Monday 1st Dec		- Normal day Final week with special location for response pieces to be viewed.

Sunday 7th Jan		- Last day

PR

Press Prelude / Teasers before official opening

- Story about the robot's journey from factory to Hull. Film GREAT and Foreign office potential. (Think film trailer)

- Robot Portraits

- Poetry, storytelling to capture young audiences and raise questions, Where Do We Go From Here?

Isaiah Hull

https://www.youtube.com/watch?v=fiAYERvjytk

Kirsty Taylor

https://www.youtube.com/watch?v=OK1olORe5z0

Interpretation / Public information

- Leaflet

- Social Media platforms and different materials available on each

- Onsite

- Volunteers

Public engagement / During live period

- Photo and Film competition / various social media platforms / poetry slams and or theatre a pieces and short films/ Music or sound scapes. Competitions again being shown in the final week in a location selected few with the learning robots, but also this could be international and national especially if we have done the GREAT film.

- General response / Where Do We Go From Here? What kind of place do we want to live in? What role does culture play?

Exhibition / End of live period

- Collected material from public engagement

- Judging devised special Panel: of competitions / Coding, photos and film

- Potentially get ABB and JLR involved to demonstrate robot

Agenda for tomorrow:

- Pre marketing and PR activity discussion

- Timeline (general) above.

- Timeline specifics and specials

- Look and feel of pieces and marketing / PR and Interpretation and platforms this is being presented on.

- Roles and responsibilities in Creative, PR, Marketing, Learning and Soundscapes etc,

- Next steps in the next 2 weeks

- AOB