## Number of Days - outdated
Bohdan Project
BASED ON DAYS… | No.
Planning | 2
Recruitment & Workshops | 3
Performances - rehearsals & actual | 4
Writing / Commission | 5
Evaluation | 1
Contingency | 1
TOTAL DAYS | 16

## Draft Budget (£10k) - outdated
Bohdan Project (£10k)
BUDGET | BASED ON | BASED ON
| no.of days | £per day
Total project days | 16 | 250 | 2400
Expenses (travel) | 5 | 60 | 300
Expenses (accommodation) | 11 | 50 | 550
Marketing |  |  | 1700
Production Costs | 4 | 250 | 1000
Project Management days | 12 | 150 | 1800
Documentation days | 4 | 250 | 1000
Miscellaneous |  |  | 250
CSL days related activity |  |  | n/a
Contingency (approx 10%) |  |  | 1000
TOTAL DAYS |  |  | 10000

## Draft Budget (£15k) - current
Bohdan Project (£15k)
BUDGET | BASED ON | BASED ON |  | NOTES
| no.of days | £per day
Engagement Project Days
Launch Event : Bohdan | 1 | 250 | 250 | when launch?
Launch Event : 2 x Polish poets | 2 | 200 | 400 | could reduce to £150 each
Free Poems : Bohdan | 4 | 250 | 1000
Mobile Poetry Station : Bohdan | 5 | 250 | 1250
Mobile Poetry Station : 1 x other person | 5 | 150 | 750 | may need more people
Exhibition/Making Space Launch : Bohdan | 1 | 250 | 250
A (More) Permanent Space : Bohdan | 4 | 250 | 1000
Expenses (travel)
Birmingham<>Hull train (Bohdan) | 15 | 55 | 825
2 x Polish guest poets plane/train | 2 | 180 | 360
Expenses (accommodation)
Launch Event (Bohdan plus 2 Polish poets) x 2 nights stay | 6 | 75 | 450
Launch Event (Bohdan plus 2 Polish poets) x 2 per diems | 6 | 25 | 150
Free Poems, Poetry Stn, Exhib & Perm Space : Bohdan | 18 | 75 | 1350
Marketing / Comms |  |  | 1000 | enough?
Production / Workshop Costs
Launches x 2 | 2 | 250 | 500
Free Poems, Exhibition & Perm Space |  |  | 500
Mobile Poetry Station (Build/Transport) |  |  | 2000
Project Management days | 10 | 150 | 1500 | Who?
Evaluation | 1 | 250 | 250
Access |  |  | 400
Photography / Filming |  |  | 400
CSL days related activity |  |  | n/a
Contingency |  |  | 415 | low
TOTAL |  |  | 15000
Assumes free venues and some additional equipment such as projectors, if required