## Slide 1
NO
YES BLF (not CCP)
YES BLF (CCP)
YES H17 (check)
YES H17 (no check)
Fill in new FR form
Fill in new FR form
Undertake due diligence
Inform Hull 2017 of result [What if they fail?]
Fill in new FR form
Approve, sign & return contract
END
Email: ?
SM
Complete Artifax using FR data
SM
Prepare & send out contract bundle
SM
Update Artifax, send to Marketing
SM
CD
Email: Still being considered
SM
Email: BLF may be in touch
SM
Email: BLF may be in touch
SM
Email: No; links to other funders
SM
Distribute joint (BLF/H17) press release
BM
Curatorial conv’s & due diligence
HD
JM
Book spaces for workshops
SM
Sign off emails with BM and introduce BM to BLF press team.
NB BLF need min two-week sign-off of press release in advance of release w/c 4 July
HD
w/c 20/06
w/c 27/06
Complete Artifax using FR data
SM
Complete Artifax using FR data
SM
w/c 04/07
w/c 25/07
Final deadline for S1 brochure
w/c 18/07
Email: ?
SM
END
Email: ?
SM
Email: ?
SM
Prepare & send out contract bundle
SM
Final deadline for S1 brochure
Approve, sign & return contract
Update Artifax, send to Marketing
SM
CD
Basic info dropped into Marketing templates; # projects confirmed
??
Approve, sign & return contract
Prepare & send out contract bundle
SM
Update Artifax, send to Marketing
SM
CD
w/c ??
Submit FR reports as per project timeline
w/c 01/08
w/c 05/09
Finance set up for successful projects
??
First workshop session
MarComms session
Submit FR reports as per contract/ payment schedule
Further workshops on event management etc
Hull 2017
Grantee
Big Lottery Fund
CREATIVE COMMUNITIES PROGRAMME: PROCESS