HULL TAKEOVER: List to discuss today/Notes

- Press Release TEXT. Let’s wrap this up.

- Helen sent amended version to everyone with Lindsey’s amends in blue.

- Decision to remove ‘Northern Voices’.

- Agreed to release tomorrow 28th August late morning for Thursday pickup – Clare please send a final version to Helen before doing so?

- Ben has signed off Martin’s quote.

- Volunteers info to be included; Clare to remove the figure 100, can add in ‘considerable amount’.

- Clare to send 2 suggestions for photo call location.

- Rachel to book a photographer for the photo call.

- Helen suggests 11.30-12pm is the best time for the companies (or earlier).

- Can Clare come to Edinburgh for the 7th August?

- Include Silent Uproar press access from 2nd says Helen.

- Press Release IMAGE choice agreed.

- Decision: Companies NDT Showcase image from Feb and curious directive stock.

- Other updates/questions on Press from Ben, Alix, Clare?

Kofi?

- Kofi to be arranged closer to the time, can Alix be on this?

Week 1 of the festival? Martin, Mikey, Mark?

- Has changed to Week 3 for press briefings.

- Phil: update on Hull Hangout, Print Flyer design process and deadlines from Companies/Helen, Print Leaflet plans and details including timelines.

Other news and updates? What’s the plan with digital? 2017 Website?

- Hull Hangout will be set up from August 1st, Phil speaking to Summerhall Weds and to update Helen

- Schedule signed off by Phil.

- Helen to work with Rachel Crow direct

- Digital article 1 week before festival begins.

- 10-12th July – only time all 4 cos are in Hull. Do we want to arrange some interviews, photos etc?

- Helen to work with Bethany direct.

- Strapline for the flyer footer banner. 2 choices.

- Phil wants: PART OF THE #HULLTAKEOVER. 5 unmissable shows. 5 amazing companies. 1 UK City of Culture.

- Helen to send to curious directive.

- IS THIS SCHEDULE OK with everyone?

Yes

- Volunteers on the Mile: schedule for the day. Clare suggests am photocall: can we agree time slots?

- See point 1