## Summary
Back to Ours C700 & C601 | BUDGET | BFI - ADDITIONAL £35,975k to BUDGET | TOTAL BUDGET | FORECAST | VARIANCE | ENCUMB | ACTUAL | [5 empty] | BUDGET | FORECAST | VARIANCE | ACTUAL
Summary Expenditure | [8 empty] | Summary Income
Development | 15000 | 2394 | 17394 | 17394 | 0 | 2348 | 3245 |  | Funding - Hull CCG |  |  |  | 75000 | 75000 | 0
Festival Programme | 160770 | 0 | 160770 | 161020 | -250 |  | 4500 |  | Funding - Other Funds |  |  |  | 35975 | 35975 | 0
Festival Engagement & Delivery | 157495 | 0 | 157495 | 159069.56 | -1574.56 | 600 | 1400 |  | Funding - Trust & Foundation |  |  |  | 0 | 0 | 0
NNT Core Team | 16500 | 9570 | 26070 | 26070 | 0 |  | 182.62 |  | Funding - ACE Strategic Touring |  |  |  | 226250 | 226250 | 0
Contingency @ 3% Programming | 4823.1 | 1026 | 5849.1 | 5849.1 | 0 |  |  |  | Box Office Earned Income |  |  |  | 53148.3333 | 56615.0521 | 3466.7188 | 150
|  | 22985 | 22985 | 22985 | 0
Total Expenditure | 354588.1 | 35975 | 390563.1 | 392387.66 | -1824.56 | 2948 | 9327.62 |  | Total Income |  |  |  | 390373.3333 | 393840.0521 | 3466.7188 | 150
Balance | 35785.2333 |  | -189.7667 | 1452.3921 |  |  |  |  | ACE STF Request as % of total project |  |  |  | 57.96% | 57.45%
Hull 2017 Net Contribution (Budget) | 301439.7667 |  | 337414.7667 | 335772.6079 |  |  | 9177.62
Development
Core Marketing, Brand Dev; Venue Dressing Kits; Templates; Signage | 10000 | 2394 | 12394 | 12394 | 0 | 2348 | 1300 | MDC
Core Marketing Campaigns, Graphic Design | 5000 |  | 5000 | 5000 | 0 |  | 1945 | MDC
Sub-Total | 15000 | 2394 | 17394 | 17394 | 0 | 2348 | 3245
MODEL: FOUR FESTIVALS IN THREE AREAS | [8 empty] | PROJECTED BOX OFFICE INCOME | Performances/ Events |  | Av Net Tkt Price | Net Box Office Income
Festival Programming Fees - all inc | [8 empty] | Festival |  | Attendance
February '17 Festival | 22050 |  | 22050 | 22300 | -250 |  | 4500 | Perf | February '17 Festival | 21 | 1990 |  | 7758.3333 | 11225.0521 | 3466.7188
May Festival | 40800 |  | 40800 | 40800 | 0 |  |  | Perf | May Festival | 24 | 3120 |  | 13350
October Festival | 48960 |  | 48960 | 48960 | 0 |  |  | Perf | October Festival | 28.8 | 3744 |  | 16020
February '18 Festival | 48960 |  | 48960 | 48960 | 0 |  |  | Perf | February '18 Festival | 28.8 | 3744 |  | 16020
Contingency £4823 is on Live Budget under Performances | [8 empty] | Totals | 102.6 | 12598 |  | 53148.3333 | 11225.0521 | 3466.7188
Sub-Total Programme Fees | 160770 | 0 | 160770 | 161020 | -250 |  | 4500
PER FESTIVAL ENGAGEMENT & DELIVERY
February '17 Festival | 26340 |  | 26340 | 27914.56 | -1574.56 | 600 | 1400
May Festival | 36775 |  | 36775 | 36775 | 0
October Festival | 47190 |  | 47190 | 47190 | 0
February '18 Festival | 47190 |  | 47190 | 47190 | 0
Sub-Total Programme Fees | 157495 | 0 | 157495 | 159069.56 | -1574.56 | 600 | 1400
Core NNT Team
Programme Director - Expenses - 18 month | 1500 |  | 1500 | 1500 | 0 |  |  | C&P
Programme Consultant / Promoter Liaison - monthly programming meetings - 1 year | 8400 | 8001 | 16401 | 16401 | 0 |  |  | C&P
Technical Co-ordinator & Venue Liaison - 18 months - av 0.5 | 24000 |  | 24000 | 24000 | 0 |  |  | A&M
Project Administrator - 18 months - 0.5 average | 18750 |  | 18750 | 18750 | 0 |  |  | A&M
Reduce as per agreement with HD | -24000 |  | -24000 | -24000 | 0 |  |  | A&M
Reduce as per agreement with HD | -18750 |  | -18750 | -18750 | 0 |  |  | A&M
Venue Programming Teams support 18 months | 2400 | 39 | 2439 | 2439 | 0 |  | 54 | A&M
Venue Partner Network Go & See Costs | 1200 |  | 1200 | 1200 | 0 |  | 128.62 | R&D
Insurance, Licences, Finance Administration | 3000 | 1530 | 4530 | 4530 | 0 |  |  | L&D
Sub-total | 16500 | 9570 | 26070 | 26070 | 0 |  | 182.62
Interactive activities by Into Film (value of partnership funding TBC) |  | 4050 | 4050 | 4050 |  |  |  | C&F
Jaws Outdoor Event |  | 18935 | 18935 | 18935 |  |  |  | C&F
Sub-total |  | 22985 | 22985 | 22985
Note on J6: Robinson Andrea (2017): JT - £269k less Salaries for Tech Co & Proj Ad = £42750
Note on H11: Robinson Andrea (2017): Total Expenditure Actual - Income Actual

## Area Festivals
NORTH |  | Cost per unit |  | Venues / People | Days | Daily rate | 2017-02-01 | Venues / People | Days | Daily rate | 2017-05-01 | Venues / People | Days | Daily rate | 2017-10-01 | Venues / People | Days | Daily rate | 2018-02-01
Venue Hire | V | 50 |  |  | 4 | 50 | 0 | 3 | 5 | 50 | 750 | 4 | 6 | 50 | 1200 | 4 | 6 | 50 | 1200
Venue Technical Hires | D | 150 |  | 2 | 4 | 150 | 1200 | 3 | 5 | 150 | 2250 | 4 | 6 | 150 | 3600 | 4 | 6 | 150 | 3600 | Can enter in
Dressing Room / Green Room Set Up / Artist Liaison | D | 60 |  | 2 | 1 | 60 | 120 | 3 | 1 | 60 | 180 | 4 | 1 | 60 | 240 | 4 | 1 | 60 | 240 | Linked to venue / days
Transport | D | 50 |  | 2 | 4 | 50 | 400 | 3 | 5 | 50 | 750 | 4 | 6 | 50 | 1200 | 4 | 6 | 50 | 1200
Duty of Care | D | 15 |  | 8 | 4 | 15 | 480 | 8 | 5 | 15 | 600 | 10 | 6 | 15 | 900 | 10 | 6 | 15 | 900
Security | [6 empty] | 400
Sub-Total Technical | [6 empty] | 2600 |  |  |  | 4530 |  |  |  | 7140 |  |  |  | 7140
Festival Production
Local Technical Manager - (1.2 days per Festival day) | D | 150 |  | 1 | 4.8 | 150 | 720 | 1 | 6 | 150 | 900 | 1 | 7.2 | 150 | 1080 | 1 | 7.2 | 150 | 1080
Crew (x2) | D | 120 |  | 2 | 4 | 120 | 960 | 2 | 5 | 120 | 1200 | 2 | 6 | 120 | 1440 | 2 | 6 | 120 | 1440
Local Technical Apprentice (1.2 days per Festival day) | D | 50 |  | 1 | 4.8 | 50 | 240 | 1 | 6 | 50 | 300 | 1 | 7.2 | 50 | 360 | 1 | 7.2 | 50 | 360
FOH Manager - | D | 80 |  | 1 | 4 | 80 | 320 | 1 | 5 | 80 | 400 | 1 | 6 | 80 | 480 | 1 | 6 | 80 | 480
FOH & Box Office Team (x2) | D | 40 |  | 2 | 4 | 40 | 320 | 2 | 5 | 40 | 400 | 2 | 6 | 40 | 480 | 2 | 6 | 40 | 480
Sub-Total Festival Staff | [6 empty] | 2560 |  |  |  | 3200 |  |  |  | 3840 |  |  |  | 3840
Festival Engagement, MarComms & Evaluation
Local Marketing & Engagement Manager | D | 150 |  | 1 | 4 | 150 | 600 | 1 | 5 | 150 | 750 | 1 | 6 | 150 | 900 | 1 | 6 | 150 | 900
Local Marketing & Engagement Apprentice | D | 50 |  | 1 | 4 | 50 | 200 | 1 | 5 | 50 | 250 | 1 | 6 | 50 | 300 | 1 | 6 | 50 | 300
Marketing Campaign (per venue) | V | 500 |  | 2 | 1 | 500 | 1000 | 3 | 1 | 500 | 1500 | 4 | 1 | 500 | 2000 | 4 | 1 | 500 | 2000
Access performances | F | 500 |  | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500
Remote Box Office Set-Up | F | 300 |  | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300
Photography / Filming / Documenting (per day) | D | 75 |  | 1 | 4 | 75 | 300 | 1 | 5 | 75 | 375 | 1 | 6 | 75 | 450 | 1 | 6 | 75 | 450
Evaluation (per day) | D | 50 |  | 1 | 4 | 50 | 200 | 1 | 5 | 50 | 250 | 1 | 6 | 50 | 300 | 1 | 6 | 50 | 300
Sub-Total Festival Engagement , MarComms, Evaluation | [6 empty] | 3100 |  |  |  | 3925 |  |  |  | 4750 |  |  |  | 4750
Total for North Festivals | [6 empty] | 8260 |  |  |  | 11655 |  |  |  | 15730 |  |  |  | 15730
Number of venues | V | [5 empty] | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 4
Number of days | D | [5 empty] | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 6
EAST |  | Cost per day |  | Venues / People | Days | Daily rate | 2017-02-01 | Venues / People | Days | Daily rate | 2017-05-01 | Venues / People | Days | Daily rate | 2017-10-01 | Venues / People | Days | Daily rate | 2018-02-01
Venue Hire (per venue) | V | 50 |  |  | 4 | 50 | 0 | 3 | 5 | 50 | 750 | 4 | 6 | 50 | 1200 | 4 | 6 | 50 | 1200
Venue Technical Hires - 10 days @ £700 | D | 150 |  | 2 | 4 | 150 | 1200 | 3 | 5 | 150 | 2250 | 4 | 6 | 150 | 3600 | 4 | 6 | 150 | 3600
Dressing Room / Green Room Set Up / Artist Liaison | D | 60 |  | 2 | 1 | 60 | 120 | 3 | 1 | 60 | 180 | 4 | 1 | 60 | 240 | 4 | 1 | 60 | 240
Transport | D | 50 |  | 2 | 4 | 50 | 400 | 3 | 5 | 50 | 750 | 4 | 6 | 50 | 1200 | 4 | 6 | 50 | 1200
Duty of Care - 20 people, 10 days @£8 | D | 15 |  | 8 | 4 | 15 | 480 | 8 | 5 | 15 | 600 | 10 | 6 | 15 | 900 | 10 | 6 | 15 | 900
Security | [6 empty] | 400
Sub-Total Technical | [6 empty] | 2600 |  |  |  | 4530 |  |  |  | 7140 |  |  |  | 7140
Festival Production
Local Technical Manager - (1.2 days per Festival day) | D | 150 |  | 1 | 4.8 | 150 | 720 | 1 | 6 | 150 | 900 | 1 | 7.2 | 150 | 1080 | 1 | 7.2 | 150 | 1080
Crew (x2) | D | 120 |  | 2 | 4 | 120 | 960 | 2 | 5 | 120 | 1200 | 2 | 6 | 120 | 1440 | 2 | 6 | 120 | 1440
Local Technical Apprentice (1.2 days per Festival day) | D | 50 |  | 1 | 4.8 | 50 | 240 | 1 | 6 | 50 | 300 | 1 | 7.2 | 50 | 360 | 1 | 7.2 | 50 | 360
FOH Manager - | D | 80 |  | 1 | 4 | 80 | 320 | 1 | 5 | 80 | 400 | 1 | 6 | 80 | 480 | 1 | 6 | 80 | 480
FOH & Box Office Team (x2) | D | 40 |  | 2 | 4 | 40 | 320 | 2 | 5 | 40 | 400 | 2 | 6 | 40 | 480 | 2 | 6 | 40 | 480
Sub-Total Festival Staff | [6 empty] | 2560 |  |  |  | 3200 |  |  |  | 3840 |  |  |  | 3840
Festival Engagement, MarComms & Evaluation
Local Marketing & Engagement Manager | D | 150 |  | 1 | 4 | 150 | 600 | 1 | 5 | 150 | 750 | 1 | 6 | 150 | 900 | 1 | 6 | 150 | 900
Local Marketing & Engagement Apprentice | D | 50 |  | 1 | 4 | 50 | 200 | 1 | 5 | 50 | 250 | 1 | 6 | 50 | 300 | 1 | 6 | 50 | 300
Marketing Campaign (per venue) | V | 500 |  | 2 | 1 | 500 | 1000 | 3 | 1 | 500 | 1500 | 4 | 1 | 500 | 2000 | 4 | 1 | 500 | 2000
Access performances | F | 500 |  | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500
Remote Box Office Set-Up | F | 300 |  | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300
Photography / Filming / Documenting (per day) | D | 75 |  | 1 | 4 | 75 | 300 | 1 | 5 | 75 | 375 | 1 | 6 | 75 | 450 | 1 | 6 | 75 | 450
Evaluation (per day) | D | 50 |  | 1 | 4 | 50 | 200 | 1 | 5 | 50 | 250 | 1 | 6 | 50 | 300 | 1 | 6 | 50 | 300
Sub-Total Festival Engagement , MarComms, Evaluation | [6 empty] | 3100 |  |  |  | 3925 |  |  |  | 4750 |  |  |  | 4750
Total for East Festivals | [6 empty] | 8260 |  |  |  | 11655 |  |  |  | 15730 |  |  |  | 15730
Number of venues | V | [5 empty] | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 4
Number of days | D | [5 empty] | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 6
WEST |  | Cost per day |  | Venues / People | Days | Daily rate | 2017-02-01 | Venues / People | Days | Daily rate | 2017-05-01 | Venues / People | Days | Daily rate | 2017-10-01 | Venues / People | Days | Daily rate | 2018-02-01
Venue Hire (per venue) | V | 50 |  |  | 4 | 50 | 0 | 4 | 5 | 50 | 1000 | 4 | 6 | 50 | 1200 | 4 | 6 | 50 | 1200
Venue Technical Hires - 10 days @ £700 | D | 150 |  | 3 | 4 | 150 | 1800 | 4 | 5 | 150 | 3000 | 4 | 6 | 150 | 3600 | 4 | 6 | 150 | 3600
Dressing Room / Green Room Set Up / Artist Liaison | D | 60 |  | 3 | 1 | 60 | 180 | 4 | 1 | 60 | 240 | 4 | 1 | 60 | 240 | 4 | 1 | 60 | 240
Transport | D | 50 |  | 3 | 4 | 50 | 600 | 4 | 5 | 50 | 1000 | 4 | 6 | 50 | 1200 | 4 | 6 | 50 | 1200
Duty of Care - 20 people, 10 days @£8 | D | 15 |  | 8 | 4 | 15 | 480 | 8 | 5 | 15 | 600 | 10 | 6 | 15 | 900 | 10 | 6 | 15 | 900
Security | [6 empty] | 600
Sub-Total Technical | [6 empty] | 3660 |  |  |  | 5840 |  |  |  | 7140 |  |  |  | 7140
Festival Production
Local Technical Manager - (1.2 days per Festival day) | D | 150 |  | 1 | 4.8 | 150 | 720 | 1 | 6 | 150 | 900 | 1 | 7.2 | 150 | 1080 | 1 | 7.2 | 150 | 1080
Crew (x2) | D | 120 |  | 2 | 4 | 120 | 960 | 2 | 5 | 120 | 1200 | 2 | 6 | 120 | 1440 | 2 | 6 | 120 | 1440
Local Technical Apprentice (1.2 days per Festival day) | D | 50 |  | 1 | 4.8 | 50 | 240 | 1 | 6 | 50 | 300 | 1 | 7.2 | 50 | 360 | 1 | 7.2 | 50 | 360
FOH Manager - | D | 80 |  | 1 | 4 | 80 | 320 | 1 | 5 | 80 | 400 | 1 | 6 | 80 | 480 | 1 | 6 | 80 | 480
FOH & Box Office Team (x2) | D | 40 |  | 2 | 4 | 40 | 320 | 2 | 5 | 40 | 400 | 2 | 6 | 40 | 480 | 2 | 6 | 40 | 480
Sub-Total Festival Staff | [6 empty] | 2560 |  |  |  | 3200 |  |  |  | 3840 |  |  |  | 3840
Festival Engagement, MarComms & Evaluation
Local Marketing & Engagement Manager | D | 150 |  | 1 | 4 | 150 | 600 | 1 | 5 | 150 | 750 | 1 | 6 | 150 | 900 | 1 | 6 | 150 | 900
Local Marketing & Engagement Apprentice | D | 50 |  | 1 | 4 | 50 | 200 | 1 | 5 | 50 | 250 | 1 | 6 | 50 | 300 | 1 | 6 | 50 | 300
Marketing Campaign (per venue) | V | 500 |  | 3 | 1 | 500 | 1500 | 4 | 1 | 500 | 2000 | 4 | 1 | 500 | 2000 | 4 | 1 | 500 | 2000
Access performances | F | 500 |  | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500 | 1 | 1 | 500 | 500
Remote Box Office Set-Up | F | 300 |  | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300 | 1 | 1 | 300 | 300
Photography / Filming / Documenting (per day) | D | 75 |  | 1 | 4 | 75 | 300 | 1 | 5 | 75 | 375 | 1 | 6 | 75 | 450 | 1 | 6 | 75 | 450
Evaluation (per day) | D | 50 |  | 1 | 4 | 50 | 200 | 1 | 5 | 50 | 250 | 1 | 6 | 50 | 300 | 1 | 6 | 50 | 300
Sub-Total Festival Engagement , MarComms, Evaluation | [6 empty] | 3600 |  |  |  | 4425 |  |  |  | 4750 |  |  |  | 4750
Total for West Festivals | [6 empty] | 9820 |  |  |  | 13465 |  |  |  | 15730 |  |  |  | 15730
Number of venues | V | [5 empty] | 3 |  |  |  | 4 |  |  |  | 4 |  |  |  | 4
Number of days | D | [5 empty] | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 6
TOTAL SPEND | [6 empty] | 26340 |  |  |  | 36775 |  |  |  | 47190 |  |  |  | 47190
157495
Venue Hire (per venue) |  | VL | 9700 |  |  |  | 0 |  |  |  | 2500 |  |  |  | 3600 |  |  |  | 3600
Venue Technical Hires |  | VL | 33300 |  |  |  | 4200 |  |  |  | 7500 |  |  |  | 10800 |  |  |  | 10800
Dressing Room / Green Room Set Up / Artist Liaison |  | VL | 2460 |  |  |  | 420 |  |  |  | 600 |  |  |  | 720 |  |  |  | 720
Transport |  | VL | 11100 |  |  |  | 1400 |  |  |  | 2500 |  |  |  | 3600 |  |  |  | 3600
Duty of Care/First Aid |  | C&P | 8640 |  |  |  | 1440 |  |  |  | 1800 |  |  |  | 2700 |  |  |  | 2700
Security |  | VL | 1400 |  |  |  | 1400
Sub-Total Technical |  |  | 66600 |  |  |  | 8860 |  |  |  | 14900 |  |  |  | 21420 |  |  |  | 21420
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Festival Production | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Local Technical Manager - (1.2 days per Festival day) |  | T&P | 11340 |  |  |  | 2160 |  |  |  | 2700 |  |  |  | 3240 |  |  |  | 3240
Crew (x2) |  | T&P | 15120 |  |  |  | 2880 |  |  |  | 3600 |  |  |  | 4320 |  |  |  | 4320
Local Technical Apprentice (1.2 days per Festival day) |  | T&P | 3780 |  |  |  | 720 |  |  |  | 900 |  |  |  | 1080 |  |  |  | 1080
FOH Manager - |  | T&P | 5040 |  |  |  | 960 |  |  |  | 1200 |  |  |  | 1440 |  |  |  | 1440
FOH & Box Office Team (x2) |  | T&P | 5040 |  |  |  | 960 |  |  |  | 1200 |  |  |  | 1440 |  |  |  | 1440
Sub-Total Festival Staff |  |  | 40320 |  |  |  | 7680 |  |  |  | 9600 |  |  |  | 11520 |  |  |  | 11520
[7 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Festival Engagement, MarComms & Evaluation | [6 empty] | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
Local Marketing & Engagement Manager |  | T&P | 9450 |  |  |  | 1800 |  |  |  | 2250 |  |  |  | 2700 |  |  |  | 2700
Local Marketing & Engagement Apprentice |  | T&P | 3150 |  |  |  | 600 |  |  |  | 750 |  |  |  | 900 |  |  |  | 900
Marketing Campaign (per venue) |  | MDC | 20500 |  |  |  | 3500 |  |  |  | 5000 |  |  |  | 6000 |  |  |  | 6000
Access Performances |  | E&C | 6000 |  |  |  | 1500 |  |  |  | 1500 |  |  |  | 1500 |  |  |  | 1500
Remote Box Office Set-Up |  | MDC | 3600 |  |  |  | 900 |  |  |  | 900 |  |  |  | 900 |  |  |  | 900
Photography / Filming / Documenting (per day) |  | MDC | 4725 |  |  |  | 900 |  |  |  | 1125 |  |  |  | 1350 |  |  |  | 1350
Evaluation (per day) |  | MDC | 3150 |  |  |  | 600 |  |  |  | 750 |  |  |  | 900 |  |  |  | 900
|  |  | 157495 |  |  |  | 26340 |  |  |  | 36775 |  |  |  | 47190 |  |  |  | 47190

## Feb 17
| EAST | [7 empty] | NORTH | [7 empty] | WEST
BTO: FEB 17 | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  |  | Global Costs | Forecast | BUDGET | Variance | ACTUALS
Show | The Red Shed | Joan | Meet Fred (BSL) | The Story of Mr B | Family Film Day | The Pigeon Detectives (+ support act) | Hekima | EAST GENERAL AREA COSTS | The Story of Mr Day (2 Relaxed Perfs - Fri 24 Feb) | Meet Fred | The Red Shed (BSL) | Hekima | Joan | Family Film Day | The Pigeon Detectives (+ support act) | NORTH GENERAL AREA COSTS | Meet Fred | The Story of Mr B | Hekima | Family Film Day | The Pigeon Detectives (+ support act) | Secret Gig | Joan (Captioned) | WEST GENERAL AREA COSTS | GENERAL FESTIVAL COSTS |  | Forecast | Budget | Variance | Actuals
Company | Mark Thomas | Milk Presents | Hijinx | Shake Shake | Leeds Film Fest | Music | Music |  | Shake Shake | Hijinx | Mark Thomas | Music | Milk Presents | Leeds Film Fest | Music |  | Hijinx | Shake Shake | Music | Leeds Film Fest | Music | Comedy | Milk Presents
Venue | Sentamu - Theatre (300) | Sentamu Drama Studio (50) | Sentamu - Theatre (200) | Sentamu Drama Studio (60) | Sentamu - Theatre (300 - includes restricted view) | Freedom - Main Theatre (350 standing) | Sentamu - Winter Garden / Agora (50) |  | Winifred Holtby Drama Studio (60) | Kingswood - Main Theatre (300) | Kingswood - Main Theatre (300) | North Point - Shop Unit? (60) | North Point - Atrium (60) | Winifred Holtby - Main Theatre (300) | North Point - Atrium (est. standing max. 200) |  | Sirius Academy - Main Hall (200) | Sirius Academy - Drama Studio (50) | Hymers (60) Canteen/Bar | Sirius Academy - Main Hall (200) | Sirius Acdemy - Main Hall (300 standing) | William Gemmell - Concert Room (140 seated) | Hymers (60)
Date | 24/02/2017 Friday | 23/02/2017 Thursday | 23/02/2017 Thursday | 25/02/2017 Saturday | 22/02/2017 Wednesday | 25/02/2017 Saturday | 23/02/2017 Thursday |  | 23/02/2017 Thursday 24/03/2017 Friday | 22/02/2017 Wednesday | 25/02/2017 Saturday | 24/02/2017 Friday | 24/02/2017 Friday | 25/02/2017 Saturday | 23/02/2017 Thursday |  | 25/02/2017 Saturday | 22/02/2017 Wednesday | 25/02/2017 Saturday | 23/02/2017 Thursday | 24/02/2017 Friday | 23/02/2017 Thursday | 25/02/2017 Saturday
Time | 7.30pm | 7.30pm | 3.30pm | 11am & 2pm | 10am - 8pm | 7.30pm | 8.45pm |  | 11am & 2pm | 6pm | 7.30pm | 8.45pm | 7.30pm | 10am - 8pm | 7.30pm |  | 1pm | 11am & 2pm | 8.45pm | 10am - 8pm | 7.30pm | 7.30pm | 7.30pm
Duration
INCOME
Variable assumptions
Capacity | 300 | 50 | 200 | 60 | 300 | 300 | 50 |  | 60 | 300 | 300 | 60 | 60 | 300 | 150 |  | 150 | 50 | 60 | 100 | 300 | 140 | 60 |  |  | 3350
Projected sales % | 75% | 70% | 55% | 75% | 65% | 75% | 70% |  | 65% | 50% | 75% | 70% | 70% | 65% | 75% |  | 65% | 70% | 65% | 65% | 75% | 75% | 65%
Estimated attendance | 225 | 35 | 110 | 45 | 195 | 225 | 35 |  | 39 | 150 | 225 | 42 | 42 | 195 | 112.5 |  | 97.5 | 35 | 39 | 65 | 225 | 105 | 39 |  |  | 2281
% Attendance Adult Tickets @ £5.00 | 75% | 70% | 55% | 75% | 65% | 75% | 70% |  | 65% | 50% | 75% | 70% | 70% | 65% | 75% |  | 65% | 70% | 65% | 65% | 75% | 75% | 65%
Adult Ticket sales | 168.75 | 24.5 | 60.5 | 33.75 | 126.75 | 168.75 | 24.5 |  | 25.35 | 75 | 168.75 | 29.4 | 29.4 | 126.75 | 84.375 |  | 63.375 | 24.5 | 25.35 | 42.25 | 168.75 | 78.75 | 25.35
Adult Ticket price | 5 | 5 | 5 | 5 | 2.5 | 7.5 | 0 |  | 5 | 5 | 5 | 0 | 5 | 2.5 | 7.5 |  | 5 | 5 | 0 | 2.5 | 7.5 | 7.5 | 5
% Attendance Child Tickets @ £2.50 | 25% | 30% | 45% | 25% | 35% | 25% | 30% |  | 35% | 50% | 25% | 30% | 30% | 35% | 25% |  | 35% | 30% | 35% | 35% | 25% | 25% | 35%
Child ticket sales | 56.25 | 10.5 | 49.5 | 11.25 | 68.25 | 56.25 | 10.5 |  | 13.65 | 75 | 56.25 | 12.6 | 12.6 | 68.25 | 28.125 |  | 34.125 | 10.5 | 13.65 | 22.75 | 56.25 | 26.25 | 13.65
Child ticket price | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 7.5 | 0 |  | 2.5 | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 7.5 |  | 2.5 | 2.5 | 0 | 2.5 | 7.5 | 2.5 | 2.5
Expected Total Ticket Yield | 984.375 | 148.75 | 426.25 | 196.875 | 487.5 | 1687.5 | 0 |  | 160.875 | 562.5 | 984.375 | 0 | 178.5 | 487.5 | 843.75 |  | 402.1875 | 148.75 | 0 | 162.5 | 1687.5 | 656.25 | 160.875
Average Ticket Yield (£) | 4.375 | 4.25 | 3.875 | 4.375 | 2.5 | 7.5 | 0 |  | 4.125 | 3.75 | 4.375 | 0 | 4.25 | 2.5 | 7.5 |  | 4.125 | 4.25 | 0 | 2.5 | 7.5 | 6.25 | 4.125
Number of performances | 1 | 1 | 1 | 2 | 3 | 1 | 1 |  | 4 | 1 | 1 | 0 | 1 | 3 | 1 |  | 1 | 2 | 1 | 3 | 1 | 1 | 1
Total Attendance | 225 | 35 | 110 | 90 | 585 | 225 | 35 |  | 156 | 150 | 225 | 0 | 42 | 585 | 112.5 |  | 97.5 | 70 | 39 | 195 | 225 | 105 | 39 |  |  |  | 3346
Gross Box Office | 984.375 | 148.75 | 426.25 | 393.75 | 1462.5 | 1687.5 | 0 |  | 643.5 | 562.5 | 984.375 | 0 | 178.5 | 1462.5 | 843.75 |  | 402.1875 | 297.5 | 0 | 487.5 | 1687.5 | 656.25 | 160.875 |  |  |  | 13470.0625
Merchant fee / Spektrix | -31.5 | -4.76 | -13.64 | -12.6 | -46.8 | -54 | 0 |  | -20.592 | -18 | -31.5 | 0 | -5.712 | -46.8 | -27 |  | -12.87 | -9.52 | 0 | -15.6 | -54 | -21 | -5.148
VAT element | -164.0625 | -24.7917 | -71.0417 | -65.625 | -243.75 | -281.25 | 0 |  | -107.25 | -93.75 | -164.0625 | 0 | -29.75 | -243.75 | -140.625 |  | -67.0312 | -49.5833 | 0 | -81.25 | -281.25 | -109.375 | -26.8125 |  |  |  | -2245.0104
Net Box Office Contribution | 788.8125 | 119.1983 | 341.5683 | 315.525 | 1171.95 | 1352.25 | 0 | 0 | 515.658 | 450.75 | 788.8125 | 0 | 143.038 | 1171.95 | 676.125 |  | 322.2862 | 238.3967 | 0 | 390.65 | 1352.25 | 525.875 | 128.9145 | 0 |  |  | 11225.0521 | 7758.3333 | 3466.7188
Less: Visiting Company and Other Costs
Programming Fee | 2250 | 600 | 1000 | 1000 | 0 | 2250 | 100 |  | 1800 | 1000 | 2250 | 100 | 600 | 0 | 1400 |  | 1000 | 1000 | 100 | 0 | 2250 | 3000 | 600 |  |  |  | 22300 | 22050 | -250
Royalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
Venue Hire (per venue) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Venue Technical Hires | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 |  | 4200 | 4200 | 0
Dressing Room / Green Room Set Up / Artist Liaison | 300 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 550 | 420 | -130
Transport | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1146.35 |  | 1146.35 | 1400 | 253.65
Duty of Care/First Aid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1469 |  | 1469 | 1440 | -29
Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2225 |  | 2603 | 1400 | -1203
Technical Manager / Apprentice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 |  | 2880 | 2880 | 0
Crew (x2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2880 |  | 2880 | 2880 | 0
FOH Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2936.21 |  | 2936.21 | 1920 | -1016.21
Marketing Manager / Apprentice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 |  |  | 1800 | 2400 | 600 | 1200
Marketing Campaign (per venue) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  | 4000 | 3500 | -500 | 200
Access Performances | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1000 | 1500 | 500
Photography / Filming / Documenting (per day) | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 100 | 50 | 50 | 0 | 50 | 50 | 50 | 0 | 50 | 50 | 0 | 50 | 50 | 50 | 50 | 0 |  |  | 950 | 900 | -50
Evaluation (per day) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 |  |  | 600 | 600 | 0
Remote Box Office Set-Up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  |  | 900 | 900 | 0
Total Cost | 350 | 50 | 550 | 50 | 50 | 300 | 0 | 2110 | 100 | 50 | 550 | 0 | 50 | 50 | 50 |  | 50 | 50 | 0 | 50 | 50 | 50 | 50 | 2600 | 17736.56 |  | 27914.56 | 26340 | -1574.56
TOTAL PROFIT OR LOSS | 438.8125 | 69.1983 | -208.4317 | 265.525 | 1121.95 | 1052.25 | 0 | -2110 | 415.658 | 400.75 | 238.8125 | 0 | 93.038 | 1121.95 | 626.125 |  | 272.2862 | 188.3967 | 0 | 340.65 | 1302.25 | 475.875 | 78.9145 | -2600 | -17736.56 | Total Variance |  |  | 1642.1587
Key Assumptions
Calculated Fields
Guaranteed Fees
Royalty rate | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Models
Box Office Data
Total Box Office | 984.375 | 148.75 | 426.25 | 393.75 | 1462.5 | 1687.5 | 0 |  | 643.5 | 562.5 | 984.375 | 0 | 178.5 | 1462.5 | 843.75 |  | 402.1875 | 297.5 | 0 | 487.5 | 1687.5 | 656.25 | 160.875
Spektrix fee | -12.7969 | -1.9337 | -5.5413 | -5.1187 | -19.0125 | -21.9375 | 0 |  | -8.3655 | -7.3125 | -12.7969 | 0 | -2.3205 | -19.0125 | -10.9688 |  | -5.2284 | -3.8675 | 0 | -6.3375 | -21.9375 | -8.5312 | -2.0914
Merchant fee | -18.7031 | -2.8262 | -8.0988 | -7.4813 | -27.7875 | -32.0625 | 0 |  | -12.2265 | -10.6875 | -18.7031 | 0 | -3.3915 | -27.7875 | -16.0312 |  | -7.6416 | -5.6525 | 0 | -9.2625 | -32.0625 | -12.4688 | -3.0566
Total Box Office minus credit cards & VAT | 788.8125 | 119.1983 | 341.5683 | 315.525 | 1171.95 | 1352.25 | 0 |  | 515.658 | 450.75 | 788.8125 | 0 | 143.038 | 1171.95 | 676.125 |  | 322.2862 | 238.3967 | 0 | 390.65 | 1352.25 | 525.875 | 128.9145
Guaranteed Royalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
FOH
Attendants - Rate | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 0 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
Hours | 4 | 4 | 4 | 6 | 9 | 4 | 0 |  | 12 | 4 | 4 | 0 | 4 | 9 | 4 |  | 4 | 6 | 0 | 9 | 4 | 4 | 4
Attendants Number | 2 | 1 | 2 | 2 | 2.5 | 2 | 2 |  | 2 | 2 | 2 | 0 | 2 | 2.5 | 2 |  | 2 | 2 | 2 | 2.5 | 2 | 1 | 2
Total Performance cost | 64 | 32 | 64 | 96 | 180 | 64 | 0 |  | 192 | 64 | 64 | 0 | 64 | 180 | 64 |  | 64 | 96 | 0 | 180 | 64 | 32 | 64
FOH Manager
Rate | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12
Hours | 6 | 6 | 6 | 8 | 10 | 6 | 0 |  | 16 | 6 | 6 | 0 | 6 | 10 | 6 |  | 6 | 8 | 0 | 10 | 6 | 6 | 6
Total cost | 72 | 72 | 72 | 96 | 120 | 72 | 0 |  | 192 | 72 | 72 | 0 | 72 | 120 | 72 |  | 72 | 96 | 0 | 120 | 72 | 72 | 72
FOH costs | 136 | 104 | 136 | 192 | 300 | 136 | 0 |  | 384 | 136 | 136 | 0 | 136 | 300 | 136 |  | 136 | 192 | 0 | 300 | 136 | 104 | 136
Crew
Attendants - Rate | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10 | 10 | 0 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
Hours | 12.5 | 20 | 20 | 10 | 10 | 10 | 10 |  | 10 | 20 | 13 | 0 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
Attendants Number | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 0 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
Total Performance cost | 250 | 400 | 400 | 200 | 200 | 200 | 200 |  | 200 | 400 | 260 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Crew costs | 250 | 400 | 400 | 200 | 200 | 200 | 200 |  | 200 | 400 | 260 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Technical Manager / Apprentice | [6 empty] | 2100 | [7 empty] | 1800
Technical input (in half days) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Rate | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 200 | 200 | 200 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Tech Manager costs | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 100 | 100 | 100 | 0 | 100 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100
Marketing Manager / Apprentice
Technical input (in half days) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Rate | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 200 | 200 | 200 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Tech Manager costs | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 100 | 100 | 100 | 0 | 100 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100
Technical Hire Costs
Light | 136 | 70 | 40 | 50 | 0 | 100 | 0 |  | 50 | 80 | 240 | 0 | 100 | 0 | 100 |  | 80 | 50 | 0 | 0 | 100 | 200 | 70
Sound | 260 | 100 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 260 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 0 | 100 | 0 | 0
AV | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Set | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 200 | 0 | 0 | 0 | 0 | 100
Miscellaneous | 0 | 0 | 10 | 10 | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Festival Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Hire Costs | 396 | 170 | 50 | 60 | 0 | 200 | 100 |  | 150 | 90 | 500 | 100 | 100 | 0 | 200 |  | 90 | 250 | 100 | 0 | 200 | 200 | 170
Note on C4: Robinson Andrea (2017): Double bill with Hekima. Single ticket for both events. Revenue is showing under JOAN only.
Note on H4: Robinson Andrea (2017): Double bill with JOAN. Single ticket for both events. Revenue is showing under JOAN only.
Note on M4: Robinson Andrea (2017): Double bill with JOAN. Single ticket for both events. Revenue is showing under JOAN only.
Note on N4: Robinson Andrea (2017): Double bill with Hekima. Single ticket for both events. Revenue is showing under JOAN only.
Note on T4: Robinson Andrea (2017): Double bill with JOAN. Single ticket for both events. Revenue is showing under JOAN only.
Note on X4: Robinson Andrea (2017): Double bill with Hekima. Single ticket for both events. Revenue is showing under JOAN only.
Note on F6: Freeth Thomas (2017): Would like to use Winter Garden as a possible future venue.
Note on G6: Freeth Thomas (2017): 320 seated capacity. Untested standing.
Note on H6: Freeth Thomas (2017): Capacitu defined by Joan. Potential to invite more people through schools groups (e.g. Dance or disabled groups invited for this show only)
Note on J6: Freeth Thomas (2017): Chosen because it's ideal for families to access without travel - unlike Kingswood
Note on M6: Freeth Thomas (2017): Could be the shop unit, but would have to drop 1m of space from the width of their stage. No access from wings. To be negotiated with company.
Note on N6: Freeth Thomas (2017): Could be in Atrium space - would fit well. Blackout would be darkened skies in February. Can Louise at North Point offer us a guarranteed shop unit for this performance.
Note on R6: Freeth Thomas (2017): Get In of 6 hours prevents 2 shows
Note on V6: Freeth Thomas (2017): Open the screen at the back of the hall and have a bar in the Heart Space.
Note on D8: Freeth Thomas (2017): Pre-tea time show
Note on K8: Freeth Thomas (2017): Soft drink provision for this show
Note on R12: Louise Yates: reduced capacity -sSpace for wheel chair users
Note on D13: Freeth Thomas (2017): Have dropped expected attendance to reflect teen audience being potentially difficult to attract.
Note on K13: Freeth Thomas (2017): Have dropped expected attendance to reflect teen audience being potentially difficult to attract.
Note on D15: Freeth Thomas (2017): Have dropped expected attendance to reflect teen audience being potentially difficult to attract.
Note on K15: Freeth Thomas (2017): Have dropped expected attendance to reflect teen audience being potentially difficult to attract.
Note on E18: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on J18: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on S18: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on AD29: Robinson Andrea (2017): Income changed from a favourable variance of £2921 to £4508. The change in Income was due to the Secret Gig ticket price being added giving additional income of £526. There was also an error on a formula which resulted in the favourable variance which has now been resolved 1/2/17
Note on B31: Freeth Thomas (2017): Includes travel but not accomodation
Note on C31: Freeth Thomas (2017): Includes accomodation and travel
Note on N31: Freeth Thomas (2017): Includes accomodation and travel
Note on X31: Freeth Thomas (2017): Includes accomodation and travel
Note on AD31: Robinson Andrea (2017): The Secret Gig was increased to £3000, increasing the forecast to £22,300 leaving an adverse variance £250 due to booking an additional celebrity act for the Secret Gig 1/2/17
Note on AD36: Robinson Andrea (2017): Reduced forecast to £550 based upon £250 for Pigeon Detectives deal memo & £30 for Mark Thomas accommodation. This may reduce further 1/2/17 Adverse variance £-130.
Note on AD38: Robinson Andrea (2017): First Aid Costs added hence adverse variance 1/2/17
Note on P39: Freeth Thomas (2017): North Point using own security
Note on B43: halved - 2 shows per shift surely?
Note on C43: halved - 2 shows per shift surely?
Note on D43: halved - 2 shows per shift surely?
Note on E43: halved - 2 shows per shift surely?
Note on F43: halved - 2 shows per shift surely?
Note on G43: halved - 2 shows per shift surely?
Note on H43: halved - 2 shows per shift surely?
Note on J43: halved - 2 shows per shift surely?
Note on K43: halved - 2 shows per shift surely?
Note on L43: halved - 2 shows per shift surely?
Note on M43: halved - 2 shows per shift surely?
Note on N43: halved - 2 shows per shift surely?
Note on O43: halved - 2 shows per shift surely?
Note on P43: halved - 2 shows per shift surely?
Note on R43: halved - 2 shows per shift surely?
Note on S43: halved - 2 shows per shift surely?
Note on T43: halved - 2 shows per shift surely?
Note on U43: halved - 2 shows per shift surely?
Note on V43: halved - 2 shows per shift surely?
Note on W43: halved - 2 shows per shift surely?
Note on X43: halved - 2 shows per shift surely?
Note on AD43: Robinson Andrea (2017): Originally recruiting & staff with freelancers, now using Events Team for some events & supplement with freelancers. Revised forecast will be £2907.50 but need to confirm with Louise & Carys before changing on V6 1/2/17. This is higher than expected due to additional training, a higher than initially expected fee for the FOH Co-ordinator & more staff hours required to deliver the project. This will show an adverse variance of £-987.50.
Note on A71: Freeth Thomas (2017): FOH staff also need to double as Box Office staff
Note on A77: Freeth Thomas (2017): FOH Manager is also the volunteer lead
Note on A104: Freeth Thomas (2017): These cells are hidden because the forecast costs no longer apply and these cells no longer link through to the forecast budget.

## May 17
| EAST | [7 empty] | NORTH | [7 empty] | WEST
BTO: FEB 17 | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast |  |  | Global Costs | Forecast | BUDGET | Variance | ACTUALS
Show | [7 empty] | EAST GENERAL AREA COSTS | [7 empty] | NORTH GENERAL AREA COSTS | [7 empty] | WEST GENERAL AREA COSTS | GENERAL FESTIVAL COSTS |  | Forecast | Budget | Variance | Actuals
Company
Venue
Date
Time
Duration
INCOME
Variable assumptions
Capacity | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
Projected sales % | 100% | 70% | 55% | 75% | 65% | 75% | 70% |  | 65% | 50% | 100% | 70% | 70% | 65% | 75% |  | 65% | 70% | 65% | 65% | 75% | 100% | 65%
Estimated attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0
% Attendance Adult Tickets @ £5.00 | 100% | 50% | 30% | 30% | 20% | 100% | 50% |  | 30% | 30% | 100% | 60% | 60% | 30% | 100% |  | 30% | 30% | 0% | 20% | 100% | 100% | 50%
Adult Ticket sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Adult Ticket price | 5 | 5 | 5 | 5 | 2.5 | 7.5 | 0 |  | 5 | 5 | 5 | 0 | 5 | 2.5 | 7.5 |  | 5 | 5 | 0 | 2.5 | 7.5 | 7.5 | 5
% Attendance Child Tickets @ £2.50 | 0% | 50% | 70% | 70% | 80% | 0% | 50% |  | 70% | 70% | 0% | 40% | 40% | 70% | 0% |  | 70% | 70% | 100% | 80% | 0% | 0% | 50%
Child ticket sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Child ticket price | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 7.5 | 0 |  | 2.5 | 2.5 | 2.5 | 0 | 2.5 | 2.5 | 7.5 |  | 2.5 | 2.5 | 0 | 2.5 | 7.5 | 2.5 | 2.5
Expected Total Ticket Yield | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Average Ticket Yield (£) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Number of performances | 1 | 1 | 1 | 2 | 3 | 1 | 1 |  | 4 | 1 | 1 | 0 | 1 | 3 | 1 |  | 1 | 2 | 1 | 3 | 1 | 1 | 1
Total Attendance | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Gross Box Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Merchant fee / Spektrix | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
VAT element | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
Net Box Office Contribution | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 13350 | -13350
Less: Visiting Company and Other Costs
Fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 40800 | 40800
Royalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 |  | 0
Venue Hire (per venue) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2500 | 2500
Venue Technical Hires | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 7500 | 7500
Dressing Room / Green Room Set Up / Artist Liaison | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 600 | 600
Transport | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 2500 | 2500
Duty of Care/First Aid | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1800 | 1800
Security | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0
Technical Manager / Apprentice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3600 | 3600
Crew (x2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3600 | 3600
FOH Costs | 136 | 104 | 136 | 192 | 300 | 136 | 0 |  | 384 | 136 | 136 | 0 | 136 | 300 | 136 |  | 136 | 192 | 0 | 300 | 136 | 104 | 136 |  |  |  | 3236 | 2400 | -836
Marketing Manager / Apprentice | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 3000 | 3000
Marketing Campaign (per venue) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 |  |  | 4000 | 5000 | 1000
Access Performances | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 |  |  | 1500 | 1500 | 0
Photography / Filming / Documenting (per day) | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 100 | 50 | 50 | 0 | 50 | 50 | 50 | 0 | 50 | 50 | 0 | 50 | 50 | 50 | 50 | 0 |  |  | 950 | 1125 | 175
Evaluation (per day) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 |  |  | 600 | 750 | 150
Remote Box Office Set-Up | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 |  |  | 900 | 900 | 0
Total Cost | 186 | 154 | 686 | 242 | 350 | 186 | 0 | 1500 | 484 | 186 | 686 | 0 | 186 | 350 | 186 |  | 186 | 242 | 0 | 350 | 186 | 154 | 686 | 2000 | 0 |  | 11186 | 36775 | 25589
TOTAL PROFIT OR LOSS | -186 | -154 | -686 | -242 | -350 | -186 | 0 | -1500 | -484 | -186 | -686 | 0 | -186 | -350 | -186 |  | -186 | -242 | 0 | -350 | -186 | -154 | -686 | -2000 | 0 | Total Variance |  |  | 53039
Key Assumptions
Calculated Fields
Guaranteed Fees
Royalty rate | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Models
Box Office Data
Total Box Office | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Spektrix fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Merchant fee | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Box Office minus credit cards & VAT | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Guaranteed Royalty | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
FOH
Attendants - Rate | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  | 8 | 8 | 8 | 0 | 8 | 8 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8
Hours | 4 | 4 | 4 | 6 | 9 | 4 | 0 |  | 12 | 4 | 4 | 0 | 4 | 9 | 4 |  | 4 | 6 | 0 | 9 | 4 | 4 | 4
Attendants Number | 2 | 1 | 2 | 2 | 2.5 | 2 | 2 |  | 2 | 2 | 2 | 0 | 2 | 2.5 | 2 |  | 2 | 2 | 2 | 2.5 | 2 | 1 | 2
Total Performance cost | 64 | 32 | 64 | 96 | 180 | 64 | 0 |  | 192 | 64 | 64 | 0 | 64 | 180 | 64 |  | 64 | 96 | 0 | 180 | 64 | 32 | 64
FOH Manager
Rate | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 |  | 12 | 12 | 12 | 12 | 12 | 12 | 12
Hours | 6 | 6 | 6 | 8 | 10 | 6 | 0 |  | 16 | 6 | 6 | 0 | 6 | 10 | 6 |  | 6 | 8 | 0 | 10 | 6 | 6 | 6
Total cost | 72 | 72 | 72 | 96 | 120 | 72 | 0 |  | 192 | 72 | 72 | 0 | 72 | 120 | 72 |  | 72 | 96 | 0 | 120 | 72 | 72 | 72
FOH costs | 136 | 104 | 136 | 192 | 300 | 136 | 0 |  | 384 | 136 | 136 | 0 | 136 | 300 | 136 |  | 136 | 192 | 0 | 300 | 136 | 104 | 136
Crew
Attendants - Rate | 10 | 10 | 10 | 10 | 10 | 10 | 10 |  | 10 | 10 | 10 | 0 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
Hours | 12.5 | 20 | 20 | 10 | 10 | 10 | 10 |  | 10 | 20 | 13 | 0 | 10 | 10 | 10 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10
Attendants Number | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 0 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
Total Performance cost | 250 | 400 | 400 | 200 | 200 | 200 | 200 |  | 200 | 400 | 260 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Crew costs | 250 | 400 | 400 | 200 | 200 | 200 | 200 |  | 200 | 400 | 260 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Technical Manager / Apprentice | [6 empty] | 2100 | [7 empty] | 1800
Technical input (in half days) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Rate | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 200 | 200 | 200 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Tech Manager costs | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 100 | 100 | 100 | 0 | 100 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100
Marketing Manager / Apprentice
Technical input (in half days) | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Rate | 200 | 200 | 200 | 200 | 200 | 200 | 200 |  | 200 | 200 | 200 | 0 | 200 | 200 | 200 |  | 200 | 200 | 200 | 200 | 200 | 200 | 200
Tech Manager costs | 100 | 100 | 100 | 100 | 100 | 100 | 100 |  | 100 | 100 | 100 | 0 | 100 | 100 | 100 |  | 100 | 100 | 100 | 100 | 100 | 100 | 100
Technical Hire Costs
Light | 136 | 70 | 40 | 50 | 0 | 100 | 0 |  | 50 | 80 | 240 | 0 | 100 | 0 | 100 |  | 80 | 50 | 0 | 0 | 100 | 200 | 70
Sound | 260 | 100 | 0 | 0 | 0 | 100 | 100 |  | 0 | 0 | 260 | 100 | 0 | 0 | 100 |  | 0 | 0 | 100 | 0 | 100 | 0 | 0
AV | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Set | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 200 | 0 | 0 | 0 | 0 | 100
Miscellaneous | 0 | 0 | 10 | 10 | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0
Festival Wide | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Technical Hire Costs | 396 | 170 | 50 | 60 | 0 | 200 | 100 |  | 150 | 90 | 500 | 100 | 100 | 0 | 200 |  | 90 | 250 | 100 | 0 | 200 | 200 | 170
Note on C4: Robinson Andrea (2017): Double bill with Hekima. Single ticket for both events. Revenue is showing under JOAN only.
Note on H4: Robinson Andrea (2017): Double bill with JOAN. Single ticket for both events. Revenue is showing under JOAN only.
Note on M4: Robinson Andrea (2017): Double bill with JOAN. Single ticket for both events. Revenue is showing under JOAN only.
Note on N4: Robinson Andrea (2017): Double bill with Hekima. Single ticket for both events. Revenue is showing under JOAN only.
Note on T4: Robinson Andrea (2017): Double bill with JOAN. Single ticket for both events. Revenue is showing under JOAN only.
Note on X4: Robinson Andrea (2017): Double bill with Hekima. Single ticket for both events. Revenue is showing under JOAN only.
Note on F6: Freeth Thomas (2017): Would like to use Winter Garden as a possible future venue.
Note on G6: Freeth Thomas (2017): 320 seated capacity. Untested standing.
Note on H6: Freeth Thomas (2017): Capacitu defined by Joan. Potential to invite more people through schools groups (e.g. Dance or disabled groups invited for this show only)
Note on J6: Freeth Thomas (2017): Chosen because it's ideal for families to access without travel - unlike Kingswood
Note on M6: Freeth Thomas (2017): Could be the shop unit, but would have to drop 1m of space from the width of their stage. No access from wings. To be negotiated with company.
Note on N6: Freeth Thomas (2017): Could be in Atrium space - would fit well. Blackout would be darkened skies in February. Can Louise at North Point offer us a guarranteed shop unit for this performance.
Note on R6: Freeth Thomas (2017): Get In of 6 hours prevents 2 shows
Note on V6: Freeth Thomas (2017): Open the screen at the back of the hall and have a bar in the Heart Space.
Note on D8: Freeth Thomas (2017): Pre-tea time show
Note on K8: Freeth Thomas (2017): Soft drink provision for this show
Note on R12: Louise Yates: reduced capacity -sSpace for wheel chair users
Note on D13: Freeth Thomas (2017): Have dropped expected attendance to reflect teen audience being potentially difficult to attract.
Note on K13: Freeth Thomas (2017): Have dropped expected attendance to reflect teen audience being potentially difficult to attract.
Note on E15: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on G15: Freeth Thomas (2017): 14yrs+ only. Challenge 25 policy on the bar - ID must be shown. Rist bands given out with different colour for adults and childrens tickets. Concern about shop fronts if capacity is larger
Note on J15: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on P15: Freeth Thomas (2017): 14yrs+ only. Challenge 25 policy on the bar - ID must be shown. Rist bands given out with different colour for adults and childrens tickets. Concern about shop fronts if capacity is larger
Note on S15: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on E18: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on J18: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on S18: Freeth Thomas (2017): Based roughly on 3 children attending with 1 adult
Note on B31: Freeth Thomas (2017): Includes travel but not accomodation
Note on C31: Freeth Thomas (2017): Includes accomodation and travel
Note on N31: Freeth Thomas (2017): Includes accomodation and travel
Note on X31: Freeth Thomas (2017): Includes accomodation and travel
Note on P39: Freeth Thomas (2017): North Point using own security
Note on B43: halved - 2 shows per shift surely?
Note on C43: halved - 2 shows per shift surely?
Note on D43: halved - 2 shows per shift surely?
Note on E43: halved - 2 shows per shift surely?
Note on F43: halved - 2 shows per shift surely?
Note on G43: halved - 2 shows per shift surely?
Note on H43: halved - 2 shows per shift surely?
Note on J43: halved - 2 shows per shift surely?
Note on K43: halved - 2 shows per shift surely?
Note on L43: halved - 2 shows per shift surely?
Note on M43: halved - 2 shows per shift surely?
Note on N43: halved - 2 shows per shift surely?
Note on O43: halved - 2 shows per shift surely?
Note on P43: halved - 2 shows per shift surely?
Note on R43: halved - 2 shows per shift surely?
Note on S43: halved - 2 shows per shift surely?
Note on T43: halved - 2 shows per shift surely?
Note on U43: halved - 2 shows per shift surely?
Note on V43: halved - 2 shows per shift surely?
Note on W43: halved - 2 shows per shift surely?
Note on X43: halved - 2 shows per shift surely?
Note on A71: Freeth Thomas (2017): FOH staff also need to double as Box Office staff
Note on A77: Freeth Thomas (2017): FOH Manager is also the volunteer lead
Note on A104: Freeth Thomas (2017): These cells are hidden because the forecast costs no longer apply and these cells no longer link through to the forecast budget.

## Notes
9/11/2016 - Andrea Robinson restructured the 'Back to Ours' budget for the purpose of supporting the team in managing the Forecast expenditure to the last agreed budget. | DONE
Therefore Andrea has copied the last agreed figures & saved as Version 6. Then copied in the Feb 17 Tab from the Festival Budget Work in Progress doc. | DONE
Then realigned the Budget figures back to the original of £26,340 | DONE
Corrected Box Office set up £900 into Budget column (in forecast column in error) | DONE
Deleted £300 & £4500 as no one knows what they are? | DONE
TF - 9/11/2016 - Have deleted 'Volunteer Duty of Care and Crew care.' next to the Crew Hospitality line as this has been split between the original budget headers of Crew Hospitality and Duty of Care. | DONE
Updated details for Venue Tech Hires tab | DONE
Updated details for Drssng Rm.Grn Rm.Artst Lisn tab | DONE
Updated details for Crew Hosp tab | DONE
Updated details for Duty of Care tab | DONE
Updated cost of Rev and Makers & Johnny Vegas Venue Tech Hire to £200 per venue | DONE
Have added £900 per area for remote Box Office set up | DONE
Removed all costs associated with Up Yours due to budget deficit | DONE
Increased ticket cost for Rev and Makers + Mark Thomas to £10/£5 to offset additional costs of the Feb Festival | DONE
Thom to do: 9.11.16
Add detail to forecast notes | N/A Anymore
Link through Venue Tech Hires from existing breakdown of costs | DONE
Split the forecast crew figures with Carys & send to Andrea | N/A
Delete crew element of Feb 17 tab - replace with day rates | DONE
Andrea to do: 9.11.16
align subheadings between Area Festivals tab & Feb 17 tab | DONE
Set up Tabs with detailed explanations of what they are & how they are made up | DONE
TF - 10.11.16 Updated Film Festival box office predictions | DONE
Updated tech venue hire costs with Carys | DONE
Mark Thomas tickets reset at £7.50/£5 - approved by HD. Rev tickets left at £10/£5. | DONE
Updated Crew and Tech Mngr & Apprntce costs according to Carys' revised costings. Agreed with Henri that Apprentice may be for May festival and beyond where support can be provided for this role, based on Feb experience. | DONE
TF - 16.11.16 Deleted Candoco. Replaced with Hekima as follow up act for JOAN double bill | DONE
Deleted Weathered Estates from Feb festival. | DONE
Increased Rev & The Makers fee line to include £650 agent's fee and £250 fee for support acts at each gig. | DONE
Changed ticket prices for Rev & The Makers to £7.50 ticket price across the board. | DONE
Deleted Up Yours from Feb festival | DONE
Have decreased the FOH Manager rate to £12 and reallocated this money to an additional FOH attendent for the Family Film Day | DONE
17/11/16 Andrea to do
Amend Area Festivals Tab to remove Venue Hire Amounts. Move the amount against Security. | DONE
Crew Hospitality - No Budget & No Forecast? No costs so take line out altogether | DONE
17.11.16 TF
Update Hekima tech costs and reinstate formula into venue tech hire cells for Hekima | DONE
Update Hekima audience figures in North Point from 0 to 60 | DONE
18.11.16 TF
Updated number of performances of Story of Mr B in Archbishop Sentamu Academy from 4 to 2 | DONE
24.11.16 TF
Updated JOAN and Hekima performance times | DONE
Updated access details in show title row | DONE
Marked Rev & Makers and Johnny Vegas as red to indicate that these acts are likely to be replaced. Have left ticketing and income assumptions until have further info | DONE
28.11.16 TF
Updated the Family Film Day adult ticket prices from £5 to £2.50 to match child prices. | DONE
02.12.16 TF
Amended Rev and The Makers to The Pigeon Detectives. Changes capacity of Freedom from 500 to 300 in line with deal memo. | DONE
Amended the Artist Liaison line for The Pigeon Detectives to £250 across, in total across all festivals. | DONE
Amended fee for The Pigeon Detectives to £4500 plus £750 for support act, in total across all venues. (£5900 altogether) | DONE
Amended security in North Point for The Pigeon Detectives to £300 | DONE
Updated Family Film Day capacity at Winifred Holtby from 50 to 300 | DONE
Updated venues for Hekima | DONE
Updated FOH and FOH Manager costs across all acts and venues | DONE
Added £600 evaluation to forecast across all areas (£200 per area) | DONE
Andrea to do:
Insert a column on Summary Tab V6 on Cashflow spreadsheet to show £35k addition | AR Done 3.1.17
Deducted individual amounts from LIVE Budgets re £35k ie C155.C273.C115.C301.GH amended staffing & Local artists amount no amendment necessary as no budget set up. | AR Done 3.1.17
Add to LIVE budget spreadsheet on BTO | AR Done 3.1.17
Andrea to do:
Would you like a column on V6 Summary showing how much left to spend? NO, but email my spreadsheet from Onedrive & see what Thom & Louise think? | DONE
Adviced by Thom/Louise to move £1k of the £9k to security in Feb 17 & the remaining £8k to leave in Security until they have worked on other Festival budgets & decided | DONE
where the budget will go.
Andrea to do:
Work on BFI Budget & go through with Glenn | DONE
Louise adv'd budget for Family Film Day = £22,365 & difference between £41,300 & £22,365 is for Outdoor Event = £18935 | DONE
Add forecast detail from LIVE Budget to my Onedrive BTO S/Sheet & Description detail to my Onedrive S/Sheet | DONE
Email updated One Drive S/Sheet to Thom & Louise to review | DONE
TF 17.1.17
Amended fee for Marketing Engagement Lead from £900 to £600 per area | DONE
Amended Johnny Vegas title to Secret Gig | DONE
TF 18.1.17
Re-added general area columns, following excel file corruption | DONE
Updated security costs and security notes tab | DONE
Updated Crew costs according to Carys' quote from HPSS for £5880. Have split this between Crew and Tech Manager / Apprentice to reflect budget allocations | DONE
Moved the following costs to the general area columns: Marketing Manager/Apprentice, Marketing Campaign, Evaluation, Remote Box Office Set Up | DONE
Removed the formula on the Tech Hires line which linked the tech hire forecast costs at the base of the Feb 17 tab in agreement with Carys. These costs have been replaced by an actual quote from HPSS for the supply of tech hires to all venues. For fine details ask Carys. | DONE
Added a general festival costs column and included Tech Hires in this. | DONE
Deleted outdated notes on security cells. | DONE
Moved the access forecast for Meet Fred (£500) from North to East where the BSL perf is taking place. | DONE
Moved the access forecast for Red Shed (£500) from East to North where the BSL perf is taking place. | DONE
Fixed link on Security line item title | DONE
Andrea to do:
Copy in New Budget Forecast spreadsheet | DONE
Include comments from each tab in to Budget Forecast as comments & delete tabs | DONE
Cross check & update forecast into LIVE budget | DONE
TF 26.1.17
Have removed first aid costs from security line and moved these to duty of care line. We had budgeted £250 against duty of care originally. | DONE
Updated Tech Hires, Tech Manager/Apprentice, Crew and Transport lines with Carys' HPSS quote | DONE
Duty of care - this has been updated to include £600 per area for first aid costs | DONE
Build general area costs | DONE
Consider adding a first aid line into the budget | DONE
TF to discuss tech quotes and Carys' spreadsheet with Andrea | DONE
Louise to do:
Louise awaiting quote for First Aid but is trying to get it for free - 4.1.17 | DONE
Louise awaiting updated budget from 'Film Hub North' (Anna/Caroline), re Outdoor Event for BFI | DONE
Carys to do: 10.11.16
Provide detailed crewing costs per show and quote for tech hire from HPSS | DONE
Andrea to do:
Ask Glenn Harley re ticket income - Glenn adv'd that this will show in the LIVE Budget eventually but only after it has been reconciled & finance are happy it is correctly split. | DONE
If you need any information in the interim speak to Jess Fairbank re ticket sales data
TF 1.2.17
Increased artists fee for Secret Gig to £3000 covering Ceri Dupree (£2000) and Gogglebox (£1000) | DONE
Added forecast figures and ticket sales prediction to Secret Gig | DONE
Reduced artists liaison cost to reflect Pigeon Detectives deal memo and Red Shed accommodation only. | DONE
Thom to do:
Provide detailed crewing costs per show and quote for tech hire from HPSS
Amend box office income for May/Oct/Feb 18 to take into account £2921.00 increased ticket monies from Feb 17 Festival
FOH Costs Feb 17 Festival - spread the amount across Feb 17 but do not change total.
Add columns on to Feb 17 tab (having to do again as seems there is an excel problem where it is showing in the Online excel but not on other version?
Start May 17 Festival budget Tab
TF to look at Dressing Room costs with Louise
Consider allocation of Photography/Filming spread throughout BTO festival
Consider transport forecast given that some of this will be used to cover tech hires & Hull 2017 van is booked for BTO
Clarify Dressing Room / Green Room / Artists Liaison forecast - should this be act (or possibly venue) specific?
Should access include some costs (e.g. design) against Mr B relaxed performances?
Adjust forecast figures in the Feb 17 Budget to decrease the adverse variances (the adverse variance will reduce from £-1530 to £-750)
AR - Details I need from Thom/Carys/Louise:
FOH Costs - forecast £3236, budget £1920 - adverse variance of £-1316 what caused the increase against budget & is this going to be a reflection of May/Oct & Feb 18? Emailed 1.2.17
Dressing Room/Green Room Set Up/Artist Liason - forecast £1550, budget £420 - adverse variance of £-1330 what caused the increase against budget & is this going to be a reflection of May/Oct & Feb 18? Emailed 1.2.17
Duty of Care - the additional First Aid costs - Is this going to impact May/Oct & Feb 18 also? Ask at next meeting
Feb 17 Budget will dictate the format for future spend, adverse variances will not reflect on future budgets - as per Henri Friday 10.2.17 | DONE
Budget details for BFI as there is now actual spend & Encumb? C601 - Received - Need to Update on LIVE | DONE
First Aid Cost - New Quote £1400 - Is this confirmed?
Phase 3 Electric to put in @ 2 venues (ie Sirius & Freedom Centre) Quote £1500 - Where is this reflected in the budget?
Evaluation ZK109.K274.C700 £3150 - If being taken out of evaluation where will this be allocated in the budget?
Need to evaluate Feb 17 spend as do not have relevant PO's raised to account for the spend?
Prestige Security PO £2050 ZK107.K265.C700 Budget only £1400 as the additional £35k BFI has been removed and added to C601 & re-allocated budget does not include security?
TF - 20.2.17
FOH Costs updated - will need calculations adding following the Feb festival
First Aid cost updated in line with actual quote | DONE
Updated Security cost in line with actual quote | DONE
Removed Access £500 for JOAN, which does not require this cost allocation | DONE

## Budget Forecast
Back to Ours C700
Budget | LIVE BUDGET TABS |  | Codes | Actual | Encumb | FESTIVALS BUDGET & FORECAST |  |  |  | Total | CORE NNT TEAM | MODEL: FOUR FESTIVALS IN THREE AREAS | Development | Contingency 3% | Budget Remaining | 2016 | 2017 | [11 empty] | 2018 | [8 empty] | Total
[6 empty] | 2017-02-01 | 2017-05-01 | 2017-10-01 | 2018-02-01 | [6 empty] | 2016-12-01 | Jan 17 | Feb 17 | 2017-03-01 | Apr 17 | May 17 | 2017-06-01 | Jul 17 | Aug 17 | 2017-09-01 | Oct 17 | Nov 17 | 2017-12-01 | Jan 18 | Feb 18 | 2018-03-01 | Apr 18 | May 18 | 2018-06-01 | Jul 18 | Aug 18 | 2018-09-01
1200 | R&D | Venue Partner Go & See | ZK102.K201.C700 | 129 | [5 empty] | 0 | 1200 |  |  |  | 1071 |  | 0 | 321 | 150 | 150 |  | 150 |  | 150 |  |  | 150 | [10 empty] | 1071 | Forecast Updated 6.1.17
1500 | C&P | Programme Director-Exps | ZK103.K223.C700 | [6 empty] | 0 | 1500 |  |  |  | 1500 |  |  | 300 |  |  | 300 |  | 300 |  | 300 |  |  |  |  | 300 | [7 empty] | 1500 | Forecast Updated 6.1.17
8400 | C&P | Programme Consultant-monthly meetings 1 Year | ZK103.K161.C700 | [6 empty] | 0 | 8400 |  |  |  | 8400 |  | 0 | 2250 | 4125 |  | 2025 | [16 empty] | 8400 | Forecast Updated 6.1.17
8640 | C&P | Duty of Care | ZK103.K227.C700 |  |  | 1440 | 1800 | 2700 | 2700 | 8640 |  |  |  |  | 8640 |  |  | 1404 | 36 |  |  | 1800 |  |  |  | 2700 |  |  |  | 2700 | [7 empty] | 8640 | Forecast Updated 6.1.17
22050 | Perf | Performer Fees-Feb17 | ZK104.K232.C700 | 4500 | [5 empty] | 0 |  |  | 22050 |  | 17550 |  |  | 5550 | 12000 | [18 empty] | 17550 | Forecast Updated 6.1.17
40800 | Perf | Performer Fees-May 17 | ZK104.K232.C700 | [6 empty] | 0 |  |  | 40800 |  | 40800 | [5 empty] | 5000 | 30800 | 5000 | [14 empty] | 40800 | Forecast Updated 6.1.17
48960 | Perf | Performer Fees-Oct 17 | ZK104.K232.C700 | [6 empty] | 0 |  |  | 48960 |  | 48960 | [9 empty] | 4500 | 35000 | 9460 | [10 empty] | 48960 | Forecast Updated 6.1.17
48960 | Perf | Performer Fees-Feb 18 | ZK104.K232.C700 | [6 empty] | 0 |  |  | 48960 |  | 48960 | [13 empty] | 15000 | 27000 | 6960 | [6 empty] | 48960 | Forecast Updated 6.1.17
4823.1 | Contingency | 3% Contingengy | ZK104.K232.C700 | [6 empty] | 0 |  |  |  | 4823 | 4823 |  |  | 662 |  |  |  | 1224 |  |  |  | 1468 |  |  |  | 1469 | [7 empty] | 4823 | Forecast Updated 6.1.17
11340 | T&P | Local Technical Manager | ZK106.K253.C700 |  |  | 2160 | 2700 | 3240 | 3240 | 11340 |  |  |  |  | 11340 |  |  | 2160 |  |  |  | 2700 |  |  |  | 3240 |  |  |  | 3240 | [7 empty] | 11340 | Forecast Updated 6.1.17
15120 | T&P | Crew | ZK106.K253.C700 |  |  | 2880 | 3600 | 4320 | 4320 | 15120 |  |  |  |  | 15120 |  |  | 1680 | 1200 |  |  | 3600 |  |  |  | 4320 |  |  |  | 4320 | [7 empty] | 15120 | Forecast Updated 6.1.17
3780 | T&P | Local Technical Apprentice | ZK106.K253.C700 |  |  | 720 | 900 | 1080 | 1080 | 3780 |  |  |  |  | 3780 |  |  | 720 |  |  |  | 900 |  |  |  | 1080 |  |  |  | 1080 | [7 empty] | 3780 | Forecast Updated 6.1.17
5040 | T&P | FOH Manager | ZK106.K253.C700 |  |  | 960 | 1200 | 1440 | 1440 | 5040 |  |  |  |  | 5040 |  |  | 960 |  |  |  | 1200 |  |  |  | 1440 |  |  |  | 1440 | [7 empty] | 5040 | Forecast Updated 6.1.17
5040 | T&P | FOH Team | ZK106.K253.C700 |  |  | 960 | 1200 | 1440 | 1440 | 5040 |  |  |  |  | 5040 |  |  | 960 |  |  |  | 1200 |  |  |  | 1440 |  |  |  | 1440 | [7 empty] | 5040 | Forecast Updated 6.1.17
9450 | T&P | Marketing Manager | ZK106.K253.C700 | 1200 | 600 | 1800 | 2250 | 2700 | 2700 | 9450 |  |  |  |  | 8250 |  |  | 600 |  | 750 | 750 | 750 |  | 900 | 900 | 900 |  | 900 | 900 | 900 | [7 empty] | 8250 | Forecast Updated 6.1.17
3150 | T&P | Marketing Apprentice | ZK106.K253.C700 |  |  | 600 | 750 | 900 | 900 | 3150 |  |  |  |  | 3150 |  |  | 600 |  |  |  | 750 |  |  |  | 900 |  |  |  | 900 | [7 empty] | 3150 | Forecast Updated 6.1.17
9700 | VL | Venue Hire | ZK107.K136.C700 |  |  |  | 2500 | 3600 | 3600 | 9700 |  |  |  |  | 9700 | [6 empty] | 2500 |  |  |  | 3600 |  |  |  | 3600 | [7 empty] | 9700 | Forecast Updated 19.1.17
33300 | VL | Venue Technical Hire | ZK107.K136.C700 |  |  | 4200 | 7500 | 10800 | 10800 | 33300 |  |  |  |  | 33300 |  |  | 2700 | 1500 |  | 2500 | 5000 |  |  |  | 10800 |  |  |  | 10800 | [7 empty] | 33300 | Forecast Updated 19.1.17
2460 | VL | Dressing Room / Green Room | ZK107.K136.C700 |  |  | 420 | 600 | 720 | 720 | 2460 |  |  |  |  | 2460 |  |  | 378 | 42 |  | 300 | 300 |  |  |  | 720 |  |  |  | 720 | [7 empty] | 2460 | Forecast Updated 19.1.17
11100 | VL | Transport | ZK107.K258.C700 |  |  | 1400 | 2500 | 3600 | 3600 | 11100 |  |  |  |  | 11100 |  |  | 1400 |  |  | 1000 | 1500 |  |  | 1000 | 2000 | 600 |  |  | 2600 | 1000 | [6 empty] | 11100 | Forecast Updated 19.1.17
1400 | VL | Security | ZK107.K265.C700 |  |  | 1400 |  |  |  | 1400 |  |  |  |  | 1400 |  |  | 1400 | [19 empty] | 1400 | Forecast Updated 19.1.17
3000 | L&D | Insurance / Licences | ZK108.K162.C700 | [6 empty] | 0 | 3000 |  |  |  | 3000 |  |  | 62 | 688 |  |  | 750 |  |  |  | 750 |  |  |  | 750 | [7 empty] | 3000 | Forecast Updated 19.1.17
10000 | MDC | Brand development | ZK109.K270.C700 | 2845 | 412 |  |  |  |  | 0 |  | 10000 |  |  | 7155 |  |  | 1887 | 2000 | 1000 |  | 800 |  | 468 |  |  |  | 1000 | [9 empty] | 7155 | Forecast Updated 19.1.17
5000 | MDC | Core Campaign | ZK109.K270.C700 | 400 | [5 empty] | 0 |  | 5000 |  |  | 4600 |  |  | 1000 | 3600 | [18 empty] | 4600 | Forecast Updated 19.1.17
20500 | MDC | Campaign - venue specific | ZK109.K270.C700 | 200 | 1704 | 3500 | 5000 | 6000 | 6000 | 20500 |  |  |  |  | 20300 |  |  | 1000 | 2300 |  |  | 5000 |  |  |  | 6000 |  |  |  | 6000 | [7 empty] | 20300
3600 | MDC | Remote box office set up | ZK109.K273.C700 |  |  | 900 | 900 | 900 | 900 | 3600 |  |  |  |  | 3600 |  |  | 2700 | [11 empty] | 900 | [7 empty] | 3600 | Forecast Updated 19.1.17
4725 | MDC | Photography | ZK109.K158.C700 |  |  | 900 | 1125 | 1350 | 1350 | 4725 |  |  |  |  | 4725 |  |  | 900 |  |  | 500 | 625 |  |  |  | 1350 |  |  |  | 1350 | [7 empty] | 4725 | Forecast Updated 19.1.17
3150 | MDC | Evaluation | ZK109.K274.C700 |  |  | 600 | 750 | 900 | 900 | 3150 |  |  |  |  | 3150 |  |  |  |  | 1141 | 1141 | 375 |  |  |  | 375 |  |  |  | 118 | [7 empty] | 3150 | Forecast Updated 19.1.17
6000 | E&C | Access performances | ZK110.K281.C700 |  |  | 1500 | 1500 | 1500 | 1500 | 6000 |  |  |  |  | 6000 |  |  | 1500 |  |  | 500 | 1000 |  |  |  | 1500 |  |  |  | 1500 | [7 empty] | 6000 | Forecast Updated 19.1.17
24000 | A&M | Tech Co-ordinator | ZK114.K299.C700 | [6 empty] | 0 | 24000 |  |  |  | 24000 | [22 empty] | 24000 | Forecast Updated 6.1.17
18750 | A&M | Project Administrator | ZK114.K299.C700 | [6 empty] | 0 | 18750 |  |  |  | 18750 | [22 empty] | 18750 | Forecast Updated 6.1.17
-24000 | A&M | Tech Co-ordinator | ZK114.K299.C700 | [6 empty] | 0 | -24000 |  |  |  | -24000 | [22 empty] | -24000 | Forecast Updated 6.1.17
-18750 | A&M | Project Administrator | ZK114.K299.C700 | [6 empty] | 0 | -18750 |  |  |  | -18750 | [22 empty] | -18750 | Forecast Updated 6.1.17
2400 | A&M | Venue Team support | ZK114.K299.C700 | 15 | [5 empty] | 0 | 2400 |  |  |  | 2385 |  | 0 | 286.8 | 448.2 | 150 | 300 | 150 |  |  |  | 450 |  | 450 |  | 150 | [7 empty] | 2385 | Forecast Updated 19.1.17
354588.1 |  |  |  | 9289 | 2716 | 26340 | 36775 | 47190 | 47190 | 157495 | 16500 | 15000 | 160770 | 4823 | 345299 | 0 | 0 | 33380.8 | 28089.2 | 3191 | 14316 | 63074 | 5300 | 1518 | 6700 | 80033 | 10210 | 2350 | 15900 | 73277 | 7960 | 0 | 0 | 0 | 0 | 0 | 0 | 345299
Back to Ours - BFI - C601
Budget | LIVE BUDGET TABS |  | Codes | Actual | Encumb | FESTIVALS BUDGET & FORECAST |  |  |  | Total
[6 empty] | 2017-02-01 | 2017-05-01 | 2017-10-01 | 2018-02-01
1530 | L&D | Licenses | ZK108.K162.C601 | [7 empty] | 1530 |  |  |  | 1530 |  |  |  |  | 1530 | [17 empty] | 1530
4050 | C&F | Interactive activities by Into Film (value of partnership funding TBC) | ZK101.K207.C601 | [8 empty] | 4050 |  |  | 4050 |  |  |  |  | 4050 | [17 empty] | 4050
8001 | C&P | Production | ZK103.K161.C601 | [7 empty] | 8001 |  |  |  | 8001 |  |  |  |  | 8001 | [17 empty] | 8001
| C&P | Project Manager | ZK103.K223.C601 | [11 empty] | 0 |  |  |  |  | 0 | [17 empty] | 0
2394 | MDC | Marketing | ZK109.K270.C601 |  | 232 | [7 empty] | 2394 |  | 2162 |  |  |  |  | 2162 | [17 empty] | 2162
39 | A&M | Admin & Misc | ZK114.K115.C601 | 39 | [6 empty] | 39 |  |  |  | 0 |  |  |  |  | 0 | [17 empty] | 0
1026 | Perf | Contingency 5% | ZK104.K232.C601 | [10 empty] | 1026 | 1026 |  |  |  |  | 1026 | [17 empty] | 1026
18935 | [11 empty] | 18935 |  |  | 18935 |  |  |  |  | 18935 | [17 empty] | 18935
35975 |  |  |  | 39 | 232 | 0 | 0 | 0 | 0 | 0 | 9570 | 22985 | 2394 | 1026 | 35704 |  |  | 0 | 0 | 35704 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 35704
-53148 | Ticket Income
337415.1
|  | C601 | Check | 35975 |  |  | 35975 |  |  | 0
|  | C700 | Check | 354588 |  | Check | 354588 |  |  | 0
Note on C7: Robinson Andrea (2017): To include First Aid
Note on T7: Robinson Andrea (2017): Carys adv'd PO raised North East Medical Svs £1404 16.2.17
Note on C13: Robinson Andrea (2017): Manager Cost of East for all Festival days £2100. Manager Cost of West & North for all Festival days £1800.
Note on C14: Robinson Andrea (2017): Total Technical Crew Cost of East, North & West for all Festival Days
Note on C16: Robinson Andrea (2017): Includes Front of House staffing.
Note on C18: Robinson Andrea (2017): Total Marketing Engagement Fee for area 30 days x £90
Note on C19: Robinson Andrea (2017): Total Marketing Engagement Fee for area 30 days x £90
Note on C20: Robinson Andrea (2017): £1400 budgeted Feb 17 but re-allocated to Security 17/11/16 as per Henri
Note on C21: Robinson Andrea (2017): Made up of light, sound, AV & set. Requires estimates from Carys. Updated forecast cost of Rev & the Makers & Johnny Vegas Venue Tech Hire to £200 per venue. Candoco cost covers hire for all areas in one column.
Note on T22: Robinson Andrea (2017): Carys adv'd PO raised & apprvd £378 All Occasions 16.2.17
Note on C23: Robinson Andrea (2017): Includes Van Hire
Note on C24: Robinson Andrea (2017): Security in Venues where there is a bar. Northpoint shopping centre will provide own security inc. Pigeon Detectives Gig. Added £1k (from additional £35k) for barriers as per Louise/Thom 5/1/17. 17/1/17 TF updated these figures according to quote from Prestige based upon £50 per person per event. 18/1/17 TF general area security costs include cost of barrier (mojo) hire.
Note on T24: Robinson Andrea (2017): Carys adv'd PO raised & apprvd £2050 Prestige Security - Only £1400 in budget as £35k additonal spend has been realllocated to BFI C601.
Note on T25: Robinson Andrea (2017): Carys adv'd Pmnt by C/Card £61.93 to PPL 16.2.17
Note on C28: Robinson Andrea (2017): Cost of print, marketing for festivals & venue dressing
Note on C29: Robinson Andrea (2017): Cost of setting up remote box offices in each area.
Note on C30: Robinson Andrea (2017): Covers documentation & marketing photography during the festival
Note on C31: Robinson Andrea (2017): Requires conversation with Evaluation Team. Would this cover an independent evaluation? Louise Yates adv'd by email 16.2.17 - £3150 will be coming out in either Mar or Apr 17.
Note on C32: Robinson Andrea (2017): Covers BSL & relaxed performances
Note on T37: Robinson Andrea (2017): Carys adv'd Stampreo £60 petty cash & £226.80 Sirius Academy PO raised & apprvd 16.2.17

## British Film Institute BFI
British Film Institute - BFI - Budget
Back to Ours C601
Codes | Summary Expenditure | TOTAL BUDGET | Picture House Family Film Day | Picture House Family Film Day | Picture House Family Film Day | Jaws Outdoor Event | INCOME | CASH | IN-KIND | NOTES
| Back to Ours - Cinematic Experience | [5 empty] | BFI | 35975
| Hull City of Culture venue partnerships | [5 empty] | HULL 2017 |  |  | Marketing and social media/Producer and management
ZK108.K162.C601 | Licenses | 1530 | 510 | 510 | 510 |  | Ticket Sale income |  |  | please estimate ticket sales and price of ticket
ZK101.K207.C601 | Interactive activities | 4050 | 1350 | 1350 | 1350
| Interactive activities by Into Film (value of partnership funding TBC) | 0 | [7 empty] | Chris Fell - Leeds Int Film Festival
ZK103.K161.C601 | Production | 8001 | 2667 | 2667 | 2667 |  |  |  |  | Louise Yates waiting for breakdown from Chris Fell. Henri requires more detail.
ZK103.K223.C601 | Project Manager | 2394 | 798 | 798 | 798 |  |  |  |  | However use this breakdown which Thom emailed me Fri 10/2/17 and input in LIVE
ZK109.K270.C601 | Marketing | [8 empty] | Budget
| TOTAL | 15975 | 5325 | 5325 | 5325
ZK104.K232.C700 | Contingency 5% | 1065 | 355 | 355 | 355
| GRAND TOTAL | 35975 | 5680 | 5680 | 5680 | 18935 | TOTAL | 35975
14.2.17 - Take out £5,325 as per GH - agreed at SLT Meeting - decided cannot add at the
moment.
15.2.17 - Henri to advise re split of £2,394 Project Management & Marketing. Needs to be
shown as Project Manager & Marketing seperately.
Note on B6: Robinson Andrea (2017): Estimate based on 35% of net box office of 700 tickets sold across 9 screenings.
Note on B7: Robinson Andrea (2017): Sneaky Experience - 3 days including actor, costume hire, scripts & activities prep.
Note on B9: Robinson Andrea (2017): Lumen

## Sheet3 (hidden)
NORTH | 2017-02-01 | 2017-05-01 | 2017-10-01 | 2018-02-01 | WEST | 2017-02-01 | 2017-05-01 | 2017-10-01 | 2018-02-01 | EAST | 2017-02-01 | 2017-05-01 | 2017-10-01 | 2018-02-01
Number of days | 10 | 10 | 10 | 8 | Number of days | 10 | 10 | 10 | 8 | Number of days | 10 | 10 | 10 | 8
Number of venues | 7 | 7 | 7 | 7 | Number of venues | 7 | 7 | 7 | 7 | Number of venues | 7 | 7 | 7 | 7
Number of paid venues | 7 | 7 | 7 | 7 | Number of paid venues | 7 | 7 | 7 | 7 | Number of paid venues | 7 | 7 | 7 | 7
Fee per paid venue | 350 | 350 | 350 | 175 | Fee per paid venue | 350 | 350 | 350 | 175 | Fee per paid venue | 350 | 350 | 350 | 175
Fee per technical hire | 700 | 700 | 700 | 700 | Fee per technical hire | 700 | 700 | 700 | 700 | Fee per technical hire | 700 | 700 | 700 | 700
Dressing room set up per venue | 85 | 85 | 85 | 85 | Dressing room set up per venue | 85 | 85 | 85 | 85 | Dressing room set up per venue | 85 | 85 | 85 | 85
Transport per venue | 71 | 71 | 71 | 35 | Transport per venue | 71 | 71 | 71 | 35 | Transport per venue | 71 | 71 | 71 | 35
Duty of care |  |  |  |  | Duty of care |  |  |  |  | Duty of care
Number of people | 20 | 20 | 20 | 20 | Number of people | 20 | 20 | 20 | 20 | Number of people | 20 | 20 | 20 | 20
Charge per day | 8 | 8 | 8 | 8 | Charge per day | 8 | 8 | 8 | 8 | Charge per day | 8 | 8 | 8 | 8
TECHNICAL COST | 12142 | 12142 | 12142 | 8945 | TECHNICAL COST | 12142 | 12142 | 12142 | 8945 | TECHNICAL COST | 12142 | 12142 | 12142 | 8945
Daily rate for: |  |  |  |  | Daily rate for: |  |  |  |  | Daily rate for:
Local Technical Manager | 150 | 150 | 150 | 150 | Local Technical Manager | 150 | 150 | 150 | 150 | Local Technical Manager | 150 | 150 | 150 | 150
- Days needed | 12 | 12 | 12 | 12 | - Days needed | 12 | 12 | 12 | 12 | - Days needed | 12 | 12 | 12 | 12
Local Technical Apprentice | 50 | 50 | 50 | 50 | Local Technical Apprentice | 50 | 50 | 50 | 50 | Local Technical Apprentice | 50 | 50 | 50 | 50
- Days needed | 12 | 12 | 12 | 12 | - Days needed | 12 | 12 | 12 | 12 | - Days needed | 12 | 12 | 12 | 12
Crew | 120 | 120 | 120 | 120 | Crew | 120 | 120 | 120 | 120 | Crew | 120 | 120 | 120 | 120
- Number needed | 2 | 2 | 2 | 2 | - Number needed | 2 | 2 | 2 | 2 | - Number needed | 2 | 2 | 2 | 2
FOH / Box Office Manager | 80 | 80 | 80 | 80 | FOH / Box Office Manager | 80 | 80 | 80 | 80 | FOH / Box Office Manager | 80 | 80 | 80 | 80
FOH / Box Office team | 40 | 40 | 40 | 40 | FOH / Box Office team | 40 | 40 | 40 | 40 | FOH / Box Office team | 40 | 40 | 40 | 40
- Number needed | 2 | 2 | 2 | 2 | - Number needed | 2 | 2 | 2 | 2 | - Number needed | 2 | 2 | 2 | 2
FESTIVAL STAFF | 6400 | 6400 | 6400 | 5600 | FESTIVAL STAFF | 6400 | 6400 | 6400 | 5600 | FESTIVAL STAFF | 6400 | 6400 | 6400 | 5600
Daily rate for: |  |  |  |  | Daily rate for: |  |  |  |  | Daily rate for:
Local Marketing & Engagement Manager | 150 | 150 | 150 | 150 | Local Marketing & Engagement Manager | 150 | 150 | 150 | 150 | Local Marketing & Engagement Manager | 150 | 150 | 150 | 150
- Days needed | 10 | 10 | 10 | 10 | - Days needed | 10 | 10 | 10 | 10 | - Days needed | 10 | 10 | 10 | 10
Local Marketing & Engagement Apprentice | 50 | 50 | 50 | 50 | Local Marketing & Engagement Apprentice | 50 | 50 | 50 | 50 | Local Marketing & Engagement Apprentice | 50 | 50 | 50 | 50
- Days needed | 10 | 10 | 10 | 10 | - Days needed | 10 | 10 | 10 | 10 | - Days needed | 10 | 10 | 10 | 10
Photography / filming | 50 | 50 | 50 | 50 | Photography / filming | 50 | 50 | 50 | 50 | Photography / filming | 50 | 50 | 50 | 50
Evaluation | 25 | 25 | 25 | 25 | Evaluation | 25 | 25 | 25 | 25 | Evaluation | 25 | 25 | 25 | 25
Marketing campaign per venue | 500 | 500 | 500 | 500 | Marketing campaign per venue | 500 | 500 | 500 | 500 | Marketing campaign per venue | 500 | 500 | 500 | 500
Access performance | 550 | 550 | 550 | 550 | Access performance | 550 | 550 | 550 | 550 | Access performance | 550 | 550 | 550 | 550
Remote box office set up | 300 | 300 | 300 | 300 | Remote box office set up | 300 | 300 | 300 | 300 | Remote box office set up | 300 | 300 | 300 | 300
ENGAGEMENT | 7100 | 7100 | 7100 | 6950 | ENGAGEMENT | 7100 | 7100 | 7100 | 6950 | ENGAGEMENT | 7100 | 7100 | 7100 | 6950
TOTAL COST | 25642 | 25642 | 25642 | 21495 | TOTAL COST | 25642 | 25642 | 25642 | 21495 | TOTAL COST | 25642 | 25642 | 25642 | 21495
TOTAL COST
2017-02-01 | 76926
2017-05-01 | 76926
2017-10-01 | 76926
2018-02-01 | 64485
295263
Target cost
Original budget | 500000
Revised | 344000
Reduction | 31.2%
Engagement / Delivery budget | 300975
Revised | 207070.8