Ballad of Big Lil: 29.03.2017 Actions

Lindsey Alvis, Henri Duckworth, Paul Veysey, Jenny Hutt, Martin Atkinson

- List to Guildhall about all spaces request by the end of 7 April.

- LA to check all plans are in place for meeting in MCR.

- Friday 7 April White Card in Manchester.

- MA to call Unison and book space. Beginning of October until Monday 20 November.

- Big silver cod, Snd, LX, lots of cable.

- Adrian wants to use piano in there.

- Put together a list of stage management.

- JH to look through framework for cvs. HD to trawl through some others.

- AD role, need to put through 2 or 3 people.

- Costume Supervisor required. Amanda has some suggestions.

- REX might send over a more Junior member of staff who knows the stock at REX.

- PV to gather together JDs for production roles. All will be freelance contract that more than covers Equity Minimum.

- One call out just after Easter for all production positions.

- First draft of JDs for 21 April to go out the following week, by Friday 28 April.

- MA to contact Rebekkah and confirm all times on schedule.

- Use Holy Apostle for community cast rehearsals. Book with Rebekkah.

- Setup volunteer conversation with Harriet to talk about all vols, including volunteer coordinator.

- Need a brief of community cast. To be confirmed at White card meeting.

- Put performance schedule on agenda for White Card.

- Double check new rules on equity agreement.