## Sheet1
LGBT 50 - DUCKIE SUMMER TEA PARTY PRODUCTION SCHEDULE |  |  |  | version | 2
date & time | activity | deliveries | location | contractor | notes
Thursday 27th July
12:00 | Security shift starts |  | QVS | Showsec | 2 x SIA
| Build podium decks |  | QVS | HPSS
| Build PA decks |  | QVS | HPSS
| Build drape truss |  | City Hall portico | HPSS
| Build control area |  | QVS | HPSS
20:00 | Security shift change |  |  |  | 2 x SIA overnight
| Build Heras around structures |  | QVS | Local crew
| Call ends |  |  | HPSS
Friday 28th July
6:00 | Road closures in place | TM signage etc. | Carr Lane / Paragon St. | SEP Events
8:00 | Build balcony stage | HPSS vans | City hall balcony | HPSS
MEWP delivered
| Security shift change |  | QVS | Showsec | 2 x SIA
9:00 | Start podium décor | Footprint truck | QVS | Footprint
| Rig bunting |  | QVS | HPSS rigger and local crew | MEWP required
| Rig PA |  | QVS | HPSS
9:30 | Rig stretch tent | Tentickle vehicle | City hall balcony | Tentickle
13:00 | Lunch
14:00 | Rig lighting |  | City hall balcony | HPSS | Stretch tent complete
| Rig backline |  | City hall balcony | HPSS
| Continue podiums |  | QVS | Footprint
| Continue bunting & dressing |  | QVS | Rigger & local crew | MEWP required
Dinner break as schedule allows
18:00 | Yorkshire Dance Sound check |  | QVS & balcony | HPSS
& dress rehearsal
20:00 | Rehearsal ends
| Work as required |  |  | All
| Security shift change |  | QVS | Showsec | 2 x SIA overnight
22:00 | Call ends - site clear
| TM stewards stand down |  | Carr Lane & Paragon St | SEP Events | Roads remain closed
Saturday 29th - Show Day
7:30 | TM steward shift starts |  | Carr Lane & Paragon St. | SEP Events
8:30 | Production staff on standby |  |  | All
9:00 | Yorkshire Dance rehearsal
|  | Bins delivered | Paragon St & QVS
|  | Tables & Chairs delivered | QVS | local crew
|  | Toilets delivered | Paragon St | Addplant
10:00 | Yorkshire Dance rehearsal ends
Duckie artists sound checks
11:00 | Show security staff briefing |  | QVS | Showsec
11:45 | Yorkshire Dance rehearsal
12:00 | Medical personnel arrive | Medical marquee delivered | Paragon St | North East Medical
12:15 | Yorkshire Dance rehearsal ends
12:30 | Pre event ELT meeting |  | Event Control
13:00 | EVENT STARTS
13:00 | Amy Lame intro & DJ |  | City Hall balcony
Tea service 1
13:20 | Toffer Campbell |  | Podium 2
13:35 | Lip Sinkers |  | All podiums
13:40 | London Gay Big Band |  | City Hall balcony
14:00 | Band change over |  | City Hall balcony
Tea service 2
14:05 | Amy Lame DJ |  | City Hall balcony
| Lip Sinkers |  | All podiums
14:20 | Yorkshire Dance |  | Balcony & QVS
15:00 | ELT meeting |  | Event Control
Tea service 3
15:05 | Amy Lame DJ |  | City Hall balcony
15:10 | Sugar Dandies |  | Podium 2
| Band change over |  | City Hall balcony
15:25 | Bird La Bird |  | Podium 2
15:42 | Lip Sinkers |  | All podiums
15:45 | London Gay Big Band |  | City Hall balcony
16:00 | Tea service 4
16:10 | London Gay Big Band |  | City Hall balcony
| Victoria Sin |  | Podium 4
| Bloke in a bath |  | Podium 1
16:45 | Sugar Dandies |  | Monument
| Band change over |  | City Hall balcony
17:00 | ELT meeting
Tea service 5
17:10 | Yorkshire Dance
17:45 | Backchat Brass Parade
17:59 | Confetti Cannons |  | City Hall balcony
18:00 | EVENT ENDS | NO VEHICLE MOVEMENTS IN QVS BEFORE 20:00 UNLESS AUTHORISED BY EVENT CONTROL
18:00 | Pack down balcony stage |  | City Hall balcony | HPSS
| Pack down FOH control |  | QVS | HPSS
| Pack down table & chairs |  | QVS | local crew
18:30 | Doors open for I Feel Love |  | City Hall
20:00 | I Feel Love starts
| Show security stand down |  |  | Showsec
| Begin bunting removal |  | QVS | Rigger & local crew
| Strike podiums |  | QVS | Footprint & local crew
|  | Tables & Chairs collected | QVS | City Furniture
|  | Astroturf removed | QVS
|  | Toilets collected | Paragon St
Bins collected
| Strike PA |  | QVS | HPSS
| Strike cable ramp |  | QVS | local crew
21:30 | I FEEL LOVE ENDS | PAUSE ALL ACTIVITY IN QVS DURING EGRESS
21:45 | Continue load out
| Strike equipment from balcony |  | City Hall balcony
| Confetti clean up |  | QVS | Streetscene
De rig stretch tent
22:00 | TM stewards stand down |  | Paragon St & Carr Lane | SEP Events | roads remain closed
1:00 | Load out complete
Sunday 30th July
9:00 |  | MEWP collected
12:00 | TM removed |  | Paragon St & Carr Lane | SEP Events | roads re open