HCAL Education Meeting 15/05/17

Hull 2017 to support HCAL in their existing education programme, discussion of who is leading on what;

- Explore Art – Room 10 (under 5’s). Delivered by HCAL but relevant to TP. David is re-costing this (including costs for the TP programme and delivery, and the taking out/reinstating) to be confirmed by 22nd May (should be around £2k)

- A Day in the Life – school workshop programme, practice led in Live Art Space. Delivered by HCAL, x2 over half terms. David to send through costings/a financial limit for this.

- Junior Open – led by Ferens’ curatorial team. Sara to meet with the team to discuss this further.

- Adult Saturday classes – still a question over who will lead on this. X3 classes over the course of TP.

- Public programme, artist/curator talks and tours – how is this funded? income generation or TP engagement fund?

- Simon and Peter to sign off the above

- Malcolm to send through visitor figures for the year and more in-depth figures for daily traffic (identifying key busy and quiet times – red, amber, green).

- Ferens copy deadlines TBC (seasons 3/4)

Timeline

w/c 29/5 – All costs together and agreed, shared calendar drafted to look at schedule as a whole

First week in June – First draft of education programme

19th/26th – Final draft of education programme