In Venue Checklist: Show days.

The purpose of this check-list is to ensure all key elements are in place prior to starting our service delivery and to ensure we are ready for the next day.

| Timing | Area | Tasks | / |
| --- | --- | --- | --- |
| ON ARRIVAL 1.30pm | General Office | - Review notes from previous day: - Feedback from volunteers and any volunteer changes. - List of any changes for the next day. - Check in with control - Check schedules have not altered. . - Go to Daily meeting (if requested) - Check in with Logistics and get radios if required. - Collect radios and earpieces (core team) - Pick up Comms pack (1st and 2nd) - Check emails/ texts for non arrival or changes from GC /Hull - Check weather report. |  |
| -2.0 (2pm) | production office. | - Collect Show Comms (if required) - Pick up and check into venues (dependent on venue is whether this needs to be done QVS/Deep imperative this is done prior to 3pm) - Log all staff arrival time |  |
|  | Leader | - Team / venue leader prep: - Check vollie and break time - Check processional sheets are ready for the day - Check welfare room is clean and ready for usage - Vollies briefing in welfare centre |  |
| -1:00 (3pm) | workforceOffice | - Check workforce in - Run through schedules with team - Brief vollies and team in venue - Meet with Production manager - Volunteers dinner session. |  |
| -1:00 (3pm) | Office | - Distribute radios, etc to relevant parties. |  |
|  | rooms | - Check if all room are prepped and clean for next sitting of crew. |  |
|  | workforce | - Brief the ELT. - Brief the team on who is responsible for each ceremony on athlete briefing. |  |
|  | office | - Check there is a dial tone on all phones. |  |
|  | producer | - Check in with GC main team |  |
| 0:30 | workforce | - Commence workforce place in venue and in position |  |
| 15 mins to go | Protocol | - Count down in all venues and locked in. |  |
| 4pm | ALL | - Start show as per running sheet |  |
| During and Post. | ELT | Meet each hour on the 15 past hour unless an emergency occurs. |  |
|  | Office 5pm | - Full production meeting - Minute with all incidents reported from the night before (comms in this meeting too) |  |
| +0:30 | Venue Team Brief | - Team debrief in the Welfare room - Crew food (from 8pm to 10pm)- Not volunteers - Unison building locked up and cleaned for the next day. - End of day production meeting – in Danish one. (10pm) |  |
| 24/7 | At home | - ELT on call in case of incident. Phones charged at all times. |  |