Humber Bridge Test 2

| Date & time | Activity | Notes |
| --- | --- | --- |
| August 30th 09:00 14:00 | Prepare LED strings for rigging at Bridge workshop Rope Access crew arrive onsite: - Project briefing - Site induction - Go to top of Hessle tower - Access the main cable | Roger Barrett / Star Damian Walsh and crew / Hull 2017 |
| August 31st 09:00 16:00 19:00 22:00 (approx) | Traffic Management installed East footpath closed Rope access crew prep kit Test rig LEDs on hangers near Hessle tower TM removed and site clear by this time Onsite to connect power and control equipment *power required from Hessle Tower* Lighting test Test Ends Footpath remains closed overnight | TM contractor Star Hull 2017 / Star HBB |
| Sept 1st 09:00 16:00 | Contingency Day Install TM in work area Install as per schedule for 31st (if no rigging possible on 31st) OR Dering LEDs TM removed by this time and site clear East Footpath reopens (if derig is complete) | TM Contractor Star Star |
| Sept 2nd 09:00 16:00 | Contingency Day 2 – required if de rig does not happen on Sept 1st Install TM in work area De rig LEDs TM removed by this time and site clear East Footpath reopens | TM contractor Star |