Hull 2017 
Project Plan

Hull 2017 
Ballad of Big Lil 
by Maxine Peake

Music & Lyrics 	Adrian McNally & The Unthanks
Director		Sarah Frankcom

Summary

Inspired by the women who campaigned for better and safer working conditions on Britain’s trawler ships, the Ballad of Big Lil is a site specific project with a strong mix of music, movement and text. The production explores Hull’s heritage as a port city, and celebrates the hard and dangerous life of trawlerman ruled by a feudal system of ship owners in a voracious capitalist system. At the heart of the story is Lillian Bilocca, a women who dared to speak out and take action to improve conditions for men at sea. With a community chorus, live music and an open bar, the evening will be a visceral, joyous evening of song, music & theatre. 

Venue		TBC

A civic space with the faded grandeur of the past. 
Current options being considered include the Guildhall, Hull

Music 	New works written by Adrian McNally and The Unthanks. To be performed live by the Unthanks. 
One song, the Ballad of Big Lil, to have lyrics by Maxine Peake, with original music by Adrian McNally and the Unthanks.

Cast & Band 	Maximum cast size = 7

Maximum band size = 4

Project Timeline

June 16 	Brief delivered to Hull 2017 by Maxine Peake

July 16 	Commission the script, 
Secure director, Confirm details of RET involvement

August 16 	Site scouting & site to be identified.
Secure dramaturg, designer, choreographer, sound & lighting designer production manager

22 Sept 16	Hull 2017 UK City of Culture Launch

10 -14 Oct 	R&D in Manchester. 
To be arranged by Michelle Hickman from Manchester
Royal Exchange with actors from Streetcar. 
In attendance: 	Maxine Peake
			Sarah Frankcom
 			Adrian McNally

Oct 16 	First full draft of the script delivered. 
Image & copy generated

Nov 11	Confirm site – venue contracts

Jan 17 		Final script delivered

Sign off brochure page

April 17 	Prelim designs & outline costings

Casting & stage management team

July 17		Casting of Community Cast

 		Final designs & detailed costings

Sept 17 	Pre-Production – build & prep venue

Oct 17 		Rehearse 

		Install at venue

Nov 17 	Tech, open & perform

Dec 17 	Close

The following details describe the production parameters which reflect the project budget 

Creative Team
Writer					Maxine Peake 
Director 				Sarah Frankcom 
Music & lyrics  			Adrian McNally & The Unthanks TBC

Set & Costume Designer		Amanda Stoodley TBC 
Lighting Designer			Chris Davey TBC
Sound Designer			Peter Rice TBC
Casting Director

Dramaturg 				Steven Greenhorn TBC 
Associate Director (Comm Cast)	to be Hull based

Consultant				Rupert Creed TBC

Production Team 
Production Manager
Company Manager
DSM
ASM
Sound Op 
LX Op
Dresser
Technician 
Production Sound

Production LX
Costume Supervisor

FOH Manager
Box Office Manager & Assistant

Stewards 
Security
Access Performance Interpreter

Bar staff 				Licensee & Operator TBC

Production Schedule 
All dates to be discussed and confirmed with MP/SF

Rehearsals Week 1			w/c 2 Oct 2107		Reh in Manchester
Rehearsals Week 2 			w/c 9 Oct			Reh in Manchester
Rehearsals Week 3			w/c 16 Oct 			Reh in Hull
Rehearsals Week 4			w/c 23 Oct			Reh in Hull

Production / Tech Week		w/c 30 Oct				
First Preview				Fri 3 Nov
Second Preview			Sat 4 Nov 	
Performance Week 1			w/c 6 Nov

Press Night				Tues 7 Nov or Wed 8 Nov

Perf Week 2				w/c 13 Nov

Perf Week 3 				w/c 20 Nov

Perf Week 4				w/c 27 Nov
Final Performances			Sat 1 Dec 2017

Proposal for possible Comm Ensemble process:
Community Cast			To be 16 + years old 
 					Overall Group of 30 – for min 20 per perf
 					Rehearsals In Hull
					3 sessions a week, evenings & weekend
					6 sessions during Tech Week, daytime, evening & Sat
 					6 performances per week during run

Min 6 performances per week inc one matinee.