## Sheet1
DATE |  | Action / Description | Specific Meeting Attendees | Specific Venues
MARCH
Thursday | 23rd March | Story Headline Notes to be sent | DdA
Monday | 27th March | Story Meeting | DdA / TR / AY (NH to attend if requested) | Leeds
Tuesday | 28th March | Story Meeting | DdA / TR / AY | Leeds
Wednesday | 29th March | Story and update sent to all
Thursday | 30th March
Friday | 31st March | Decision re Project Go Ahead
APRIL
Monday | 3rd April
Tuesday | 4th April
Wednesday | 5th April
Thursday | 6th April | Creative Workshop (Creative workshop group) | DdA / TR / AY / NH / Bruno Merz / Mark Bailey | Hull
Friday | 7th April | Creative Workshop | DdA / TR / AY / NH / Bruno Merz / Mark Bailey | Hull
Monday | 10th April | Things to do in this week - Seating Discussion; Outreach Stickers / Flyers to be decided and finalised ready for production - Graphic Designer to be available to create artwork; Project Re-Budget to begin | Angela / Niccy / Jo
Tuesday | 11th April
Wednesday | 12th April | Seating Meeting | Niccy / Angela / Wilky / Sam
Thursday | 13th April
Friday | 14th April | Good Friday
Monday | 17th April | Easter Monday
Tuesday | 18th April | Initial Music Themes Delivered for Approval |  | Online Process to BBC and Hull 2017
Wednesday | 19th April | Performance Schedule Discussion
Thursday | 20th April | Venue informed and notified : Payment terms discussed. | NH
Friday | 21st April | Outreach Materials Initial Music Themes delivered
Monday | 24th April | First Outreach Workshop - with generic stickers for schools
Week of | 24th April | Site Visit | Wilky / Angela / Niccy / Sam + contractors
Week of | 30th April | Outreach Stickers to be delivered if possible
MAY
Week beg | 15th May | Confirm Projection Film Locations; Agree Set Design
| after May | Council Permissions Applied for if required
JUNE
Week beg | 5th June | Children's Performer Auditions - to find child performers ( age 5 to 8 )/ older young adult performers ( 15+ ) ( 8 of each tbc ) |  | Hull
Sunday | 11th June | TBC Children's Performer Auditions |  | Hull
Week beg | 12th June | Agree Children's Rehearsal Schedule for License process - with restrictions for rehearsal times from Child Licensing Hours information for two age groups
Week beg | 19th June | Cast children so license process can begin
Week beg | 26th June | Music Score Delivery for Part Production and Conductor Prep
| 26th June to 2nd July | Hull Literary Festival
JULY
Week beg | 17th July | Children's Performer Rehearsals begin
AUGUST
Week beg | 7th August | Tech Week
Week beg | 14th August | Performance Week