Production Schedule

Into the Light

Tuesday 24th July			6pm- 8pm 	Full Cast Rehearsal in QVS

Wednesday 25th July			6pm- 8pm 	Full Cast Rehearsal in QVS

| Friday 28th July |  |  | Notes |
| --- | --- | --- | --- |
| Time |  |  |  |
| 1pm |  | Move costumes to The Duckie Shop |  |
|  |  | Kirsty/Hannah |  |
|  |  | Clear Horncastle spaces |  |
| 5pm |  | Meet Dresser/ Volunteers |  |
| 5:00pm – 5:45pm |  | Meet Full Cast at The Duckie Shop |  |
|  |  | Change into costumes |  |
| 6:00pm – 8:00pm |  | Dress Rehearsal |  |
|  |  | Band Sound check |  |

| Saturday 29th July |  |  |
| --- | --- | --- |
| 9:30am | All Cast to meet at The Duckie Shop |  |
|  | Rehearsal in the Square |  |
| 11:00am | Back Chat Brass Band arrive | Based ?? |
|  | Marshal Volunteers arrive (25) Into the Light Production Meeting (Including YD staff) Not cast/dancers | Sarah to meet and greet |
| 11:45am | Full run of the show with Brass Band Marshals |  |
| 12:15pm | Lunch – clear the square Volunteer lunches provided by Hull 2017 (Marshals/dressers) |  |
|  | Best of Fiends – Band set up |  |
| 1:00pm | Costumes/ Makeup/Hair | Duckie Shop |
| 2:00pm | Half hour call for cast and both bands |  |
| 2:20pm | Parade from Duckie Shop to QVS Lead by Brass Band Cue Best of Fiends Amy Lame – Introduce the work | Full Cast |
| 2:30pm | Arrive in QVS Perform “Into the Light” |  |
| 3:00pm | Walk back to The Duckie Shop Route: Along Ferrens Way |  |
| 3:00pm – 3:30pm | De brief on the performance |  |
| 3:30pm – 4:30pm | Break |  |
| 5:00pm | Final half hour call for the performance |  |
| 5:30pm | Parade from Duckie Shop to QVS Lead by Brass Band Cue Best of Fiends Amy Lame – Introduce the work |  |
| 5:40pm | Arrive in QVS Perform “Into the Light” |  |
| 6:10pm | Finish “Into the Light” Finale moment!!!! |  |

Marshal plan:

- Parade –(there and back) 5 at the back/ 5 at the front at the sides/ 5 in the middle/ 10 waiting at QVS

- Marshals to be assigned to one member of YD staff who will direct them to what they need to do throughout the day.

Yorkshire Dance Staff

Manage 10 people and 6 Marshalls each

Depending on what work happens around the podiums

Kirsty	Redhead

Antony	 Dunn

April Skipp

Sarah Shooter

One to One support on the day (to review)

- Henry

- Alix

- Liam (Under 18)

- Andie/Frank  (Under 18)  ????