| ARTIST | CONTACT | OUTLINE | AREA | KEY DATES | TO DO |
| --- | --- | --- | --- | --- | --- |
| Joshua Sofaer | joshua@joshuasofaer.com http://www.joshuasofaer.com/ | Nose Emporium | Bransholme North Point Shopping Centre – Louise Smith | 27/28 July site visit 28 – 30 August get in 31-4 Sept – Live 5 Sept get out | Marketing steer – Nose to see you # or 2017? Safeguarding – DBS check to be sent in, policy/guide advice to be given Risk Ass & PL to be sent to centre Set design plan Volunteer requirements sent to SR |
| Periplum Claire Raftery Damian Wright | periplumperformance@googlemail.com http://www.periplum.co.uk | Message in a Bottle | East – Greatfield with workshops also on Preston road Greatfield Hub – Claire Taylor claire@greatfield.org.uk Child Dynamix – Paul Clark Paul.Clark@childdynamix.co.uk Purple House - Christina Reading Christina.Reading@purplehouse.co.uk St Stephens – Jennie Mason jennie_mason@hotmail.com | Dates to be discussed – workshops late August – residency Late Sept & early Oct | Site visit 12 July Getting delivery options & contacts – Milk float ongoing List of east & north groups – Site visit to Preston Road & Greatfield Schedule of deliveries – a more realistic plan than 7 consecutive days Bottle design Rearrange meeting with Claire Taylor |
| Davy & Kristin McGuire | davyandkristinmcguire@gmail.com http://www.davyandkristinmcguire.com | Little Film Scenes | North/West Bingo Hall & Anlaby Rd | 7 – 12th Sept Live | Location – Outside of Bingo Hall Permissions for bingo hall Story board – Katy sending email |