Hull 2017 
Project Summary 

Hull 2017 
Ballad of Big Lil 
by Maxine Peake

Music & Lyrics 	Adrian McNally &The Unthanks
Director		Sarah Frankcom

Summary

Inspired by the women who campaigned for better and safer working conditions on Britain’s trawler ships, the Ballad of Big Lil is a site specific project with a strong mix of music, movement and text. The production explores Hull’s heritage as a port city, and celebrates the hard and dangerous life of trawlerman ruled by a feudal system of ship owners in a voracious capitalist system. At the heart of the story is Lillian Bilocca, a women who dared to speak out and take action to improve conditions for men at sea. With a community chorus, live music and an open bar, the evening will be a visceral, joyous evening of song, music & theatre.

The following details describe the production parameters which reflect the project budget

Venue		TBC, Hull

A civic space with the faded grandeur of the past. 
Current options being considered include the Guildhall, Hull

Music 	New musical works written by Adrian McNally and The Unthanks. To be performed live by the Unthanks. 
One song, the Ballad of Big Lil, to have lyrics by Maxine Peake, with original music by Adrian McNally and the Unthanks.

Cast & Band  	Cast of 8

Band of 6
	Max cast & band no more than 14

Digital 	Explore live broadcast & filming opportunities to extend reach for audiences.

Project Timeline

June 16 	Brief delivered to Hull 2017 by Maxine Peake

July 16 	Commission the script, 
Secure director, Confirm details of RET involvement

August 16 	Site scouting & site to be identified.

Sept/Oct 16	Recce visit for Guildhall – SF, AS, PR as well as MP if schedule allows

10 -14 Oct 	R&D in Manchester. 
To be arranged by Michelle Hickman from Manchester
Royal Exchange with actors from Streetcar. 
In attendance: 	Maxine Peake
			Sarah Frankcom
 			Adrian McNally (only avail 10 & 11 and tbc)
			Amanda Stoodley

Nov/Dec 16 	Secure dramaturg, designer, choreographer, sound & lighting designer production manager

First full draft of the script delivered

Image & copy generated

Confirm site – venue contracted

Feb 17 	Final script delivered

Sign off season brochure page

April 17 	Prelim designs & outline costings

Casting of professional company 

Stage management team confirmed

July 17		Recruitment & Casting of Community Cast

Final designs & detailed costings

Sept 17 	Pre-Production – build & prep venue

Oct 17 		Rehearse 

		Install at venue

Nov 17 	Tech, open & perform

Nov 17 	Close

Creative Team
Writer					Maxine Peake 
Music & lyrics  			Adrian McNally & The Unthanks TBC

Director 				Sarah Frankcom

Set & Costume Designer		Amanda Stoodley 
Lighting Designer			Chris Davey 
Sound Designer			TBC 
Casting Director			TBC – RET?
Associate Director (Comm Cast)	to be Hull based

Consultant				TBC

Production Team 
Production Manager
Company Manager
DSM
ASM
Sound Op 
LX Op
Dresser
Technician 
Production Sound

Production LX
Costume Supervisor

FOH Manager
Box Office Manager & Assistant

Stewards 
Security
Access Performance Interpreter

Bar staff 				Licensee & Operator TBC

Production Schedule 
All dates to be discussed and confirmed with MP/SF and Unthanks
Rehearsals Week 1			w/c 2 Oct 2107		Reh in Manchester 
 				 			 		(Pro Cast)
 									Reh in Hull Comm Cast

Rehearsals Week 2 			w/c 9 Oct			Reh in Manchester

(Pro Cast)
 									Reh in Hull Comm Cast

Rehearsals Week 3			w/c 16 Oct 			Reh in Hull
Rehearsals Week 4			w/c 23 Oct			Reh in Hull
Start venue set up

Production / Tech Week		w/c 30 Oct				
First Preview				Fri 3 Nov
Second Preview			Sat 4 Nov 	
Performance Week 1			w/c 6 Nov

Press Night				Tues 7 Nov or Wed 8 Nov

Perf Week 2				w/c 13 Nov
Final Performances			Sat 18 Nov 2017

Proposal for possible Community Ensemble process:
Community Cast			To be 16 + years old 
 					Overall Group of 30 – for min 20 per perf
 					Rehearsals in Hull
					3 sessions a week, evenings & weekend
					6 sessions during Tech Week, daytime, evening & Sat
 					6 performances per week during run

Min 6 performances per week inc one matinee.

Updated: LA 28.11.16