## YEAR PROGRAMME
YEAR LONG TRANSFORMATIVE FILM PROGRAMME OVERVIEW
PROJECTS THAT MATTER TO LIAM IN BLUE
SEASON | PROJECT TITLE | BOX OFFICE HOLDER | CONTRACT HOLDER | PROJ REF. | DATE | PROGRAMMING ORGANISATION | LOCATION | TARGET AUDIENCE DEMOGRAPHIC | TARGET AUDIENCE NOS. | Marketing: L/R/N | REPORT DUE
YEAR LONG | Hull Short Film City | HIC - TBC | LEEDS FILM | LEEDS-2017-HSFC | YEAR LONG | LEEDS FILM and HIC | Hull Truck and Middleton Hall |  | 385
| LIFF comes to HIC | HIC - TBC | LEEDS FILM | LEEDS-2017-LIFF | YEAR LONG | LEEDS FILM and HIC | Hull Truck and Middleton Hall |  | 706
MADE IN HULL | Anthony Minghella Retrospective | HULL UNI | LIAM - HULL 2017 | HULL2017-JAN-AMR | 24-26 Jan 2017 | JAMES - UNIVERSITY OF HULL | Middleton Hall | Students/Middleclass lecture attenders, local young professionals | 235 | Posters for local distribution, regional Press Release, some content could be national worthy. | 2016-02-26
| Basil Kirchin: Mind on the Run | HULL 2017 | LIAM - HULL 2017 | HULL2017-FEB-BKMOTR | 18 Feb 2017 | MARTELL - SERIOUS/LISA LIVE CINEMA UK | Hull City Hall | TBC | 600 | TBC | 2016-03-19
| Back to Ours: Cinematic Experience FEB | HULL 2017 | LIAM - HULL 2017 | HULL2017-FEB-BTO | 22,23,25 Feb 2017 | CHRIS FELL - LEEDS FILM AND HIC | Archbishop Sentamu, East Hull Hymers College, West Hull Kingswood Academy, Bransholme | Local families. | 7 |  | 2016-03-26
| Hull on Film: Yorkshire Film Archive | HIC | MELANIE - DOC/FEST | DOCFEST-FEB-HOF | 24 Feb 2017 | MEL- DOC/FEST, YFA AND HIC |  |  | 150 |  | 2016-03-25
| HIC Additional Programme for WOW | HIC | HIC | HIC-FEB-WOW | Feb - Mar 2017 | JO PARSONS - SHOWROOM/HIC | Middleton Hall and Hull Truck |  | 235 |  | 2016-04-12
| WOW Hull: On Screen | HULL 2017 | LINDSEY - HULL 2017 | HULL2017-MAR-WOW | 10-12 Mar 2017 | JO PARSONS - SHOWROOM | Hull City Hall and local shop | young women, polish community, | 765 |  | 2016-04-13
| Ziggy Stardust and the Spiders from Mars | HULL 2017 | LIAM - HULL 2017 | HULL2017-MAR-ZIG | 17 Mar 2017 | JO WINGATE - SENSORIA AND HIC | Fruit | music lovers/film lovers | 59 |  | 2016-04-18
| City of Cinema | HULL UNI - TBC | LIAM - HULL 2017 | HULL2017-MAR-COC | 25-26 Mar 2017 | JAMES - UNIVERSITY OF HULL | Middleton Hall | regional film makers | 176 |  | 2016-04-27
ROUTES AND ROOTS | Doc 'n Roll Film Festival | HULL 2017 | LIAM - HULL 2017 | HULL2017-APR-DNRF | 27 - 30 April 2017 | DOC 'N ROLL AND HIC
| Back to Ours: Jaws attacks Hull | HULL 2017 | LOUISE - HULL 2017 | HULL2017-MAY-BTOJAWS | 26 May -5 Jun 2017 | LIVE CINEMA UK
| Back to Ours: Cinematic Experience MAY | HULL 2017 | LOUISE - HULL 2017 | HULL2017-MAY-BTO | 26 May -5 Jun 2017 | LEEDS FILM AND HIC
| Where are we Now? Festival | HULL 2017 | LIAM - HULL 2017 | HULL2017-JUN-WAWN | 2 - 4 Jun 2017 | NEU REEKIE
| Doc/Fest Satellite Screening | HIC | MEL - DOC/FEST | DOCFEST-JUN-DFSS | 7 - 14 Jun 2017 | DOC/FEST AND HIC |  |  |  |  | 2016-07-17
| Hull Film Festival | HIC | HIC | HIC-JUN-HFF | 28 Jun - 9 Jul 2017 | HIC |  |  |  |  | 2016-08-10
| The Floating Cinema | TBC | ANNA - UP PROJECTS | UP PROJECTS-JUN-TFC | 28 Jun - 9 Jul 2017 | HIC AND UP PROJECTS
FREEDOM | Docs on the Docks | HIC | MEL - DOC/FEST | DOC-JUN-DOTD | 28 Jun - 9 Jul 2017 | DOC/FEST AND HIC |  |  |  |  | 2016-08-10
| Tea Break Short Film Festival | TBC | MAL - CREATIVE COLLEGE | CREATIVECOL-JUN-TBSFF | 28 Jun - 3 Jul 2017 | CREATIVE COLLEGE
| LGBTQ 50 | HULL 2017 - TBC | CIAN - HULL 2017 | HULL2017-JUL-LGBTQ50 | 22 - 29 Jul 2017 | HIC
| Freedom Symposia | HULL UNI | LIAM - HULL 2017 | HULL2017-JUL-FS | JUL -SEPT | UNIVERSITY OF HULL
TELL THE WORLD | Back to Ours: Cinematic Experience OCT | HULL 2017 | LOUISE - HULL 2017 | HULL2017-OCT-BTO | 28 Oct - 5 Nov 2017 | JO - SENSORIA AND HIC
| New Live Cinema Europe | HULL 2017 | SAM - HULL 2017 | HULL2017-OCT-NLCE | SEPT/OCT | LISA - LIVE CINEMA UK
| Hull Scream | HIC | HIC | HIC-OCT-HS | 31 Oct 2017 | HIC |  |  |  |  | 2016-12-01
| Hull Noir | TBC | LIAM - HULL 2017 | HULL2017-NOV-HN | 17 - 19 Nov 2017 | HIC
| Substance Festival | HULL 2017 | MARTIN - HULL 2017 | HULL2017-DEC-SUBFEST | 8-10 Dec 2017 | LUKE BAINBRIDGE
2018 | Back to Ours: Cinematic Experience | HIC | HIC | HIC-FEB18-BTO | 14,15,17 FEB | Louise -Hull 2017 | Archbishop Sentamu, East Hull Hymers College, West Hull Kingswood Academy, Bransholme |  |  |  | 2016-03-26

## CONTRACTS BY PROJECT
CONTRACTS, CONTRACTS, CONTRACTS AND PARTNERSHIPS
SEASON | PROJECT TITLE | PROJ REF. | BUDGET HOLDER | BOX OFFICE HOLDER | DELIVERY PARTNER | SUPPORTING PARTNER | CONTRACT TYPE/NOTE
MADE IN HULL | Anthony Minghella Retrospective | HULL2017-JAN-AMR | LIAM - HULL 2017 | HULL UNI | HULL UNI |  | CONTRACT UNI OF HULL TO PROGRAMME AND DELIVER THIS EVENT.
| Basil Kirchin: Mind on the Run | HULL2017-FEB-BKMOTR | LIAM - HULL 2017 | HULL 2017 | SERIOUS | LIVE CINEMA UK | LIVE CINEMA UK CONTRACTED AND PAID TO NEGOTIATE FILM LICENCE /DELIVER LIVE CINEMA SCREENING OF DR PHIBES
| Back to Ours: Cinematic Experience FEB | HULL2017-FEB-BTO | LIAM - HULL 2017 | HULL 2017 | LEEDS FILM | HIC | CONTRACT WITH LEEDS FILM TO DELIVER BTO, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
| HIC Additional Programme for WOW | HIC-FEB-WOW | HIC | HIC | HIC | SHOWROOM | WHAT ARE THE MARKETING RULES FOR WOW - THIS WAS SAM'S IDEA TO HAVE A LEAD UP TO THE EVENT - THEY ARE GOING TO PRINT WITH THEIR BROCHURE THIS WEEK… HOW DO THEY REFERENCE WOW?
| WOW Hull: On Screen | HULL2017-MAR-WOW | LINDSEY - HULL 2017 | HULL 2017 | SHOWROOM |  | CONTRACT TO JOAN AT THE SHOWROOM FOR HER TO PROGRAMME AND PRODUCE THE FILM PART OF WOW
| Ziggy Stardust and the Spiders from Mars | HULL2017-MAR-ZIG | LIAM - HULL 2017 | HULL 2017 | SENSORIA |  | CONTRACT JO AT SENSORIA TO PROGRAMME AND PRODUCE THIS EVENT
| City of Cinema | HULL2017-MAR-COC | LIAM - HULL 2017 | HULL UNI - TBC | HULL UNI |  | CONTRACT UNI OF HULL TO PROGRAMME AND DELIVER THIS EVENT.
ROUTES AND ROOTS | Doc 'n Roll Film Festival | HULL2017-APR-DNRF | LIAM - HULL 2017 | HULL 2017 | DOC N ROLL | HIC | CONTRACT COLM AT DOC 'N ROLL FILM FESTIVAL TO DELIVER THIS FESTIVAL IN PARTNERSHIP WITH HIC - ITS HIC LEGACY TO BRING THIS FESTIVAL TO HULL IN 2018 AND BEYOND
| Back to Ours: Jaws attacks Hull | HULL2017-MAY-BTOJAWS | LOUISE - HULL 2017 | HULL 2017 | LIVE CINEMA UK |  | CONTRACT LISA AT LIVE CINEMA UK TO PROGRAMME AND DELIVER THIS EVENT. (IN THEORY - WILL SPEAK WITH ANNABEL)
| Back to Ours: Cinematic Experience MAY | HULL2017-MAY-BTO | LOUISE - HULL 2017 | HULL 2017 | LEEDS FILM | HIC | CONTRACT WITH LEEDS FILM TO DELIVER BTO, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
| Where are we Now? Festival | HULL2017-JUN-WAWN | LIAM - HULL 2017 | HULL 2017 | NEU REEKIE |  | CONTRACT NEU REEKIE TO USE THIS BUDGET TO DELIVER FILM EXHIBITION WITHIN THE FESTIVAL
FREEDOM | LGBTQ 50 | HULL2017-JUL-LGBTQ50 | CIAN - HULL 2017 | HULL 2017 - TBC | HIC | LGBT HULL | CONTRACT HIC TO PROGRAMME AND WORK WITH THE LGBT TEAM TO DELIVER A FILM STRAND TO LGBTQ50
| Freedom Symposia | HULL2017-JUL-FS | LIAM - HULL 2017 | HULL UNI | HULL UNI |  | CONTRACT HULL UNI TO PROGRAMME AND DELIVER SEASON
TELL THE WORLD | Back to Ours: Cinematic Experience OCT | HULL2017-OCT-BTO | LOUISE - HULL 2017 | HULL 2017 | SENSORIA | HIC | CONTRACT JO AT SENSORIA TO PROGRAMME AND DELIVER, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
| New Live Cinema Europe | HULL2017-OCT-NLCE | SAM - HULL 2017 | HULL 2017 | LIVE CINEMA UK |  | THIS IS MATCH FUNDING FOR THEIR EUROPEAN FUNDED PROJECT. CREATING NEW LIVE CINEMA WORK - ONE PIECE WILL BE SHOWN IN HULL
| Hull Noir | HULL2017-NOV-HN | LIAM - HULL 2017 | TBC | HIC |  | CONTRACT HIC TO PROGRAMME AND DELIVER THE FILM STRAND OF THE CRIME WRITING FESTIVAL
| Substance Festival | HULL2017-DEC-SUBFEST | MARTIN - HULL 2017 | HULL 2017 | HULL 2017 / LUKE BAINBRIDGE |  | I HAVE NO IDEA
2018 | Back to Ours: Cinematic Experience | HIC-FEB18-BTO | HIC | HIC | HIC |  | HIC HAVE BEEN CONTRACTED BY FHN TO DELIVER THIS IN PARTNERSHIP WITH LOUISE HULL 2017 TEAM. THIS IS BECAUSE NO ONE KNOW WHAT IS HAPPENING TO HULL 2017 AFTER 2017, BUT I KNOW THAT YOU ARE PLANNING THE TOUR THIS HALF TERM. IF THERE WILL BE A LEGACY, HIC AND LOUISE ARE PROBABLY THE PEOPLE WHO WILL MAKE THIS HAPPEN.

## CONTRACTS BY ORGANISATION
DELIVERY PARTNER | PROJECT TITLE | SUPPORTING PARTNER | PROJ REF. | BUDGET HOLDER | BOX OFFICE HOLDER | CONTRACT TYPE/NOTE
HULL UNI | Anthony Minghella Retrospective |  | HULL2017-JAN-AMR | LIAM - HULL 2017 | HULL UNI | CONTRACT UNI OF HULL TO PROGRAMME AND DELIVER THIS EVENT.
| City of Cinema |  | HULL2017-MAR-COC | LIAM - HULL 2017 | HULL UNI - TBC | CONTRACT UNI OF HULL TO PROGRAMME AND DELIVER THIS EVENT.
| Freedom Symposia |  | HULL2017-JUL-FS | LIAM - HULL 2017 | HULL UNI | CONTRACT HULL UNI TO PROGRAMME AND DELIVER SEASON
SERIOUS | Basil Kirchin: Mind on the Run | LIVE CINEMA UK | HULL2017-FEB-BKMOTR | LIAM - HULL 2017 | HULL 2017 | LIVE CINEMA UK CONTRACTED AND PAID TO NEGOTIATE FILM LICENCE /DELIVER LIVE CINEMA SCREENING OF DR PHIBES - AS HULL2017 ARE THE BUDGET HOLDER, IS IT A HULL 2017 CONTRACT?
LEEDS FILM | Back to Ours: Cinematic Experience FEB | HIC | HULL2017-FEB-BTO | LIAM - HULL 2017 | HULL 2017 | CONTRACT WITH LEEDS FILM TO DELIVER BTO, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
| Back to Ours: Cinematic Experience MAY | HIC | HULL2017-MAY-BTO | LOUISE - HULL 2017 | HULL 2017 | CONTRACT WITH LEEDS FILM TO DELIVER BTO, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
SHOWROOM | WOW Hull: On Screen |  | HULL2017-MAR-WOW | LINDSEY - HULL 2017 | HULL 2017 | CONTRACT TO JOAN AT THE SHOWROOM FOR HER TO PROGRAMME AND PRODUCE THE FILM PART OF WOW
SENSORIA | Ziggy Stardust and the Spiders from Mars |  | HULL2017-MAR-ZIG | LIAM - HULL 2017 | HULL 2017 | CONTRACT JO AT SENSORIA TO PROGRAMME AND PRODUCE THIS EVENT
| Back to Ours: Cinematic Experience OCT | HIC | HULL2017-OCT-BTO | LOUISE - HULL 2017 | HULL 2017 | CONTRACT JO AT SENSORIA TO PROGRAMME AND DELIVER, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
DOC N ROLL | Doc 'n Roll Film Festival | HIC | HULL2017-APR-DNRF | LIAM - HULL 2017 | HULL 2017 | CONTRACT COLM AT DOC 'N ROLL FILM FESTIVAL TO DELIVER THIS FESTIVAL IN PARTNERSHIP WITH HIC - ITS THEIR LEGACY TO BRING AGAIN TO HULL IN 2018 AND BEYOND
LIVE CINEMA UK | Back to Ours: Jaws attacks Hull |  | HULL2017-MAY-BTOJAWS | LOUISE - HULL 2017 | HULL 2017 | CONTRACT LISA AT LIVE CINEMA UK TO PROGRAMME AND DELIVER THIS EVENT. (IN THEORY - WILL SPEAK WITH ANNABEL)
| New Live Cinema Europe |  | HULL2017-OCT-NLCE | SAM - HULL 2017 | HULL 2017 | THIS IS MATCH FUNDING FOR THEIR EUROPEAN FUNDED PROJECT. CREATING NEW LIVE CINEMA WORK - ONE PIECE WILL BE SHOWN IN HULL
NEU REEKIE | Where are we Now? Festival |  | HULL2017-JUN-WAWN | LIAM - HULL 2017 | HULL 2017 | CONTRACT NEU REEKIE TO USE THIS BUDGET TO DELIVER FILM EXHIBITION WITHIN THE FESTIVAL
HULL 2017 / LUKE BAINBRIDGE | Substance Festival |  | HULL2017-DEC-SUBFEST | MARTIN - HULL 2017 | HULL 2017 | I HAVE NO IDEA
HIC | LGBTQ 50 | LGBT HULL | HULL2017-JUL-LGBTQ50 | CIAN - HULL 2017 | HULL 2017 - TBC | CONTRACT HIC TO PROGRAMME AND WORK WITH THE LGBT TEAM TO DELIVER A FILM STRAND IN LGBTQ50
| Hull Noir |  | HULL2017-NOV-HN | LIAM - HULL 2017 | TBC | CONTRACT HIC TO PROGRAMME AND DELIVER THE FILM STRAND OF THE CRIME WRITING FESTIVAL
| Back to Ours: Cinematic Experience FEB 18 |  | HIC-FEB18-BTO | HIC | HIC | HIC HAVE BEEN CONTRACTED BY FHN TO DELIVER THIS IN PARTNERSHIP WITH LOUISE HULL 2017 TEAM. THIS IS BECAUSE NO ONE KNOWS WHAT IS HAPPENING TO HULL 2017 AFTER 2017, BUT I KNOW THAT YOU ARE PLANNING THE TOUR THIS HALF TERM. IF THERE WILL BE A LEGACY, HIC AND LOUISE ARE PROBABLY THE PEOPLE WHO WILL MAKE THIS HAPPEN.
HIC SUPPORTING PROJECTS | Back to Ours: Cinematic Experience FEB | HIC | HULL2017-FEB-BTO | LIAM - HULL 2017 | HULL 2017 | CONTRACT WITH LEEDS FILM TO DELIVER BTO, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
| Back to Ours: Cinematic Experience MAY | HIC | HULL2017-MAY-BTO | LOUISE - HULL 2017 | HULL 2017 | CONTRACT WITH LEEDS FILM TO DELIVER BTO, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
| Back to Ours: Cinematic Experience OCT | HIC | HULL2017-OCT-BTO | LOUISE - HULL 2017 | HULL 2017 | CONTRACT JO AT SENSORIA TO PROGRAMME AND DELIVER, HIC ARE SUPPORTING THE PROJECT AS THEY WILL BE THE LEGACY PARTNER. THIS IS PART OF THEIR PDP.
| Doc 'n Roll Film Festival | HIC | HULL2017-APR-DNRF | LIAM - HULL 2017 | HULL 2017 | CONTRACT COLM AT DOC 'N ROLL FILM FESTIVAL TO DELIVER THIS FESTIVAL IN PARTNERSHIP WITH HIC - ITS HIC LEGACY TO BRING THIS FESTIVAL TO HULL IN 2018 AND BEYOND

## HIC EXPECTATIONS
HIC EXPECTATIONS
HIC RECIEVE
1 | 43% of the overal BFI award is for the investment of HIC through: Anna and FHN support, direct investment in HIC (staff/project budgets etc), evaluation, and the business consultant
2 | Point 1. does not include cash value of partnerships with film organisations (Leeds Film, Doc/fest etc ) or Hull 2017 team
3 | Partnership with 7 organisations: Showroom, Doc/fest, Sensoria, Doc 'n Roll Film Festival, Leeds Film, Up Projects and Hull 2017
4 | Increase the range of film on offer in HIC programme through partnerships
5 | A Business Consultant which will generate a 5 year strategic plan for HIC
6 | Access to Hull 2017 marketing and promotion
7 | A year long evaluation of the TFCH programme which will support further funding applications
8 | Increase the audience for Indie film in Hull (local and national) through the Hull 2017 platform and partnerships
9 | HIC profile has been raised and will continue to be raised with the BFI and the national film network
10 | HIC are left with the independent film legacy and partnerships in Hull
HIC OFFER
1 | Work with all partners to bring a wider range of film programming to Hull
2 | Provide marketing within HIC brochure and social media for all partnership projects
3 | Assist with venue booking and costs for partnership projects
4 | Facilitate the projects through Programme Coordinator time and input and the board
5 | Promote the film activities and Hull 2017 year long venture
6 | Accredit BFI, FHN and Hull 2017 for support of projects
7 | Provide data and information for evaluations

## REPORTING SCHEDULE
REPORTING SCHEDULE | HULL 2017 IN ORANGE
PROJ REF. | JANUARY | FEBRUARY | MARCH | APRIL | MAY | JUNE | JULY | AUGUST | SEPTEMBER | OCTOBER | NOVEMBER | DECEMBER | JANUARY | FEBRUARY | MARCH
HIC SWOT ANALYSIS 2016 | 2016-01-15
HIC AUDIENCE DATA 2016 | 2016-01-15
HULL2017-JAN-AMR |  | 2016-02-26
HULL2017-FEB-BKMOTR |  |  | 2016-03-19
HULL2017-FEB-BTO |  |  | 2016-03-26
DOCFEST-FEB-HOF |  |  | 2016-03-25
HIC 1ST QUARTER AUDIENCE DATA |  |  |  | 2016-04-01
HIC-FEB-WOW REPORT |  |  |  | 2016-04-12
HULL2017-MAR-WOW |  |  |  | 2016-04-13
HULL2017-MAR-ZIG |  |  |  | 2016-04-18
HULL2017-MAR-COC |  |  |  | 2016-04-27
HULL2017-APR-DNRF |  |  |  |  | TBC
HULL2017-MAY-BTOJAWS | [5 empty] | TBC
HULL2017-MAY-BTO | [5 empty] | TBC
HULL2017-JUN-WAWN | [6 empty] | TBC
LEEDS-2017-HSFC | [6 empty] | 2016-07-15
LEEDS-2017-LIFF | [6 empty] | 2016-07-15
HIC 2ND QUARTER AUDIENCE DATA | [6 empty] | 2016-07-15
DOCFEST-JUN-DFSS | [6 empty] | 2016-07-17
MIDTERM BFI REPORT | [6 empty] | 2016-07-31
HIC-JUN-HFF REPORT | [7 empty] | 2016-08-10
UP PROJECTS-JUN-TFC | [7 empty] | TBC
DOCFEST-JUN-DOTD | [7 empty] | 2016-08-10
CREATIVECOL-JUN-TBSFF | [7 empty] | TBC
HULL2017-JULY-LGBTQ50 | [7 empty] | TBC
HULL2017-JUL-FS | [7 empty] | TBC
HULL2017-OCT-BTO
HULL2017-OCT-NLCE
HIC-OCT-HS REPORT | [11 empty] | 2016-12-01
HULL2017-NOV-HN
HULL2017-DEC-SUBFEST | [12 empty] | 2016-01-15
HIC FINAL AUDIENCE NUMBERS FOR 2017 | [12 empty] | 2016-01-15
LEEDS - 2017-HSFC | [12 empty] | 2016-01-15
LEEDS-2017-LIFF | [12 empty] | 2016-01-15
FINAL BFI REPORT | [13 empty] | 2016-02-28
HIC-FEB18-BTO REPORT | [14 empty] | 2016-03-26

## FINANCIAL RESPONSIBILITY
FUNDING AWARDS
COMPANY | AMOUNT | PROJECT | INFORMATION | SEASON
HULL INDEPENDENT CINEMA |  |  |  | JAN-MAR | APR-JUN | JUL-SEPT | OCT-DEC | JAN - FEB 2018
| 22000 | Coordinator | Oct 16 - Feb 2018 post
| 9000 | Marketing person | Oct 16 - Feb 2018 post
| 1700 | Towards extra marketing costs | print, Fb, website, PR etc
| 700 | WOW month leading up |  | FEB/MAR
| 12000 | Hull Film Festival | incl. Marketing, project manager, films, talent etc |  | 28-3 Jul
| 500 | Hull Scream | need to put most of the money in yourself |  |  |  | 2016-10-31
| 5325 | Back to Ours FEB 18 | changed this to minimise payments to Hull 2017 tbc
TOTAL | 51225
LEEDS FILM |  |  |  | JAN-MAR | APR-JUN | JUL-SEPT | OCT-DEC | JAN - FEB 2018
| 1800 | Hull Short Film | one per month
| 4800 | LIFF comes to HIC | 12 non-uk distributed films
TOTAL | 6600
DOC/FEST |  |  |  | JAN-MAR | APR-JUN | JUL-SEPT | OCT-DEC | JAN - FEB 2018
| 0 | Virtualilty Cinema
| 4000 | Hull on Film: Yorkshire Film Archive |  | 2016-02-24
| 979 | DOC/FEST Satelite |  |  | Friday 9 Jun
| 4216 | Docs on the Docks |  |  | 28-3 Jul
TOTAL | 9195
UP PROJECTS |  |  |  | JAN-MAR | APR-JUN | JUL-SEPT | OCT-DEC | JAN - FEB 2018
TOTAL | 15000 | The Floating Cinema |  |  | 28 Jun-3 Jul
CREATOR COLLEGE |  |  |  | JAN-MAR | APR-JUN | JUL-SEPT | OCT-DEC | JAN - FEB 2018
TOTAL | 2800 | TEA BREAK SHORT FILM FESTIVAL |  |  | 28 Jun - 3 Jul
HULL 2017 |  |  |  | JAN-MAR | APR-JUN | JUL-SEPT | OCT-DEC | JAN - FEB 2018
| 5325 | Back to Ours Feb | Contract with Leeds Film | 17-27 Feb
| 1600 | Anthony Minghella | Need to get TV prog, film licences etc - NEEDS TO BE GOOD! | 24 - 26 Jan
| 2100 | City of Cinema | Contract with Hull uni | 24-26 Mar
| 6450 | Mind on the Run | NEEDS LIVE:CINEMA SUPPORT - email lisa | 2016-02-18
| 21500 | WOW: HULL | Contract with Showroom | 10-12 MAR
| 1000 | Ziggy Stardust and the Spiders from Mars | URGENT - Been announced as on sale - contract with Sensoria | 2016-03-17
| 14450 | Doc 'n Roll Festival in Hull | Contract with Doc 'n Roll Festival |  | 27 - 20 APR
| 20000 | Jaws Attacks - Back to Ours | Contract with Live Cinema UK |  | 26 May-5 Jun
| 19000 | Where are we Now? | Contract with Neu Reekie |  | 2-4 JUN
| 5325 | Back to Ours May | Contract with Leeds Film |  | 26 May - 5 Jun
| 1400 | LGBTQ50 | Contract with SQUIFF |  |  | Sept
| 600 | Freedom Symposia | Contract will Hull Uni |  |  | SEPT
| 5325 | Back to Ours OCTOBER | Contract with Sensoria |  |  |  | OCT
| 8000 | New Live Cinema Europe | Contract with Live Cinema UK |  |  |  | OCT
| 1000 | Hull Noir | Contract with HIC |  |  |  | 17-19 Nov
| 19000 | Substance | Needs confirming that they will deliver |  |  |  | 8-10 Dec
TOTAL | 132075