15/11/2017

Turner Prize Events Meeting

Katy Fuller, Jenny Hutt, Lily Mellor, Rebecca Clark, Ben McKnight

Apologies: Chris Clay, Mike Berriman

- GUESTLIST

  - RSVP Responses
196 Yes RSVP on 15/11/17
Guestlist has been sent to TATE - JH has asked Hannah Morgan to chase TATE list. TATE has 50 including their staff

LM to chase Andrea - 1 place to fill. All other artists sorted.

JH/RC to get the seating plan from CC of Hull Minster layout, complete first pass at seating plan w/c 20/11/2017.

  - Accreditation
Wristbands have arrive – no accreditation. List of staff to be sent to all venues.

  - Press
BM asked if there is capacity to seat an extra 4-5 press?
JH to e-mail BM/DC about names and dietary requirements
BM to send press contact list to JH
Artists have been briefed by TATE not Hull 2017

- BBC

BBC guests on programme and inserts, 2-3 people on main programme

KF has pitched the below to BBC:
16:50 Martin Green
17:45 Goldie / Alex F
20:30 and 21:30 George Vasey and Sacha Craddock
21:30 Cosey Fanni Tutti

Earlier guests from 13:20 – are Hull 2017 expected to wrangle these guests?

George and Sacha are confirmed to do the live programme from Ferens at 20:30, and 21:30 - 22:00.

JH/RC to go through schedule and input BBC World/BBC 4/World Tonight/Look North/BBC News

JH to get speech notes for Goldie and TATE
BM to speak to Alex and ask if Goldie wants notes made for him

Martin welcome at 19:45, followed by Alex Farquharson. No speech from leader

- LM to speak to Chris Marr about Rosalind’s film

- Technical recce confirmed for 17/11/2017
Eimear, Alison, Lorrie on Standby for phone call at 12:30

- PRESS

- Welcome Press pack

- Schedules for:

Curators	 	- LM
Goldie		- JH
Press 		- MB to send to RC
Master		– RC

- BM – speech for Martin to welcome. Alex Farquharson to follow. JH to confirm.

- LM to send Rosalind’s films to Eimear McNamara

- Front Row - 28/29 November – BM awaiting confirmation 
No recce, but would need 2 hours at Ferens in Turner galleries 
George do pre-record in Hull and Sacha do live in London 
BM to chase for confirmation and more details

- BBC Radio 6 Music in live studio 01/12/2017 – 02/12/2017
Ferens FOH are charging £400 hire fee for the Live Art Studio for both days, Simon Green heavily discounted it (60%) – good promotion for Ferens.

- 4 x artists to be briefed on 05/12/2017 prior to the announcement. Brief to be sent in advance as well as briefed on the day
BM to arrange B&Q to do this / LM to contact artists about schedule

- Press file from 15:00 – 19:30 in Live Art Studio – who are the privileged few who know the winner? BM to confirm names

- Briefing
Goldie, artists, fact sheet for presenters, Ferens staff, Maria Balshaw
BM to pull press briefings together and confirm time, location and who will do brief

- MB to test Wi-Fi in Trinity Square café – you have to put your e-mail address in, is this a problem? MB confirmed W-Fi is strong.

- JH to create schedule for Goldie

- MINSTER

- 17/11/2017 – technical production schedule with JW.

- LM to confirm 350gsm place settings and 3 x logos to be printed on these. Names to be hand written

- JH to look at areas in Minster for volunteer break out area / Cry room for artists / storing kit for 28 x crew

- Turner Prize 2017 branding lectern/narthex

- LM to get quotes for T-Shirts, speak to Laura Smith about branding.

- JZ doing flowers – no candelabras. Some candles on the tables – factor in lighting candles. JH to speak to JZ Kirsty.

- KF – numbering tables. Table numbers in the same design as the place setting.

- Toilets - Signage – black and gold for toilets?

- CATERING

Menu – JH confirmed with Lesley 16/11/2017 
JH to confirm wine order with Saunts once menu is confirmed

- AOB

Alex to do the unveiling of a plaque AM of 05/12/17
LM to feedback to Simon Green that Alex is in the jury meeting 10:00-15:00