Extra shows – daylight, crowd numbers existing media coverage and complaints

Entrance via Thoresby Primary School – strong rejection from councillor, we will need a very strong practical reason beyond artistic to convince them.

Environmental impact – Need to consider how site will be treated in production

Thoresby primary school entrance is a narrow pathway, unless we use schoolyard separate from entrance

Crew base is same as audience base – primary school. You would have to pay school for any use of electricity to power things overnight.

Our TEN didn’t suggest a bar license. We would need to revisit this.

A hull 2017 rep should have authority to call stop in emergency too.

Routes of access during get in for school goers

Thoresby entrance

Bar and TEN licence

Week of 10th april circa deputy director in hull to work with guides and choir through site etc.