# Land of Green Ginger Away Day

19 July 2017 Katy’s House, Present: Katy, Lou, Maddie, Elizabeth, Gareth, Adam. Apologies: Chrissie

## Stunt

- Post Antony’s outrage, what happens next?

- Moment: w/c 28 August

  - Either at Freedom Festival or The Sesh

  - Options for Season Launch: crates behind photo op or something more overt?

  - Performers moving them through Fruit Market?

  - Can we roll out the same stunt a couple more times leading to Macnas?

  - A crate full of ginger biscuits at Feast, a free ticketed event at Queen’s Gardens as part of Freedom Festival. We haven’t put crates in city centre yet, so this could be a good selfie opportunity at Queen’s Gardens.

  - Cautious re: spending money because not sure how affective this stunt will be

  - What have we got left? Big crates already stenciled on, which is not necessarily a bad thing. Could be a good way of joining the dots. Add Acts I, II, III, which would get people thinking about where the next acts will be.

  - They found the book with a riddle inside a poem. Is there a game? Cut outs of letters, map of city where it’s already been. Or a chalk activity. This kind of activity would need a facilitator. This is a much better idea than a proper show.

  - If we have the GGF there, who would that be? Our two performers can’t do street theatre-style work

  - Final thinking: installation, clue of locations, riddle, old crate with stencils on. Best location: Band-stand side of Queen’s Gardens towards rose garden.

## Script

- Mini crate that grows to become Macnas crate = very slow burn

  - Mini crate in smallest window??

- W/C 21st August: more about voice collecting i.e. ‘did you contribute your voice?’

- W/C 28th August see above at Freedom Fest

- 6-10th September voice collecting

  - evenings at choirs

  - during day: working their way up Hessle Road in public areas to Pickering Park

- W/C 11 September:

  - GGF and RRD ship a crate full of voice vessels to Pickering Park and PR + leaflets the same week. ‘Hull’s super voice is coming to Pickering Park’

  - Major connection discovered in old RRD underground network, connecting to Pickering Park

  - 10ft x 10ft i.e. big enough to stand in.

- Thor dates:

  - Get in 19th September

  - Tech run 21st September?

  - Last day 30 September? (First day 22 September?)

  - 1st Oct: get out

- W/C 9th Oct Davy’s crate: peeping into scene of tiny people

  - GGF investigate pumping station because of flashing lights. Teaser images. They also notice different drain signs

  - The LOGG mark is the sign to move crate out to Derringham and once placing there the crate becomes animated

  - There’s been a society of tiny people, some whom live at bingo hall and most at the pumping station. LOGG has revealed this society to wider community. We don’t need to over-explain it.

- W/C 16th October Macas: Green Ginger Unleashed (working title)

  - Tiny crate could grow. Can’t open it. Full of furniture. Take back to GGF HQ. Grows some more.

  - Tiny footprint -> big footprint

  - Crate with date time and map

  - Will need to do lots of traditional marketing for this; meaning GGF need to know about this before.

  - Need another riddle.

  - Practically: how does nice story fit in with practical needs.

  - Resident notification needs to go out 4 weeks before (i.e. 16 Oct)

  - Use of shadow as a way of heralding giants…

- 20 Oct – 5 November = Davy’s live dates

  - New title ideas: Miniature Metropolis, Mini Metropolis, Tiny Town

  - 1 day per week not open

  - bookable slots and open times to general public

  - Beast of a week: 30th October = Davy live, BTO, school hols, Macnas rehearsals

## Actions

- Maddie

  - Think about immediate next steps for Longhill aftermath, and speak to Chris about it

  - Put together project plan for stunt

  - Update Joshua’s budget to include VIP guest and other closing event costs

  - Put together FOH spec for Davy’s event managers

  - Ask Davy re: their days here

- Chrissie

  - Nose Guardian blog and sponsors PR next week

  - Update Nose Pamphlet

  - Map: need one for Aswarm and also Macnas that’s generally designed for LOGG. For Aswarm, it’s to point out that they’ve been collecting voices all over the city. For Macnas, it’s to show the parade route.

- Katy

  - Send Mikey email today about being at Freedom Fest

- Gareth

  - Look up crate-like sheds