LGBT 50 – Duckie Summer Tea Party

Individual Roles & Responsibilities_version 2

| Name | Organisation | Event Role | Event Responsibilities |
| --- | --- | --- | --- |
| Chris Clay | Hull 2107 | Event Manager | - Overall management of event resources and personnel. - Authorised to call a show stop - Strategic decisions regarding delays or cancellation (in conjunction with the Event Producer) - Lead responsibility for Health & Safety. - Strategic liaison with Emergency Services, medical and security teams. - Write the Event Management Plan - Lead contact with production contractors |
| Cian Smyth | Hull 2017 | Event Producer | - Relationship & contract management with Duckie & Yorkshire Dance - Strategic decisions regarding delays or cancellation (in conjunction with the Event Manager) - Lead responsibility for creative content |
| Melissa McVeigh | Hull 2017 | Deputy Event Manager | - Lead contact with site and ancillary contractors - Deputise for the Event Manager if required |
| Haitham Ridha | Hull 2017 | Assistant Event Producer | - Volunteer lead - Deputise for the Event Producer as required - Liaison with Duckie |
| Rebecca Clark | Hull 2017 | Event Logger | - Maintain event log recording all notable occurrences, decisions and outcomes. - Minute ELT meetings |
| Alix Johnson | Hull 2017 | Communications lead | - Lead contact for all press and media - Implement crisis comms plan if necessary |
| Jenny Hutt | Hull 2017 | Production Liaison | - Liaison with Duckie |
| Claire Drury | Hull 2017 | Production Liaison | - Liaison with Yorkshire Dance |
| Elizabeth Bergeron | Hull 2017 | Production Liaison | - Liaison with Yorkshire Dance |
| Hannah Williams – Walton | Hull 2017 | Production Liaison | - Liaison with Duckie (After Party) |
| Chris Bilton | North East Medical | Medical Manager | - Management & coordination of medical resources - Advise the Event Manager on medical issues and contingency plans |
| Mark Norbury | Showsec | Security Manager | - Management & coordination of security personnel - Advise the Event Manager on security issues and contingency plans |
| Sarah Moor | Hull 2017 | Marketing Lead | - Responsible for all marketing and branding materials - Responsible for site and event dressing |
| Dicky Eton | Duckie | Producer | - Lead responsibility for all elements of the event produced by Duckie |
| Kirsty Redhead | Yorkshire Dance | Producer | - Producer for ‘Into the Light’ |