LOGG FORTNIGHTLY ACTIVITY UPDATE

|  | PUBLIC FACING EVENTS/MOMENTS | INTERNAL | PRESS | DIGITAL | OTHER |
| --- | --- | --- | --- | --- | --- |
| Monday 24 July |  | Katy off Volunteer chat re: Cardboard City |  |  |  |
| Tuesday 25 July |  |  |  |  |  |
| Wednesday 26 July | GNGG – nose flute lessons | Maddie off |  |  |  |
| Thursday 27 July | GNGG – get creative! | Gareth off Phone call with Noeline |  |  |  |
| Friday 28 July | GNGG – lunchtime concert |  |  |  |  |
| Saturday 29 July | GNGG – afternoon tea | Lou off |  |  |  |
| Sunday 30 July | GNGG – story time |  |  |  |  |
| Monday 31 July |  |  |  |  |  |
| Tuesday 1 August |  | Katy and Gareth back | Article in HDM about the GNGG being gifted back to city of Hull by being placed residence at Hull History Centre till the end of the year | Nose Guardian and Assistants are preparing for departure of GNGG |  |
| Wednesday 2 August | GNGG – nose flute lessons |  |  |  |  |
| Thursday 3 August | GNGG – get creative! | Budget catch up Weekly catch up |  |  |  |
| Friday 4 August | GNGG – lunchtime concert |  |  |  | Cardboard City filming begins |
| Saturday 5 August | GNGG – afternoon tea | Maddie back |  |  |  |
| Sunday 6 August | GNGG – story time |  |  |  |  |

Updates

Elizabeth is focusing on scheduling participants for filming in Cardboard City (PS Lynn Hubbard is the best!)

Elizabeth, Lou and Gareth are planning GNGG’s closing ceremony

Chrissie’s working on the final touches of the GNGG press release and is putting together a draft of the GNGG closing ceremony invite. She’s also sadly working on pulling apart the GGF via FB

Lou’s also turning her attention to recruiting participants for Macnas, as well as making sure Aswarm are happy with their final voice collection schedule

Gareth is liaising with Yorkshire Water to give them all the info they need for Cardboard City

Katy and Maddie are having a well-earned rest

Key Dates:

17 June: Gold Nose of Green Ginger shop opens at North Point

3 – 6 July: Project VEAR voice collection

12 – 16 July: Project VEAR voice collection

10th, 13-14 July: And Now: community activity in Longhill

15 July: And Now: The Longhill Burn

19 August: Gold Nose of Green Ginger closing procession at North Point and reception at the History Centre

6 – 10 September: Project VEAR voice collection

22 – 30 September: Project VEAR live at Pickering Park – currently being negotiated with artists

20 October – 5 November: Cardboard City live at Springhead Pumping Station

11 November: Macnas parade in Old Town