Larkin Exhibition
Wednesday 17th August 2016

Present: SW, HD, CS, JT, HWW,
Notes: SMHS

NOTES

Update

Cian Smyth has joined Hull 2017 as a producer on the Larkin Exhibition.

Guest Curator

No news on Lenny Henry

No direct link to Stephen Fry at the moment.

Martin Green doesn’t think we should approach Tracy Thorn – as we have been in contract with her already.

Martin also suggested approaching Andrew Motion - the group discussed this as a possibility but wanted to know the progress of the rest of the group first.

Martin also suggested Cerys Matthews

Reese Shearsmith still to be asked.

Cian is going to speak to Lavinia Greenlaw who is the poetry advisor for 1418 to see if she knows any celebrities that would be good to contact.

Action: Simon to get an update re progress from Graham.

BBC

Henri hasn’t spoken to Sue at BBC as Sue is on leave. Henri will follow up when she’s back.

Simon has met with the BBC and talked about a reciprocal in kind approach between the History Centres archive and BBC archive.

Action: Simon to get in touch with Pat Connor to discuss.

Action: James to see if there’s anything in the Hull 2017 contract with the BBC to see if there’s a way we may be able to use their archive for free.

Action: Simon to make a shortlist of interesting material on the BBC archive lists and find out costings for viewing and use.

Research

Research has begun. 										
Larkin the Librarian – Philip has covered

Action: Simon is going to review and ask a librarian to try and find relating material in the archive.  
Larkin the Poet – James has covered 
Larkin’s Family – Philip has covered 
Larkin & Jazz – It was suggested that we ask John White who is part of the Larkin Society.

Action: Simon to follow up.

Henri said it would be useful to have a list of key items that have not been exhibited before.

Action: Simon to ask James and Graham to look through the inventory and note the ones that have not be seen before or ones that sound unusual.

Wrap Around Programme
For Ref, collation of activities which have been staged in the past

Budget
Simon and Henri have reviewed the budget and development of both Plan A and Plan B budgets.

Other

Cian suggested making a list of interesting curators who have done experiential exhibitions before.

Action: Everyone to bring any suggestions they may have to the next meeting.

Cian suggested looking to see if there were any anniversary dates that fall next year – for poems etc.

Action: Group to research and feedback if any come up.

Cian suggested that if we can’t get a celebrity curator we could ask celebrities to record individual poems to show at the exhibition.

Action: Simon Wilson to discuss with James about Faber doing activity as part of the wrap round programme.

Next Meetings