Dream Think Speak

SHOW REPORT – ‘ONE DAY, MAYBE’

PERFORMANCE : 25							DATE : 22.09.17

SHOW 1 : 18:00		ATTN. 38

SHOW 2 : 18:32		ATTN. 40

SHOW 3 : 19:00		ATTN. 40

SHOW 4 : 20:15		ATTN. 38

SHOW 5 : 20:47		ATTN. 40

SHOW 6 : 21:17		ATTN. 40

NOTES

ONE :

- Two Kpads had to be re-revealed on the High Street.

- The performer projector switched to a dark blue screen, then black with a white box. It then went to the correct screen. This all happened before the mini-kabuki.

- The “Police GO” cue was not heard because there was radio traffic at the time. The cue was given again after three minutes when the 1st floor SM’s realised the performers had not reacted. From now on a confirmation will be given that the cue has been delivered.

TWO :

- One Kpad was stuck on the Hostage 4 page on the 3rd floor. The patron was checked out, re-enter their details and then re-revealed.

- As the first group of performers were running three minutes late the “Police GO” was delayed by a minute to alleviate pressure on the Jesa. The first Jesa men left

FOUR :

- The alignment of the performer projector had to be corrected during the change.

FIVE :

- One Kpad had to be re-revealed.

NOTES:

- The alignment of the main projector needed some attention this evening and will be fixed tomorrow.

- The door of Cell 10 has been repaired. A new handle was fitted at the end of the evening as the original came away several times. The door needs a little bit of repainting.

- Cell door 3 lock is broken and will be fixed tomorrow.

- The late cueing of the first “Police GO” meant the Jesa men left the cells as the second group was approaching. Mx Hirst has asked that they wait for a cue if this occurs again.

- There were some glitches with VR units tonight. Mr Foley will make contact with the VR technicians to trouble-shoot

- The second lift to the APCOA car park has been vandalised so is out of order. The engineer will be coming on Tuesday so it will be out of commission over the weekend. The car park attendant may have to open up the lower floor for parking as Saturday brings members of the public who are not our patrons.

Many Thanks

Jay Hirst

CSM