| Name of Individual / Organisation | Luca Silvestrini’s Protein |
| --- | --- |
| Name of Project | (In)Visible Dancing |

Please provide a breakdown of key activities /tasks for your project from start to finish. Please include your preparation and planning activity as well as start / end dates of your public activity (eg. public performance, exhibitions, festival).

| START DATE | END DATE | ACTIVITY / TASK | STATUS | NOTES |
| --- | --- | --- | --- | --- |
|  |  |  | COMPLETE / ON-TIME / BEHIND |  |
| November 2017 |  | Initial contact with Hull groups about new show | Completed |  |
| January 2017 | March 2017 | Preparation and initial R&D discussions within Protein |  |  |
| January 2017 |  | Contract Protein performers | Local ambassador and coordinator recruited. Musician fixer and musicians recruited. | Rate and rooms secured for company in Hull city centre – Ibis hotel |
| March 2017 |  | Planning meeting with Hull groups and performers. Call out for auditions | Call out for apprentice dancers happened from January 2017 onwards. Call out for local groups happened from January 2017 onwards. Performance site and schedule finalised. Meeting set up with Hull based and well known skateboarder Paul Regan to possibly ascertain his interest and involvement in the piece. | Volunteers need to be recruited. Event form needs to be recruited. Waiting to hear back as to whether security will be required for the Finale on Sat 1 July. Company dancers, apprentice dancers and musicians can now be contracted. |
| 21 April | 5 May | R&D and rehearsals at Warwick Arts Centre | R&D in Warwick not required | The project has changed to a special edition of the company’s renowned work (In)visible Dancing |
| “ | “ | Costume/props design and purchase | This will happen in now from June 2017 onwards |  |
| w/c 8 May |  | Audition local dancers and meet groups | Audition for apprentice dancers happening on Sunday 19 March. Recruitment for local groups ongoing. | Volunteer / general public and local groups ‘big dance’ style classes planned and led by local coordinator – devise used to generate interest for the show plus main Finale taught so people can take part. |
| 19 June | 24 June | Rehearsals in Hull with local performers |  |  |
| 27 June | 1 July | Daily performances of show on King Edward St (five shows including Finale) | Performance schedule now confirmed. |  |

Activity Examples: Planning Meeting, Auditions, Contracting, Rehearsal, Costume Design, Performances