## Sheet1
Caravan of Love
Draft Schedule for Sean McAllister_version 3
week beginning | days | activity | milestones & phases
2016-03-07 | 3 | Meet potential creative team members and partner organisations who are delivering the archiving project. Development meetings with Hull 2017 team.
2016-03-14 | 3 | R&D, creative development
2016-03-21 | 3 | R&D, creative development
2016-03-28 | 3 | R&D, creative development |  | CONTRACT CREATIVES
2016-04-04 | 2 | Creative & design development |  | H2017 roadshow
2016-04-11 | 2 | Creative & design development |  | H2017 roadshow
2016-04-18 | 2 | Creative & design development |  | H2017 roadshow
2016-04-25 | 2 | Creative & design development | INITIAL CONCEPT & DESIGN DELIVERY | H2017 roadshow
2016-05-02 |  |  | procurement | H2017 roadshow
2016-05-09 | 1 | Design meetings | procurement | H2017 roadshow
2016-05-16 |  |  | procurement | H2017 roadshow
2016-05-23 | 2 | Design meetings | procurement | H2017 roadshow
2016-05-30 |  |  | procurement
2016-06-06 | 1 | Design meetings | procurement
2016-06-13 |  |  | procurement
2016-06-20 | 2 | Design meetings
2016-06-27 | 1 |  | FINAL DESIGN DELIVERY | script & content development
2016-07-04 | 2 | script & content meetings |  | script & content development
2016-07-11 |  |  |  | script & content development
2016-07-18 | 2 | script & content meetings |  | script & content development
2016-07-25 |  |  |  | script & content development
2016-08-01 | 2 | script & content meetings |  | script & content development
2016-08-08 |  |  |  | script & content development
2016-08-15 | 2 | script & content meetings |  | script & content development
2016-08-22 |  |  |  | script & content development
2016-08-29 | 2 | script & content meetings |  | script & content development
2016-09-05 |  |  | Programme launch | script & content development
2016-09-12 | 2 | auditions & pre production meetings |  | volunteer cast auditions
2016-09-19 | 2 | auditions & pre production meetings |  | volunteer cast auditions
2016-09-26 | 2 | auditions & pre production meetings | Technical specs finalised | volunteer cast auditions
2016-10-03 | 2 | pre production meetings
2016-10-10
2016-10-17 | 2 | pre production meetings
2016-10-24
2016-10-31 | 2 | pre production meetings
2016-11-07
2016-11-14 | 2 | pre production meetings
2016-11-21 | 2 | professional cast rehearsals | Rehearsals begin
2016-11-28 | 2 | professional cast rehearsals
2016-12-05 | 2 | full company rehearsals (including volunteer cast)
2016-12-12 | 2 | full company rehearsals (including volunteer cast)
2016-12-19 | 3 | full company rehearsals (including volunteer cast)
2016-12-26 | 3 | full company rehearsals (including volunteer cast)
2017-01-02 | 5 | full company rehearsals (including volunteer cast) | onsite build | onsite rehearsals
2017-01-09 | 6 | tech rehearsals & perfs
total days: | 76