TURNER PRIZE MARCOMMS MEETING

Date:		Tuesday 18 April, 3.00PM-4.00PM

Location: 	Project Room 2, Lowgate

Attendees: 	Sarah Black, Lily, Chris Marr, George, Ben McKnight, Anna Marshall, Sarah Moor and Chloe Patrickson

_______________________________________________________________________

MINUTES

| NO. | MINUTES | ACTION |
| --- | --- | --- |
|  | Minutes and matters arising from previous meeting: - Recap - Circulate photos of the jury – need to be obtained - Laura - print quotes have been requested - Chris, Laura and Sarah – draft marketing plan - Long list received by Sara – 12 artists |  |
|  | Important points from meeting with Tate Press - Tate – agreed PR will be signed off next week. - Ferens should be included in note to editors and have a section in the Press Pack - Content should be at Tate for 28th. - Tate agreed to do rights claims so images can be used. - Tate doing the invite list – goes out a week before opening. - Briefing for Martin by next Friday - Press visit – Tate have their own photographers who will visit 21 - 22 Sept 2017 - Consider using upstairs of the Ferens for press to sit - If BBC Breakfast do a feature they will be setting up before 6am on Monday. - Wider team – also need to be considered / cared for separate to press. - Press preview at 10.30am - 16 Tate patrons will be attending in the afternoon. - Preview will be that evening. Action: - Anna to gather info for invite list to send to Ben. - Ben to forward this on to Daisy. - Ben to talk to Jane at B&Q about creating briefing for Martin. - Have the jury ever been to Hull? - Ferens to sign a non-disclosure agreement. Marketing - Logos – Phil to provide full insight. - Tate to be used for Turner Prize word mark. - No Turner Prize logo but they are keen for us to use their font in marketing material (as above) - Tate have offered to send templates and examples of past material to use for reference. Not limited to these templates. - Meeting on Thurs 27.04.17 with Tate and BBC will help identify what BBC need. - Ferens – discussion about its placement on marketing as a host brand should happen between Tate, Ferens and Hull 2017 - Artist’s films - Cross promotion with Tate’s social channels. - All films should be signed off and include subtitles. Sodium mentioned as potential filmmakers. Action: - Sara and Phil to decide on filmmakers for artist videos. - Sara and Chris to create brief for filmmakers promptly. - Films to be ready for at least when exhibition is open. - Important to ensure shots of artists in Hull are featured in the videos. - Films should be signed off by Tate. - One member of Hull2017 should chaperon filmmakers when interacting with the artists. Events - SB Chase documents for awards ceremony. - Maria to take the stand first for opening talk – this then followed by presenter. - Presenter for 2017 – should have strong Hull or Yorkshire connection. Needs to be a name. - B&Q – may have info on who had too much relevance to present. Action: - All to brainstorm a presenter – consider Musicians, Writers, Poets - Ideas: Cosey Fanni Tutti, Genesis P-Orridge, Roland Gift, The House Martins - Paul Heaton, Lem (poetry), Melvyn Bragg, George Alagiah, Paul Smith – Maximo Park, Gareth Pugh, Vic Reeves, Reece Shearsmith - Adelphi’s history – bands connected - Consult the galleries who might have people in mind? | AM BM BM SB/PB SB/CM ALL |
| 3. | Catalogue - Sara, Phil, Sarah – next Tuesday going to Kingston Press to see if they can print the catalogue. - Last year’s catalogue paper was wrong – too glossy, was supposed to be newsprint material. Action: - Need to work out: - Quantities, - Purpose - Selling Price - Who/what is it for? | ALL |
| 4. | Sponsorship & Stakeholders - Opportunities to seek sponsorship for. - Too late for sponsorship for awards night. - Sponsorship for catalogue, events, partner events. - Ask Malcom for numbers of Ferens opening and visitor data for the gallery - Learning and Engagement plan - How to service stakeholders – in the 15 weeks identify key days - Tuesday mornings (9am-10am) for target groups? - Wednesday nights for corporate events? - X amount of evenings need to be agreed through the period. - Also need to reach people who would not normally come to Ferens / the uninitiated – special event? And through our marketing have a tool that is measurable. Action: - Decide on key days for target groups and corporate events. - Decide on X amount of evenings lent to corporate events throughout the 15 weeks. - Block out first week or two so no events are booked in this time. - Speak to Partnerships to see what they usually do - Create a marketing tool that is measurable to monitor those who would not usually come to Ferens. | AM SB/AM/BM CM/SM |
| 5. | Marketing Plan - Main objectives – Sara and Phil to fill in the gaps - End of April – key messages from audience development team. (LEARNING) Meeting to discuss is next week (26th) - Ben add to PR section. - Booking of poster sites - quiet period chance to get assets together. - Tate might create four posters not just one. - Posters should have a call to action. Eg. Discuss – words that fit our objectives. Then one picked to be put in community zones. We could have 4 posters, with 4 different words used on each to target different groups/audiences. - This will create threads eg. One word can be used to place in community zones to draw communities in. - Four words – artist’s talks could be a thread; events follow from a separate thread. Makes it accessible and feel like a direct invite. - Artist talks will be ticketed but affordable. - Audiences will purchase tickets through Hull 2017 Action: - Main objectives – Sara to fill in the gaps - Discuss PR in meeting next week - Sara to go through Marketing plan with Phil - Comment about age in plan is not relevant anymore – needs to be changed as it is the most recent time someone over 50 may be featured (Dependent on chosen artists) | SB SM |
|  | Next Meeting: Monday 8 May – Sara to choose a time closer to the date. |  |