V2.0-HULL CITY OF CULTURE – PRODUCTION SCHEDULE

| Weds 21st Dec | 8am – 6pm | Whitefriar Gate | Production - Internal clean all shop interiors |
| --- | --- | --- | --- |
| Thurs 22nd Dec | Midday – 6pm | Whitefriar Gate | Production - Install Projection film to windows in shop units 9, 16 & 17 |
| Fri 23rd Dec | Midday – 10pm | Whitefriar Gate | Production/Creative & Video – Projection test to window cubes in unit 8 |
| Sat 24th Dec | XMAS EVE | Holidays |  |
| Sun 25th Dec | XMAS DAY | Holidays |  |
| Mon 26th Dec | BOXING DAY | Holidays |  |
| Tues 27th Dec | 8am – 11am | The Deep | Steelworkers build PA towers |
|  | 9am - Midday | The Deep | Lighting deliver and install |
|  | 10am – 2pm | Queen Victoria Square | Video install projectors and control |
|  | 10am – 2pm | The Deep | Video install projectors and control |
|  | 11am – 8pm | Queen Victoria Square | Graphics apply window vinyls to City Hall, Ferens & Maritime Museum |
|  | 11am – 8pm | Whitefriar Gate | Graphics apply window vinyls to shop units |
|  | Midday – 4pm | The Underpass | Video install projectors and control |
|  | Midday – 4pm | Scale Lane Staith | Video install projectors and control |
|  | Midday – 6pm | Queen Victoria Square | Lighting deliver and install rooftop fixtures and control |
|  | Midday – 7pm | The Underpass | Lighting deliver and install fixtures and control |
|  | Midday – 8pm | The Underpass | Production install screens |

| Tues 27th Dec | 1pm – 4pm | Queen Victoria Square | Audio install PA |
| --- | --- | --- | --- |
| (continued) | 2:30pm – 6pm | Whitefriar Gate | Video install projection into shop units |
|  | 4pm – 8pm | ALL SITES | Video carry out system checks and tests |
|  | 5pm – 7pm | Queen Victoria Square | Lighting deliver and install fixtures and control to Monument area |
| Weds 28th Dec | 8am – 1pm | Zebedees Yard | Lighting deliver and install fixtures and control |
|  | 8am – 3pm | Queen Victoria Square | Graphics complete window vinyls to City Hall, Ferens & Maritime Museum |
|  | 8am – 6pm | The Underpass | Audio install PA |
|  | 8am – 6pm | The Deep | Audio install PA |
|  | 8am – 6pm | Whitefriar Gate | Audio install PA |
|  | 8am – 6pm | Zebedees Yard | Audio install PA |
|  | 8am – 6pm | Scale Lane Staith | Audio install PA |
|  | Midday – 6pm | Whitefriar Gate | Audio install window speakers into shop units 16,17 & 20 |
|  | 2pm – 7pm | The Underpass | Lighting deliver and install fixtures and control |
|  | 4pm – 4am | ALL SITES | Video – initial line up all projectors |
|  | 4pm – 10pm | The Underpass | Lighting – programme intelligent fixtures |
|  | 5:30pm – 7pm | Whitefriar Gate | Lighting deliver and install fixtures and control in shop units |
| Thurs 29th Dec | 09:00 |  | ALL ARTISTES ON SITE |
|  | 10am – Midday | ALL SITES | All Departments - System checks and fine tuning |
|  | Midday – 4pm | Zebedees Yard | Audio – Sound check |
|  | 4pm – 7pm | Whitefriar Gate | Audio & Video – System checks |
|  | 4pm - Midnight | Queen Victoria Square | Lighting – programme intelligent fixtures |
|  | 4pm - Midnight | Queen Victoria Square | Audio & Video – System checks |
|  | 4pm - Midnight | Whitefriar Gate | Audio & Video – System checks |
|  | 4pm - Midnight | The Deep | Audio & Video – System checks |
|  | 4pm - Midnight | The Underpass | Audio & Video – System checks |
|  | 4pm - Midnight | Scale Lane Staith | Audio & Video – System checks |

HULL CITY OF CULTURE – PRODUCTION SCHEDULE

| Fri 30th Dec | Midday – 4pm | ALL SITES | Production & Event Management – Noise level checks for Hull CC approval |
| --- | --- | --- | --- |
|  | Midday – 9pm | Zebedees Yard | Lighting – programme intelligent fixtures |
|  | Midday – 10pm | Queen Victoria Square | Audio & Video – System checks |
|  | Midday – 10pm | The Underpass | Audio & Video – System checks |
|  | Midday – 10pm | Scale Lane Staith | Audio & Video – System checks |
|  | Midday – 10pm | The Deep | Audio & Video – System checks |
|  | 9pm – 10pm | Zebedees Yard | Audio – Sound check |
|  | 9pm – 11pm | The Deep | Lighting – programme intelligent fixtures |
|  | 11pm – Midnight | ALL SITES | DRESS REHEARSALS |
| Sat 31st Dec | CONTINGENCY |  |  |
| Sun 1st Jan | 2pm | ALL SITES | Technical and Production crews – Show Standby |
| Mon 2nd Jan | 3pm | ALL SITES | Technical and Production crews – Show Standby |
| Tues 3rd Jan | 3pm | ALL SITES | Technical and Production crews – Show Standby |
| Weds 4th Jan | 3pm | ALL SITES | Technical and Production crews – Show Standby |
| Thurs 5th Jan | 3pm | ALL SITES | Technical and Production crews – Show Standby |

HULL CITY OF CULTURE – PRODUCTION SCHEDULE

| Fri 6th Jan | 3pm | ALL SITES | Technical and Production crews – Show Standby |
| --- | --- | --- | --- |
| Sat 7th Jan | 3pm | ALL SITES | Technical and Production crews – Show Standby |
| Sun 8th Jan | ALL DAY | ALL SITES | DISMANTLE |
| Mon 9th Jan | ALL DAY | ALL SITES | DISMANTLE |