NNT – 13/6/16

Henri, Lou, Ian, James M, Martin

| Agenda | Action | who | Deadline |
| --- | --- | --- | --- |
| Admin | Job description to be completed | Henri to send to Lou | Yes |
| Partnership Agreements | To include – free venue, local team requirements, use of hcoc logo – bespoke for schools & social venues | Henri | Henri meeting Will this week |
| Contacts | Venue contact spreadsheet to be lifted from ACE bid | Martin | June |
| Branding | To include – Brochure, Name, Description, partner venues, highlights | All | ASAP – 11th July content deadline |
| Inform Venues & set up area meetings | Try to sign up venues by 4th July so they can be named in brochure. Individual meetings rather than in clusters | Ian & Lou – schools James & Lou community | 4th July |
| Monthly partner meetings dates | Meeting 1 – Louise to book Rollitz meeting room, Wed 14th July 4-6pm | Lou | ASAP |
| Consultant Brief | To include meeting dates & day either side – 20 days available in budget | Lou | Yes |
| Inflatable Screen | Jane Earnshaw possibly has inflatable screen for YF project | Martin | June |
| Circus | Joint projects and programme from circus budget | Lou | Ongoing Lou to attend meetings |