CCP			14 & 15 June 2016

Stage One 		Programme Sense Check & Cut			CD, JM, HD		

Opening Totals		
Hull 2017 & BIG		All for Consideration		 		75
			Total Value of All Projects			£816,065

For Ref			BIG AFA Projects				13
									£113,092

Sense Checks Done:
Geography
Calendar
Choirs – Clare Drury
Dance – RD
Cultural Organisations
Hull Carnival Arts
Duplication & Concern around Delivery 
Disability
Artlink
APUS
Bransholme
Uni
Heritage Potential Projects Flagged

Sense Checks Still to Do:
Film -  go through all projects (long & short list) with Anna
Murals – Sam 
MOCC  - Sam 
Visual Arts – Public Art - Exhibitions - Sam

BIG – CCP – flagged non-priority projects to encourage BIG to cut.
BIG

Hull 2017 & BIG		Added						4
Hull 2017 & BIG 	Removed 					5

Hull 2017 & BIG		All for Consideration		 		74
			Total Value of All Projects			£788,999

For Ref			BIG - AFA Projects				13 - £113,092
			BIG – YES Projects				23 - £199,473
 			BIG – MAYBE Projects 				14 - £156,588

Rationalise Exercise 
Cut RM Education –  move to Digital programme
Reduce budgets – Goodwin; Amplfy; MadPride; Reading Rooms; Assemble Fest
Combined projects – Handmade & Carnival Arts; Gypsy Moths, Refugee Week; 
Removed 3 x NHS; 
De-dupe – Greatfield; Mela;

Revised Total								67
									£679,591

Other Projects rated low priority
Exhibition Boards at St John and at Trinity
HANA Cultural Festival or Rooted in Hull  
Not Forgotten Town – move to Film
Re Made in Hull 
Inflated Hull
Beer Mats – make this a Marketing  Initiative
Open Doors

Revised Total								55
									£561,845

Next in Line
Noah – because it’s a big one -  or Handmade with Carnival Arts on Orchard Park doesn’t materialise.

Couple of smaller ones don’t pass ‘deverability test’ – eg Bantu, Rev Lansford, 

Which would get us to £300k total.

Actions
1	Complete Sense Checks

2	Curatorial Actions – notes on spreadsheet					HD/JM

3	Interventions – RM Education; Skelton Hooper; Pride; Hullzapoppin; 		HD

4	BIG Feedback on project selection

5	BIG Feedback on support package

6	HLF – send Fran short list of ‘heritage’ projects 					HD

7	CCP Documentation Review							CD/SMHS

8	Pull of all Tours & Trails projects from the 650 for Tina / VHEY / City Arts info.	SMHS

9	CCP Comms Timeline								CD

10	MAP of projects to share with BIG						JM

11	Calendar – flow in Funder columns; remove to bottom the ‘cut projects’		SMHS

12	Rationalise with BIG – ie communicate with BIG which projects from their YES and MAYBE list are high priority or low priority for H2017.