## Evaluation Days
Kate Fox Project (funded by the University)
DAYS BASED ON… | No.
Planning | 2
Recruitment & Workshops | 0
Performances - rehearsals & actual | 0
Writing / Commission | 0
Evaluation | 6
Contingency | 0
TOTAL DAYS | 8

## PROJECT BUDGET
Kate Fox Project
BUDGET | BASED ON | BASED ON |  | NOTES
| no.of days | £per day
Engagement Project Days | 22 | 300 | 6600 | 1. Budget totals £17.5k if reduce number of days to 18 Engagement Days, 18 PM days, 8 Evaluation days
2. Req £2.5k from Evaluation to add to budget to ensure success, or reduce Evalution days
Expenses (travel) | 22 | 50 | 1100
Expenses (accommodation) | 15 | 75 | 1125
Marketing / Comms |  |  | 2000
Production / Workshop Costs | 6 | 250 | 1500 | 9600
Project Management days / Associate spoken word artists | 22 | 150 | 3300
Evalution Focused Days | 10 | 300 | 3000
Access |  |  | 500
Photography / Filming |  |  | 500
CSL days related activity |  |  | n/a
Other |  |  | 500
TOTAL DAYS |  |  | 20125

## Engagement Days
Kate Fox Project (NOT funded by the University)
BASED ON DAYS… | No.
Planning | 4
Recruitment & Workshops | 8
Performances - rehearsals & actual | 5
Writing / Commission | 5
Evaluation | 0
Contingency | 0
TOTAL DAYS | 22

## Non-funded PROJECT BUDGET
Kate Fox Project (NOT funded by the University)
BUDGET | BASED ON | BASED ON
| no.of days | £per day
Total project days | 22 | 150 | 3300
Expenses (travel) | 5 | 60 | 300
Expenses (accommodation) | 11 | 50 | 550
Marketing |  |  | 1700
Production Costs | 4 | 250 | 1000
Project Management days | 12 | 150 | 1800
Documentation days | 4 | 250 | 1000
Miscellaneous |  |  | 250
CSL days related activity |  |  | n/a
Contingency (approx 10%) |  |  | 1000
TOTAL DAYS |  |  | 10900