Hull 2017 
Project Summary 

Hull 2017 
The Ballad of Big Lil 
by Maxine Peake
Music & Lyrics 	Adrian McNally 
Director		Sarah Frankcom

Summary

Inspired by the women who campaigned for better and safer working conditions on Britain’s trawler ships, the Ballad of Big Lil is a site specific project with a strong mix of music, movement and text. The production explores Hull’s heritage as a port city, and celebrates the hard and dangerous life of trawlerman ruled by a feudal system of ship owners in a voracious capitalist system. At the heart of the story is Lillian Bilocca, a women who dared to speak out and take action to improve conditions for men at sea. With a community chorus, live music and an open bar, the evening will be a visceral, joyous evening of song, music & theatre.

The following details describe the production parameters which reflect the project budget

Venue		TBC, Hull

A civic space with the faded grandeur of the past. 
Current options being considered include the Guildhall, Hull

Music 	Original songs and soundscore written by Adrian McNally. 
Existing and /or traditional songs to be arranged by Adrian McNally. 
To be performed live by the Unthanks. 
At present one song, the Ballad of Big Lil, to include lyrics by Maxine Peake, with original music by Adrian McNally and the Unthanks.

Cast & Band  	Cast of 8

Band of 6
	Max cast & band no more than 14
 	Company wage; actor/musician contract

Digital 	Explore live broadcast & filming opportunities to extend reach for  audiences.

Project Timeline

June 16 	Brief delivered to Hull 2017 by Maxine Peake

July 16 	Commission Writer, 
Secure director, confirm details of RET involvement

August 16 	Site scouting & site to be identified.

Sept ’16	Secure composer, designer, choreographer, sound & lighting designers, production manager

22 Sept 16	Hull 2017 UK City of Culture Launch

Sept/Oct 16	Recce visit for Guildhall – SF, AS, PR as well as MP if schedule allows

10 -14 Oct 	R&D in Manchester. 
To be arranged by Michelle Hickman from Manchester
Royal Exchange with actors from Streetcar. 
In attendance: 	Maxine Peake
			Sarah Frankcom
 			Amanda Stoodley
			Peter Rice

Nov/Dec 16 	First full draft of the script delivered

Image & copy generated

Confirm site – venue contracted

Feb 17 	Final script delivered

Sign off season brochure page

April 17 	Prelim designs & outline costings

Casting of professional company 

Stage management team confirmed

July 17		Recruitment & Casting of Community Cast

 		Final designs & detailed costings

Sept 17 	Pre-Production – build & prep venue

Oct 17 		Rehearse 

		Install at venue

Nov 17 	Tech, open & perform

Nov 17 	Close

Creative Team
Writer					Maxine Peake 
Music & Lyrics & MD 			Adrian McNally 
Director 				Sarah Frankcom 
Set & Costume Designer		Amanda Stoodley  
Lighting Designer			Chris Davey 
Sound Designer			Peter Rice 
Casting Director			TBC – RET?

Dramaturg 				Steven Greenhorn TBC 
Associate Director (Comm Cast)	to be Hull based

Consultant				Rupert Creed TBC

Production Team 
Production Manager
Company Manager
DSM
ASM
Sound Op 
LX Op
Dresser
Technician 
Production Sound

Production LX
Costume Supervisor

FOH Manager
Box Office Manager & Assistant

Stewards 
Security
Access Performance Interpreter

Bar staff 				Licensee & Operator TBC

Production Schedule 
All dates to be discussed and confirmed with MP/SF and AMcN/Unthanks

Rehearsals Week 1			w/c 2 Oct 2107		Reh in Manchester 
 				 			 		(Pro Cast)
 									Reh in Hull Comm Cast

Rehearsals Week 2 			w/c 9 Oct			Reh in Manchester

(Pro Cast)
 									Reh in Hull Comm Cast

Rehearsals Week 3			w/c 16 Oct 			Reh in Hull; full band 
Rehearsals Week 4			w/c 23 Oct			Reh in Hull; full band
Start venue set up

Production / Tech Week		w/c 30 Oct			In Venue; full band	
First Preview				Fri 3 Nov
Second Preview			Sat 4 Nov 	
Performance Week 1			w/c 6 Nov			In venue; full band

Press Night				Tues 7 Nov or Wed 8 Nov

Perf Week 2				w/c 13 Nov			In venue; full band
Final Performances			Sat 17 Nov 2017

Proposal for possible Community  Ensemble process:
Community Cast			To be 16 + years old 
 					Overall Group of 30 – for min 20 per perf
 					Rehearsals In Hull
					3 sessions a week, evenings & weekend
					6 sessions during Tech Week, daytime, evening & Sat
 					6 performances per week during run

Min 6 performances per week inc one matinee.

Updated: HD/LA Sept 2016