NNT – 6/6/16

Henri, Lou, Ian, James M, Martin

| Agenda | Action | who | Deadline |
| --- | --- | --- | --- |
| Admin | Job description to be completed | Henri to send to Lou | SLT 14th June |
| Partnership Agreements | To include – free venue, local team requirements, use of hcoc logo – bespoke for schools & social venues | Henri | June |
| Contacts | Venue contact spreadsheet to be lifted from ACE bid | Martin | June |
| Branding | Branding session to be set up with Henri, Lou, Martin A, Ian, James M, James T, Billy, Tara | Martin | ASAP – 11th July content deadline |
| Inform Venues & set up area meetings | East Meeting - Freedom centre, Sentimu, Kingswood & Winifred Holtby West Meeting 1 – Boulevard, Sirius, Hymers & St Georges West Meeting 2 – St Georges, Gemmell & Walton Street | Ian & Lou | June |
| Monthly partner meetings dates | Meeting 1 – Partnership agreements, intro to consultant & team, marcomms, feb programme Meeting 2 – Programming & venue tech spec | Ian & Lou | June |
| Consultant Brief | To include meeting dates & day either side – 20 days available in budget | Lou | June |