| AIMS & OBJECTIVES | INDICATORS | BASELINE | TARGET | METHODS | TIMING | RESOURCES | RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Invite every Hull resident to the live event | Number of invites delivered | 0 | Number of occupied households, Hull: 113,900 All households, Hull: 119,000 | [Ask Laura] | TBC | TBC | Niccy Halifax |
|  | % of residents who recall receiving an invite | 0 | 90% | Audience/visitor survey | Recruit fieldwork agency now Sign off survey with fieldwork agency by 23/12/2016 Contact details collection 01/01/2017 – 07/01/2017 CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency | Elinor Unwin & Regenris to create survey Professional Fieldwork Agencyto undertake fieldwork and provide data tables Regeneris to analyse and produce report |
| Enable better understanding of the last 70 years of Hull’s history and heritage through the creation and delivery of a spectacular opening event | Number of delivery team members | - Producer: 0 - Artists: 0 - Production Staff: 0 - Other staff: 0 - Volunteers: 0 | - Producer: - Artists: - Production Staff: - Other staff: - Volunteers: | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax Ground Control |
|  | Equal opportunities data on delivery team | - Post code: 0 - Gender: 0 - Age: 0 - Sexual orientation: 0 - Ethnicity: 0 - Disability: 0 - Conditions: 0 | - Post code: - Gender: - Age: - Sexual orientation: - Ethnicity: - Disability: - Conditions: | Equal Opps Form & Project Monitoring Sheet | At contract (or ASAP) | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of partners | - Artistic: 0 - Heritage: 0 - Funder: 0 - Public sector: 0 - Voluntary/Charity Sector: 0 - Education: 0 - Other: 0 | - Artistic: - Heritage: - Funder: - Public sector: - Voluntary/Charity Sector: - Education: - Other: | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of creative development sessions | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of rehearsals of live performance | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of sites used in project | - Total: 0 - Heritage sites: 0 | - Total: - Heritage sites: | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of known Hull histories presented by the project | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of commissions of new artwork and/or interpretation | - | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of art forms involved within project | - | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Arts Council England Quality Metrics | Self, Peer and Public - Concept - Presentation - Distinctiveness - Challenge - Captivation - Enthusiasm - Local impact - Relevance - Rigour Self and Peer only - Originality - Risk - Excellence | Self, Peer and Public - Concept - Presentation - Distinctiveness - Challenge - Captivation - Enthusiasm - Local impact - Relevance - Rigour Self and Peer only - Originality - Risk - Excellence | Audience/visitor survey Creative team survey & depth interviews Peer survey & depth interviews | CATI surveys from 02/01/2017 – 20/01/2017 Pre-event 16/12/2016 Post-event 08/01/2017 Post-event attendance | £6,000 for Fieldwork Agency Staff time Evaluator time Expenses for Peer(s) £500 | Elinor Unwin Fieldwork Agency Regeneris |
|  | HLF Quality Metrics | TBC | TBC | Audience/visitor survey Creative team survey & depth interviews Peer survey & depth interviews Heritage partner survey & depth interviews | CATI surveys from 02/01/2017 – 20/01/2017 Pre-event 16/12/2016 Post-event 08/01/2017 Pre-event 16/12/2016 Post-event attendance Pre-event 16/12/2016 Post-event attendance | £6,000 for Fieldwork Agency Staff time Evaluator time Expenses for Peer(s) £500 | Elinor Unwin Fieldwork Agency Regeneris |
|  | Awareness of/knowledge of the histories presented by the project | Citywide Residents Survey 2016 comparable categories: - Hull Blitz - Hull in the Civil War - Fishing and whaling industry - Trade through the ages - Ship building - Famous sons/daughters of Hull | - WW2 & Rebuilding - Fishing - The Docks - Migration - Hull game changers? - Work and industry - Music and culture - Sport - Art & Literature - Architecture in Hull - People of Hull - Visitors to Hull | Audience/visitor survey & vox pops Core Team/Artist survey & depth interviews | CATI surveys from 02/01/2017 – 20/01/2017 Vox Pops 01/01/2017 – 07/01/2017 Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | £6,000 for Fieldwork Agency Staff time Evaluator time £x for filming and editing of vox pops | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | New and surprising histories people have discovered in regard to Hull’s history and heritage | 0 | ? | Audience/visitor survey & vox pops Core Team/Artist survey & depth interviews | CATI surveys from 02/01/2017 – 20/01/2017 Vox Pops 01/01/2017 – 07/01/2017 core Team/Artist Survey: Core Team/Artist Depth interviews: ? | £6,000 for Fieldwork Agency Staff time Evaluator time £x for filming and editing of vox pops | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | How has the project made people feel about Hull’s history and heritage? | N/A | ? | Audience/visitor survey & vox pops Core Team/Artist survey & depth interviews | CATI surveys from 02/01/2017 – 20/01/2017 Vox Pops 01/01/2017 – 07/01/2017 Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | £6,000 for Fieldwork Agency Staff time Evaluator time £x for filming and editing of vox pops | Elinor Unwin Fieldwork Agency Regeneris Videographer |
| Generate National Media coverage & interest | Number of press releases | ? | ? | Project Monitoring Sheet | ? | Staff Time | Niccy Halifax Alix Johnson |
|  | Number of TV appearances | ? | ? | Project Monitoring Sheet | ? | Staff Time | Niccy Halifax Alix Johnson |
|  | Number of Radio appearances | ? | ? | Project Monitoring Sheet | ? | Staff Time | Niccy Halifax Alix Johnson |
|  | Number of editorial pieces by Hull 2017 on website | ? | ? | Project Monitoring Sheet | ? | Staff Time | Niccy Halifax David Watson |
|  | Number of social media posts on Hull 2017 platforms | ? | ? | Project Monitoring Sheet | ? | Staff Time | Niccy Halifax David Watson |
|  | Editorial coverage received (volume & sentiment) | ? | ? | Gorkana Media Monitoring / Other TBC | From: ? To: 20/01/2017 | PR Company | Alix Johnson |
|  | Number of impressions across digital platforms | ? | ? | Google Analytics & Falcon / Other TBC | From: ? To: 20/01/2017 | PR Company | David Watson |
|  | Number of engagements across digital platforms | ? | ? | Google Analytics & Falcon | From: ? To: 20/01/2017 | PR Company | David Watson |
|  | How audiences found out about the project | Baseline Research Project 2016 | Media Campaign Plan targets | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
| Uncover unexpected stories relating to the last 70 years of Hull’s history | What was discovered? | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | How was it found? | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | What difference did it make to people? | 0 | - Artists: - Partners: - Participants: - Audiences: | Audience/visitor survey & vox pops Core Team/Artist survey & depth interviews | CATI surveys from 02/01/2017 – 20/01/2017 Vox Pops 01/01/2017 – 07/01/2017 Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | £6,000 for Fieldwork Agency Staff time Evaluator time £x for filming and editing of vox pops | Elinor Unwin Fieldwork Agency Regeneris Videographer |
| Increase total audiences for Hull’s cultural offer by 25% | Footfall at key sites (need to measure throughout December and January to ensure that a comparison can be made to the active days) | 01/12/2016 - 31/12/2016: - Queen Victoria Square - Beverley Gate - Whitefriargate - Zebedee’s Yard - Land of Green Ginger - Silver Street - Scale Lane - Scale Lane Straigth - Underpass - Stage @TheDock - The Wash to Humber Street 01/01/2017 – 31/01/2017: - Queen Victoria Square - Beverley Gate - Whitefriargate - Zebedee’s Yard - Land of Green Ginger - Silver Street - Scale Lane - Scale Lane Straigth - Underpass - Stage @TheDock - The Wash to Humber Street | X% higher average footfall on live dates vs. other dates across all sites | Infra-red Footfall Counters | 01/07/2017 – 07/01/2017 | £x | Niccy Halifax ? |
|  | People are inspired to take part in/attend other projects as a result of the project | Baseline Research Project 2016 |  | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
| Increase engagement and participation in culture amongst Hull residents (HU1-HU9) by 7% | % of audiences from HU1-HU9 | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | % who are lapsed/first time attenders and participants | Baseline Research Project 2016 & Citywide Residents Survey 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | Mapping of attenders across Hull Local Authority Area | Baseline Research Project 2016 | ? | Audience/visitor Survey | 23/01/2017 – 27/01/201 | Staff time Business Intelligence Team @ HCC | Elinor Unwin Richard Morfitt |
| Increase the diversity of audiences for Hull’s cultural offer | Equal opportunities data on attenders - Gender - Age - Group size and age of group members - Employment status - Ethnicity - Disability - Conditions | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | Number of access provisions created/ provided for participants and attenders | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Satisfaction levels with access provisions created/provided for participants and attenders | 0 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | % of participants /attenders who state that would have taken part/attended if the access provisions made were not provided | 0 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
| Increase positive attitudes towards Hull as a place to live, work, study and visit by 10% | Motivation for taking part in/attending the project | Baseline Research Project 2016 | ? | Audience/Visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | % of people who state that as a result of the project their attitudes towards Hull have changed for the better | 0 |  | Audience/visitor survey & vox pops Core Team/Artist survey & depth interviews | CATI surveys from 02/01/2017 – 20/01/2017 Vox Pops 01/01/2017 – 07/01/2017 Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | £6,000 for Fieldwork Agency Staff time Evaluator time £x for filming and editing of vox pops | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | % of attenders who strongly agree or agree with a range of value statements | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | Interest amongst non-Hull base delivery team members to deliver/work on future cultural projects in Hull | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
| 75% of Hull residents being proud to live in Hull | % of residents who agree that the project has made them proud to live in Hull | Citywide Residents Survey 2015 and 2016 | 75% of Hull respondents | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
| 75% of Hull residents agreeing they would speak positively about Hull to others | Likelihood of recommending the project/ones like it Hull it to others | Citywide Residents Survey 2015 and 2016 | 75% of Hull respondents | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
| Provide training and development opportunities to 2,800 residents |  |  |  |  |  |  |  |
|  | Number of training sessions for Hull 2017 volunteers | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of volunteers attending training sessions | 0 | ? | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
| By March 2018, 75% of local cultural organisations will agree the city’s cultural infrastructure has been developed as a result of capacity building and collaborative work undertaken with Hull 2017 and partners | Skills and know how development of artist/creative practitioners and delivery partners | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | Confidence level of artist/creative practitioners and delivery partners | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | Ambition of artist/creative practitioners and delivery partners | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | Level of profile of artist/creative practitioners and delivery partners | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | Perceptions of Hull amongst artists/creative practitioners and delivery partners | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | Understanding of Hull’s history and heritage amongst artists/creative practitioners and delivery partners | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
| By the end of 2017, Hull 2017 will deliver economic impacts of at least £60m | Number of jobs created by project |  |  | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of freelancers employed |  |  | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Number of days worked by delivery team |  |  | Project Monitoring Sheet | Ongoing project monitoring | Staff time | Elinor Unwin Niccy Halifax |
|  | Main purpose for visiting Hull (non HU1-HU9) | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | % of first time visitors | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | Visitor satisfaction levels | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | Length of stay | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | Visitor spend on accommodation if overnight visitor | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
|  | Visitor spend on other items | Baseline Research Project 2016 | ? | Audience/visitor Survey | CATI surveys from 02/01/2017 – 20/01/2017 | £6,000 for Fieldwork Agency Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris |
| By the end of 2017, Hull 2017 and partners will have contributed to sustainable legacy projects that build on the success of Hull 2017 UK CoC initiatives | How will the commissioned pieces be accessible or utilised in future? | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
|  | How will the project direct audiences to the archive utilised should they wish to access it in future? | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |
| Unexpected outcomes | ? | 0 | ? | Core Team/Artist survey & depth interviews | Core Team/Artist Survey: Core Team/Artist Depth interviews: ? | Staff time Evaluator time | Elinor Unwin Fieldwork Agency Regeneris Videographer |