08/11/2017

Turner Prize Events Meeting

Katy Fuller, Jenny Hutt, Lily Mellor, Mike Berriman, Rebecca Clark, Ben McKnight

Apologies: Chris Clay

- GUESTLIST

  - RSVP Responses
122 Yes RSVP on 08/11/17
JH to chase Jacqui Gay for names of 10 HCC x invites

10/11/17 – first deadline
LM to chase artists and art world list
JH to do group reminders (BBC, Arts Council, Hull 2017 board) and add-column in with a note for those we assume are coming
BM to speak to Bolton & Quinn to chase art world invitees

  - Accreditation
Guest wristband to say “Turner Prize 2017 Award Ceremony”
Black deboss with gold infill / Black deboss with no infill

RC to do contractor accreditation

  - Press
JH to send guest list to Hannah Morgan and Alison Kee, copy BM and B&Q

JH/BM to clarify B&Q invite list – send PDF invite to targeted critics and correspondents

- BBC

BBC guests on programme and inserts, 2-3 people on main programme 

BM to go back to Alison to actively pitch guests: 
16:50 Martin Green
17:45 Goldie
20:30 and 21:30 George Vasey and Sach Craddock
21:30 Cosey Fanni Tutti

LM to inform George and Sacha that they are doing the live programme from the Ferens at 20:30 (for 4 minutes) and 21:30 - 22:00. BM to push back on BBC.

JH/RC to go through schedule and input BBC World/BBC 4/World Tonight/Look North/BBC News

JH to get speech notes for Goldie and TATE

Martin welcome at 19:45, followed by Alex Farquharson. No speech from leader

- LM to speak to Chris Marr about Rosalind’s film – edited clips have been ok’d by Rosalind which can be shared with BBC

- Technical recce with BBC, HPSS and Durham AND all-in production meeting 
JH to confirm 17/11/2017 (suggest London come up on 07:20 train)
John Wilmott, Eimear McNamara, Alison Kee, Andrew Swann + Hull 2017

- PRESS

- Front Row - 28/29 November – BM awaiting confirmation 
No recce, but would need 2 hours at Ferens in Turner galleries 
George do pre-record in Hull and Sacha do live in London 
BM to chase for confirmation and more details

- BBC Radio 6 Music in live studio 01/12/2017 – 02/12/2017
Ferens FOH are charging £650 per day. LM to ask Simon to waive hire fee but send costs to cover staffing

- 4 x artists to be briefed on 05/12/2017 prior to the announcement. Brief to be sent in advance as well as briefed on the day
BM to arrange B&Q to do this / LM to contact artists about schedule

- Press file from 15:00 – 19:30 in Live Art Studio – who are the privileged few who know the winner? BM to confirm

- Briefing
Goldie, artists, fact sheet for presenters, Ferens staff, Maria Balshaw
BM to pull press briefings together and confirm time, location and who will do brief

- MB to test Wi-Fi in Trinity Square café

- JH to create schedule for Goldie

- MINSTER

- LM to confirm 350gsm place settings and 3 x logos to be printed on these. Names to be hand written

- JH to look at areas in Minster for volunteer break out area / Cry room for artists / storing kit for 28 x crew

- CC no longer likes the idea of the gauze
JH to speak to Lisa Mayes about branding lectern with Turner Prize 2017

- JH/LM to get quotes for T-Shirts, speak to Laura Smith about branding

- CATERING

JH to meet Saunts and select menu, w/c 16/11/2017
JH to confirm wine order with Saunts once menu is confirmed

- AFTER PARTY
2 x DJ spec booked out from HPSS for both locations
RC to complete a TEN for HSG – 11:00 – 02:00
JH to confirm and book SIA for Ferens / Minster / HSG

- BUDGET
£10,00	Lighting

£7,500	Sound / screens / staging / candelabras / flowers

- CONTRACTS 
RC to draft