Back To Ours

Made in Hull _ February 2017

Show Report Comments

| Name | Show | Comments |
| --- | --- | --- |
| Henri Duckworth | The Story of Mr B |  |
|  | Picture House |  |
|  | Joan & Hekima |  |
|  | The Red Shed |  |
|  | The Pigeon Detectives |  |
|  | Meet Fred |  |
|  | The Secret Gig |  |
| Louise Yates | The Story of Mr B | Archie - 6th form room small for future shows Winifred – drama room is a bit messy and dark on initial entrance The amount of volunteers and staff stood out as small audience – spaces were away form entrance to building so placing of box office, food and evaluation was important to overall audience experience |
|  | Picture House | Music in foyer needed. Volunteers as ushers in the theatre space, help with children on stairs. Market experiential element earlier |
|  | Joan & Hekima | Heating need in North Point Spare scanners and confirmation on box office presence Asks groups holding tickets to confirm 3 days in advance so tickets can be sold |
|  | The Red Shed | Tech spec to be double checked with companies. Expect bar queues at evening shows |
|  | The Pigeon Detectives | Freedom light for gigs and capacity to increase to 400/450 Pit barriers – increase mojo to either end with gate Too many staff and volunteers on entrance, stamps worked well |
|  | Meet Fred | Music in foyer Fire exit in Sirius theatre Disruption during Kingswood performance, young people and volunteers entering and exiting |
|  | The Secret Gig | Use HPSS to avoid H&S issues with touring equipment. Clarity on doors and show start time on ticket. |
| Thomas Freeth | The Story of Mr B |  |
|  | Picture House |  |
|  | Joan & Hekima |  |
|  | The Red Shed |  |
|  | The Pigeon Detectives |  |
|  | Meet Fred |  |
|  | The Secret Gig |  |
| Carys Tavener | The Story of Mr B | - Consider capacities and seating plans for productions with small children. - Test smaller, underused venue spaces' capacities before usage - Schedule more time to tidy classroom spaces |
|  | Picture House | - Outline expectations of TSM roles with more emphasis on the festival's universal language |
|  | Joan & Hekima | - Enquire as to artist evaluation/signage requirements prior to festival live dates - Check with artists again just before confirming hire list with supplier - Musicians require completely separate room to rehearse and sound check during prior production |
|  | The Red Shed | - Confirm technical riders with Touring/Technical Manager. - Schedule more efficient method of access to grid @ 'Archie' - Consider who and where with engineers (assign to venue or assign to show?) - Consider comms packs across all venues |
|  | The Pigeon Detectives | - Attain a more thorough risk assessment - Consider added risks (such as artist encouraging spectators' behaviour) |
|  | Meet Fred | - CT to arrange meeting with HPSS to spend time in Archbishop Sentamu's theatre for patching - Clarify in-house technician assistance before festival - Warn artists of venue hindrances (e.g. sound-proof control box) - Bar was flown in an out to focus (bounce focus disliked by all artists) - hire zargees |
|  | The Secret Gig | - Appoint TSM and/or operator to Secret Gigs. - Insist on thorough artist risk assessment |
| Lisa Mayes | The Story of Mr B |  |
|  | Picture House |  |
|  | Joan & Hekima |  |
|  | The Red Shed |  |
|  | The Pigeon Detectives |  |
|  | Meet Fred |  |
|  | The Secret Gig |  |
| Jo Charlton | The Story of Mr B |  |
|  | Picture House |  |
|  | Joan & Hekima |  |
|  | The Red Shed |  |
|  | The Pigeon Detectives |  |
|  | Meet Fred |  |
|  | The Secret Gig |  |
| Alix Johnson | The Story of Mr B |  |
|  | Picture House |  |
|  | Joan & Hekima |  |
|  | The Red Shed |  |
|  | The Pigeon Detectives |  |
|  | Meet Fred |  |
|  | The Secret Gig |  |
| James McGuire | The Story of Mr B |  |
|  | Picture House |  |
|  | Joan & Hekima |  |
|  | The Red Shed |  |
|  | The Pigeon Detectives |  |
|  | Meet Fred |  |
|  | The Secret Gig |  |