19.04.2017

R1BW Noise Management Meeting

Helen Thackeray		Hull City Council Events Team
Melissa McVeigh		Hull 2017
Jack May			BBC
Gary Lathan			BBC
Mike Johnson			BBC
Frankie Tee			BBC			
Chris Dunnachie		ERYC
Helen Shewan			ERYC
Matt Kilroy 			Vanguardia

Apologies: Chris Clay, Rob Spring

Resident updates

HT - Hull 2017 are holding 3 x resident’s meetings on 25/04, 28/04 and 29/04. Not about ticketing, only about updates. Tickets will be given to residents who are clearly affected. Tickets will not be allocated to caravan park.

HT - Ideally like to be able to say the levels of noise that will be generated but this is difficult to say.

HT - Sproatley has its own resident’s meetings – most vocal and most well attended.

MK – list of properties which will be affected or fall under the perimeter of the house. Undertaken basic predications – highest at 72 (?) rough calculation which doesn’t take into account topography. Subject to agreement, look at properties which are not under management of BC estate – set the noise limit of 70db LAW 15 minutes

4 properties affected:
Ellerby cottage, Crabtreee Lane, Lodge Farm (Sproatley) and Field House.

HT – liaised with Field House. Occupant has some care issues which need to be accounted for.

HT - confirmed Coniston to Sproatley road, Skirlaugh and Londesborough road will all receive notifications, including public meetings.

MK – Noise management plan, if there are any properties which are happy to be monitored that can be arrange. HT to publish the indicative locations at resident’s meetings.

HT – Spoken to all houses on the estate and arrangements have been made clear 
MK - based on predictions, the noise will not go over 75db.

MK – complaints side needs to be looked at.  Who goes out and monitors these?

HT – There will be a designated number for residents to call, this will come into event control and will be planned by the local authority/Hull 2017/EYRC. Message will go direct from event control to Vanguardia.

ACTION: JM to confirm number.

HT – we would expect ERYC to have a phone number and keep a record if further investigation is required post event.

MK – Vanguardia to follow up, monitor, take records and if levels are breached then source of noise is investigated. Sound checks are likely to dictate what is contributing to each location.

HT – Does EYRC have a webpage for FAQs? Hull 2017 can share the schedule so the hot line can answer

Friday 26th

14:00 - 17.30 for noise propagation
18:00 – 20:00 Sound checks for Saturday headliner

Vanguardia will be monitoring the sound check.

FT – typically they haven’t made any noise before 08:00.

HT – to speak to Methodist church in the vicinity of event site about moving their service on Sunday 28th as sound checks will take place in the morning

HT – haven’t informed residents of timings yet. Timings will either be included in the resident’s meetings or there will be a further letter sent out.

4 non-estate houses – information will be given to them by HT/CC when tickets are distributed (date TBC)

MK – Vanguardia will periodically monitor sound throughout the day. Complaints will take priority.

CD – Local authority to confirm a key representative and share with Gary Lathan, feed into event control.

JM – confirmed the event will finish at 22:00

MK – to amend and circulate noise management document

JM – confirmed there will be pyro.

JM – BBC will be offering ear plugs at welfare point or the information point (not unlimited)