Epicycle Team Meeting 21.06.2017

Attending: Lily Mellor, Katy Fuller, Hannah Williams Walton, Carys Tavener, Rachel Crow, Michael Berriman, Pippa Gardner, Michelle Evans

| To Do | Lead | Notes |
| --- | --- | --- |
| Finalise ticketing/non ticketing with Chris | KF |  |
| Circulate PID to team | LM |  |
| Equal opps forms for artists | LM/HWW | Can fill out manually when they are here. |
| Break down marketing £5k in to photography, film, etc. | RC |  |
| Chase more images/copy from CirkVOST for Marketing purposes | LM/HWW |  |
| Marketing timeline | RC | RC to liaise with Phil |
| PPL | CT |  |
| Send Contract to Tim and ask for EMP by mid-next week | KF | By Friday 23/06 |
| Answer Pearson Trustees’ queries | KF/HWW | After site visit on 23/06 |
| Liaise with Adam about Blue Badge Parking and Audio Description | LM | On site visit 23/06 |
| Liaise with Jan about transportation costs, flights (can Jan come on Monday?), accomm, timings, per diems/catering | LM/Adam | On site visit 23/06 |

- Trustees are keen for us NOT to ticket. Ticketing would add costs that wouldn’t be covered as it is a free event. Pearson is self-sufficient as there are lots of things around to do instead if it is too busy. Supporting local businesses/restaurants/bars.

- Q about the 500 deck chairs and controlling that – is it first come first served?

- For Info: The Sesh is the week before and The Hull Show in East Park is happening the same weekend, although this finishes at 20:30

- Can we stop people drinking? Public place. No alcohol sales included in our premise licence

MarComms

- Comms to start relevatively late – comms push in the final week before the show (beginning of Aug)

- Lots of local (avenues) marketing

- For Info: Contains Strong Language BBC announcement 17th July Hull and 24th July London. Tickets on sale from 24th.

- Two Hull 2017 deck chairs on site somewhere – well lit, not obstructing

- £7.5k – £1.5k sitedressing, £1k resident notification, £5k marketing – RC to look at how that can be broken down in to photography etc.

- Points to convey; FAQs, encourage people to go by bus/lack of parking, resident notification as quite disruptive, deck chair accessibility, mark the show as ‘Highly Visual’

Access

- Some wouldn’t be able to get in and out of deck chairs. We could provide a limited amount of chairs for access purposes – do they ask a Steward for a chair on arrival or can they book in advance?

- Possibility of blue badge parking

- Possibility of Audio Description

M&E

- No M&E budget attached

- Could do clickers on each entry/exit point for Pearson.

- Would like to collect audience contact details to send them an email survey, ideally 386.

- Equal opps for artists – could sign when they’re here