Turner Prize Core Team Meeting

05.10.2017

Katy Fuller, Lily Mellor, Laura Smith, Ian Read, Ben McKnight, Jenny Hutt, Rebecca Clark, Will Hutchinson

1. Legal

1a. Event Contracts

- Venue agreement required for the Minster, JH to share Jane’s details with WH

- Agreement for Goldie, KF to share talent contact with WH

1b. Learning Contracts

- IR to send WH list of artists /contractors / suppliers for educations for Learning Programme of events

2. Press

- Goldie - BM to speak to EB

- BM and JH are primary contacts for Eimear McNamara at the BBC (Press & Operations)

- Room for press to file - JH to confirm use of Minster office with Jane

3. Events

3a. Turner // Return - 16 November 18:00 - 23:00

- LM & IR to meet with KS

- IR to check capacity spaces (per gallery space) – 770 overall

- Entrance – both sets of doors open. Constructing new entrance or dressing new entrance?

- Can it be set up the night before? No storage for furniture and piano can’t move.

- IR to speak to Vicky Knightwaller regarding catering, JH to share contact with IR

- Speak to Ferens about PA system in studio, lapel mics, handheld mics etc.

- IR to enquire about opening the café for hot beverages

- IR to pull it together as a schedule and present to KS

3b.  Awards Night

- JH to set up meeting with Saunts Catering

- Clarity on the logistics of getting artist to Ferens from Minster

- KF to confirm budget for 05.12 with JH