PROJECT OVERVIEW – LGBT 50

| NAME OF PROJECT | LGBT 50 |
| --- | --- |
| PROJECT START - FINISH DATES | ? – 24/09/2017 |
| PROJECT LIVE DATES | 22/07/2017 - 29/07/2017 |
| COC PROJECT LEAD | Cian Smyth |
| PROJECT SUMMARY | From June: Duckie taking over shop in city centre as a base for happenings – workshops etc. 22 July: 50 Queers for 50 Years, presented by Duckie and Pride in Hull, 12noon Starts at Hull College Duckie will take part in Pride in Hull’s presentation of the 1st UK Pride parade featuring 50 handmade and oversized LGBT icons from Dusty Springfield to Freddie Mercury, Clare Balding to Quentin Crisp and a myriad of other stately homos of England. The parade will end with a Pride concert in Queen’s Gardens and a headline performance by Marc Almond. Parade = unticketed and free. Concert = tickets TBC. 22 – 29 July: A Moment in Time, Various venues across Hull A photography exhibition uses publicly-submitted photographs to tell the LGBT+ story before the decriminalisation of homosexuality in 1967 and in the 50 years since. 24 July: Lads ‘n’ Lasses, Fruit, Time TBC New piece of theatre written and performed by local young people’s theatre group Aposarts, around the topic of homophobia in school 25 July: Pride in Hull Film Festival, Kardomah 94, Time TBC 26 July: Comedy Night, Kardomah 94, Time TBC 27 July: Polari, Kardomah 94 Time TBC Paul Burston’s peerless LGBT literary salon. 27 July – 24 September: The House of Kings and Queens, Humber Street Gallery A specially commissioned exhibition of photography by Lee Price. Captured in Sierra Leone, where homosexuality remains illegal, Price’s powerful images offer a glimpse into The House where inhabitants can live without oppression, exposing what it means to be gay in Hull’s sister city Freetown. 29 July: A Duckie Summer Tea Party, Queen Victoria Square, From 2pm A Summer tea party by the inimitable Duckie features a 50 performer dance show by Gary Clarke and Yorkshire Dance, a cake making contest, special performances and dancing to the London Gay Big Band. Fancy waiters in black tie will be serving tea and cakes to hundreds of patrons while others dance the square into vibrant life. 29 July: Into the Light, A Gary Clarke Dance Project, Queen Victoria Square Yorkshire Dance and Duckie present a new work by Gary Clarke celebrating 50 years of queer culture involving participants from Hull LGBT community and friends. (inc 100-200 Yorkshire Dance recruited participants). 29 July: I Feel Love, Hull City Hall, 8 - 9.30pm BBC Radio 2 presents I Feel Love, a live concert from Hull City Hall broadcast on Radio 2 and Red Button which is part of the BBC’s Gay Britannia season. Presented by BBC Radio 1’s Scott Mills and Scissor Sisters’ front woman and Radio 2 presenter Ana Matronic, and will feature a stellar line-up of artists including Bright Light Bright Light, Will Young, Tom Robinson and stars of the West End stage. More artists to be announced. Expect an evening of anthems, torch songs and celebration. Ticketed. LGBT+ L&P Project, 15 June – 27 July To celebrate the 50th anniversary of the decriminalisation of homosexuality Hull 2017 are putting together a collection of writings connected to Hull and East Yorkshire’s LGBT community. We’re looking for ten writers to contribute. You don’t have to have written anything before, you just need a few good stories to tell – funny stories, sad stories, tough stories, tender stories – stories we don’t often hear, connected in some way to the LGBT experience. |
| TARGET AUDIENCES | - LGBT+ Audiences |
| CORE PROJECT TEAM | - Cian Smyth - Martin Green - Niccy Hallifax - Haitham Ridha - Aidan Lesser - Jenny Hutt - Sarah Moor - Bethany Watson - Alix Johnson - Ian Read - Nicola Taylor - Matthew Walton - Joanna Morley - Chris Clay - Mel McVeigh - Colin Renshaw |
| ARTISTS | - Gary Clark, Choreographer - Robin Whitmore, Duckie |
| HERITAGE PARTNERS (IF APPLICABLE) | - EJ Scott, Duckie |
| DELIVERY PARTNERS | - Colin Wilson, Hull Pride - Andy Train, Hull Pride - Anthony Cherry, BBC - Florence Griffiths, BBC - Simon Casson, Duckie - Dickie Eton, Duckie - Kirsty Redhead, Yorkshire Dance - Wieke Eringa, Yorkshire Dance |
| PROJECT SPECIFIC AIMS/OBJECTIVES TO MEASURE | - Within a festival of events celebrating LGBT culture, enable participants and audiences to explore LGBT themes and interact with people they wouldn’t normally have interacted with. - Create opportunities for intergenerational interactions exploring LGBT themes - Engage participants in a new dance work (marking the 50th Anniversary of the start of decriminalisation of homosexuality) to encourage a mass dance moment - Enable creative community engagement in LGBT heritage - Increase awareness of the 50th anniversary of the partial decriminalisation of homosexuality in England and Wales - Explore LGBT heritage from 1967 – 2017 through creative events and activities |
| HULL 2017 STRATEGIC OBJECTIVES THAT THE PROJECT IS CONTRIBUTING TO | High quality programme of arts, culture and heritage - 365 day of cultural programme that is ‘of the city’ yet outward looking and includes 60 commissions - Improving understanding and appreciation of Hull’s heritage Develop audiences - Increase total audiences for Hull's arts, cultural and heritage offer - Increase engagement and participation in arts and heritage amongst Hull residents - Increase the diversity of audiences for Hull’s arts and heritage offer Improve perceptions of Hull both internally and externally - Enhance positive media coverage of Hull’s arts and heritage offer - Increase in Hull residents who are proud to live in Hull and would speak positively about the city to others - Improve positive attitudes towards Hull as a place to live, study, visit and do business Strengthen Hull and East Riding economy - Increase visitor numbers to Hull Improve wellbeing through engagement and participation - Increase levels of happiness and enjoyment as a result of engaging with arts and culture - Increase levels of confidence and community cohesion among local audiences and participants Increase aspirations, abilities and knowledge of residents - Delivery of training and development opportunities to local residents through arts and culture initiatives |
| SUMMARY OF PROPOSED METHODS | June/July: Duckie Shop - Audience count (?) 22 July: 50 Queers for 50 Years (Parade and Concert) - Audience count (Pride doing) - Short audience survey (tablets/at event/with vols/collaborate with Pride in Hull) - Pride in Hull End of Project CCP report 22 – 29 July: A Moment in Time - Audience count (No. of sites??? Clickers – are vols already there?) - Short audience survey (paper/at event/with vols??) 24 July: Lads ‘n’ Lasses - Short audience survey (paper/at event/with vols/collaborate with Pride in Hull) - Audience count (Clicker/tickets) 25 July: Pride in Hull Film Festival - Short audience survey (paper/at event/with vols/collaborate with Pride in Hull) - Audience count (Clicker/tickets) 26 July: Comedy Night - Short audience survey (paper/at event/with vols/collaborate with Pride in Hull) - Audience count (Clicker/tickets) 27 July: Polari - Short audience survey (paper/at event/with vols/collaborate with Pride in Hull) - Audience count (Clicker/tickets) 27 July – 24 September: The House of Kings and Queens - In-gallery audience survey (HSG template adapted to show) - Audience count (Beam Counters) 29 July: A Duckie Summer Tea Party - Audience count (£900) - Audience contact detail collection (postcards?) 29 July: Into the Light, A Gary Clarke Dance Project - Audience Count (Same as Tea Party?) - Audience contact detail collection (postcards?) 29 July: I Feel Love - Audience contact detail collection (postcards?) - Post-event audience survey to ticket bookers + collected contacts via Facebook ad (online) - Audience Count (ticket sales/redemption) LGBT+ L&P Project - L&P participants survey at final workshop - Interview with project leader/artist - End of project L&P report Whole Event - End of Project Report from Duckie and Yorkshire Dance (?) - Post-Event CATI Survey (incorporating HLF and Spirit outcomes) - Project Monitoring Workbook |

PROJECT MONITORING & EVALUATION PLAN – Project Specific Objectives

| AIMS | OBJECTIVES | OUTPUTS & OUTCOMES | WHO YOU’LL GATHER INFORMATION FROM | METHOD OF DATA COLLECTION | WHEN TO GATHER DATA | RESOURCES | PERSON (S) RESPONSIBLE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Within a festival of events celebrating LGBT culture, enable participants and audiences to explore LGBT themes and interact with people they wouldn’t normally have interacted with. | Create opportunities for intergenerational interactions exploring LGBT themes | No. of audience/participants members agree/strongly agree that events “...gave me the opportunity to interact with other people who I wouldn't have normally interacted with'” | Audience/Participants | Audience surveys at event and post-event Participant survey | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
|  |  | No. of audience/participants members agree/strongly agree that events: “...made me think more positively about people from other generations” and “…inspired me to talk to people from other generations about the stories presented” | Audience/Participants | Audience surveys at event and post-event Participant survey | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
|  |  | Artists report creating opportunities for intergeneration interactions | Artists (Duckie, Yorkshire Dance) | End of Project Report | W/C 29th July | Staff Time | Pippa Gardner |
|  | Engage participants in a new dance work to encourage a mass dance moment | Engage up to 42 participants from the LGBT community and its’ friends | Core Project Team | Project Monitoring Workbook | Ongoing | Staff Time | Pippa Gardner |
|  |  | A new dance work which explores heritage themes including marking the 50th Anniversary of the start of decriminalisation of homosexuality | Core Project Team | Project Monitoring Workbook | Ongoing | Staff Time | Pippa Gardner |
|  |  | Proportion of audience members who agree or strongly agree that the event encouraged them to dance | Audience Members | Audience surveys at event and post-event | 29 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
| Enable creative community engagement in LGBT heritage | Increase awareness of the 50th anniversary of the partial decriminalisation of homosexuality in England and Wales | No. of audience demonstrating awareness of 2017 as the 50th anniversary of the partial decriminalisation of homosexuality in England and Wales | Audience Members | Audience surveys at event and post-event | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
|  | Explore LGBT heritage from 1967 – 2017 through creative events and activities | No. of audience members reporting an increase in understanding and appreciation of Hull’s LGBT+ heritage | Audience Members | Audience surveys at event and post-event | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
|  |  | Artists report exploring heritage themes through their commissions | Artists (Duckie, Yorkshire Dance) | End of Project Report | W/C 29th July | Staff Time | Pippa Gardner |

PROJECT MONITORING & EVALUATION PLAN – Hull 2017 Strategic Objectives

| AIMS | OBJECTIVES | OUTPUTS & OUTCOMES | WHO YOU’LL GATHER INFORMATION FROM | METHOD OF DATA COLLECTION | WHEN TO GATHER DATA | RESOURCES | PERSON (S) RESPONSIBLE |
| --- | --- | --- | --- | --- | --- | --- | --- |
| High quality programme of arts, culture and heritage | 365 day of cultural programme that is ‘of the city’ yet outward looking and includes 60 commissions | No. of new commissions | Core Project Team | Project Monitoring Workbook | Ongoing | Staff Time | Pippa Gardner |
|  |  | No. of events within LGBT50 Festival | Core Project Team | Project Monitoring Workbook | Ongoing | Staff Time | Pippa Gardner |
|  | Improving understanding and appreciation of Hull’s heritage | No. of events within the festival exploring a heritage theme | Core Project Team | Project Monitoring Workbook | Ongoing | Staff Time | Pippa Gardner |
|  |  | No. of audience members reporting an increase in understanding and appreciation of Hull’s LGBT+ heritage | Audience Members | Audience surveys at event and post-event | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
| Develop audiences | Increase total audiences for Hull's arts, cultural and heritage offer | No. of audience at events | Pride in Hull / Direct at Events | Various (Clickers, Beam Counter, Fieldworkers) | 22 July – 24 Sep | Clickers, Beam Counters, Paid Fieldworkers | Pippa Gardner |
|  | Increase engagement and participation in arts and heritage amongst Hull residents | No. of audience/participants at events from Hull | Audience/Participants | Audience surveys at event and post-event Participant survey | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
|  | Increase the diversity of audiences for Hull’s arts and heritage offer | Diversity of audiences/participants at events | Audience/Participants | Audience surveys at event and post-event Participant survey | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
| Improve perceptions of Hull both internally and externally | Enhance positive media coverage of Hull’s arts and heritage offer | No. of positive media coverage of LGBT50 events in Hull | Media Monitoring | Gorkana | August 2017 | Staff Time | Alix Johnson |
|  | Increase in Hull residents who are proud to live in Hull and would speak positively about the city to others | Increase in positive responses to proud to live in Hull and would speak positively about the city to others | Hull Residents | Citywide Survey | Jan 2018 | Staff Time, Research Agency Contract | Elinor Unwin |
|  | Improve positive attitudes towards Hull as a place to live, study, visit and do business | Increase in positive responses to attitudes towards Hull | Hull Residents | Citywide Survey | Jan 2018 | Staff Time, Research Agency Contract | Elinor Unwin |
| Strengthen Hull and East Riding economy | Increase visitor numbers to Hull | No. of audience who are visitors to Hull | Audience | Audience surveys at event and post-event | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
| Improve wellbeing through engagement and participation | Increase levels of happiness and enjoyment as a result of engaging with arts and culture | No. of participants reporting an increase in happiness as a result of events | Participants | Participant survey | W/C 29th July | Staff Time | Pippa Gardner |
|  |  | No. of audience/participants reporting the events as an enjoyable experience | Audience/Participants | Audience surveys at event and post-event Participant survey | 22 July – 6 August | Staff Time, Volunteer Time, Tablets, Printed Surveys | Pippa Gardner |
|  | Increase levels of confidence and community cohesion among local audiences and participants | No. of participants reporting an increase in confidence levels as a result of taking part | Participants | Participant Survey | W/C 29th July | Staff Time | Pippa Gardner |
| Increase aspirations, abilities and knowledge of residents | Delivery of training and development opportunities to local residents through arts and culture initiatives | No. of participants in participatory elements of festival events | Core Project Team | Project Monitoring Workbook | Ongoing | Staff Time | Pippa Gardner |