## Overview Exhibition Hall
| Suggested Date |  | Title | Status | Comments | External Contact | Location (other than exhibition hall) |  | Staffing
British Museum | w/c 12/12 |  | Installation
| Mon 02/01/2016 |  | Opening Night BM
| Tues 03/01/2016 |  | British Museum |  |  | Una Helle | Exhibition Hall | The greatest gathering of artistic talent ever seen in Hull - in one exhibition. From Dürer to Degas, Michelangelo to Matisse, Rembrandt to Riley, this exhibition examines the process and practice of drawing, illustrated by a selection of work created over 500 years. Lines of thought uncovers the genius behind the drawings of some of art's most prominent masters giving us fresh insight into the creative impulse of some of the world's greatest artists.
| Tues 28/02 |  | Last Day British Museum (8 weeks) |  |  | Una Helle | Exhibition Hall
| Wed 1/3 - Mon 6/3 |  | Demounting & Transport (6 March) | TBC
| Tues 7/3 - Mon 20/3 |  | Repairs | TBC
National Portrait Gallery | 20/3 - 27/3 |  | Installation | TBC
| 2016-03-28 |  | Opening Night NPG
| 29/3 - 11/6 (10 weeks) |  | Paul Smith to J K Rowling: BP Portrait Award Commissions from the National Portrait Gallery |  | changed start date from 23/03 due to concerns over repair times for exhib. Hall | Laura Downs | Exhibition Hall | A chance to take an intimate look at the creative journey of some of the UK’s leading cultural visionaries. Listen to the challenges and the obstacles they faced and how this shaped them into the person they are today and be part of the conversation around a cultural vision for the future.
| 2016-06-11 |  | Last Day of Exhibition (Sunday) (11 weeks) |  |  |  | Exhibition Hall
| Mon 12/6 - Thu 15/6 |  | Demounting/ | TBC
| Fri 16/6 - Fri 23/6 |  | Repairs | TBC
Larkin | Sat 24/6 - Fri 30/6 |  | Installation | TBC
| Sat 1 July |  | Opening Night Larkin | TBC
| July |  | Larkin | Confirmed |  |  | Exhibition Hall
| August |  | Larkin | Confirmed |  |  | Exhibition Hall
| September |  | Larkin | Confirmed |  |  | Exhibition Hall
| 2016-10-01 |  | Last Day of Exhibition (Sunday) 13 weeks
| Mo 2/10 - Fri 6/10 |  | Demounting | TBC |  |  | Exhibition Hall
| Sat 7/10 - Sun 15/10 |  | Repair | TBC
UK Government Art Collection | Mon 16/10 - Wed 18/10 |  | Installation | TBC
| 2016-10-19 | 2016-10-12 | Opening Night Government Art Collections | TBC
| October |  | Government Art Collection | TBC
| November |  | Government Art Collection | TBC |  |  | Exhibition Hall
| Sun 26/11 | 2016-11-19 | Last Day of Exhibition (Sunday) (5 weeks) | TBC
| Mon 27/11- Thu 30/11 | 20/11 - 23/11 | Demounting | TBC |  |  | Exhibition Hall
| Fr 1/12 - Fr 8/12 | 24/11- 27/11 | Repair | TBC
Cuneo | Sat 9/12 - Wed 13/12 |  | Installation | TBC
| Th 14/12 |  | Opening Night Cuneo
| December - March |  | Cuneo | TBC |  |  | Exhibition Hall
Other Locations
| April - Oct |  | Steinunn: Nordic reflections on Hull | in discussion |  | Steinunn Thorarinsdottir | Outside
Deferred
|  |  | British Mercantile Maritime Memorial Collection | moved to 2018 |  |  | we have the space, they have picture, needs a curator (maybe Robb Robinson?) - JB interesting, says Hull, first showing
| March - June |  | Hessle Road Photographs | depending on success of funding application |  | Alec Gill & Paul Beriff | various locations on campus

## Sheet1
NPG
full confirmation on Wedn 27/7 | synopsis, title, image
Abigail kokoci
| come up with title | speak to John Bernasconi